# SAP Business One Contract Management Add-On

Document 1: Core Requirements & Database Schema

# 1. Executive Summary

This document provides comprehensive specifications for the Contract Management Add-On for SAP Business One, including detailed database schemas, field specifications, and integration requirements with direct HANA database capabilities.

## 1.1 Key Features

- Complete contract lifecycle management from creation to closure

- Interim Certificate Payment (ICP) module with progressive billing

- Direct HANA database read/write operations for performance

- Bilingual support (Arabic/English) throughout the system

- Integration with SAP B1 Business Partners, Items, and Financials

- Comprehensive workflow management with approval processes

- Advanced financial calculations with deductions and retentions

# 2. Database Architecture

The system uses 14 User-Defined Tables (UDTs) in SAP Business One, with direct HANA database integration for optimized performance. All tables follow SAP B1 naming conventions with @ prefix.

## 2.1 Contract Header Table (RVCM_CNTRCT)

Main table for contract master data. Table Code: @RVCM_CNTRCT

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 20 | Auto-generated contract number (PK) |
| Contract Name | U_ContractName | Alphanumeric | 254 | Contract name (Arabic/English) |
| Contract Name AR | U_ContractNameAR | Alphanumeric | 254 | Contract name in Arabic |
| Customer Code | U_CardCode | Alphanumeric | 15 | Business Partner code (FK to OCRD) |
| Customer Name | U_CardName | Alphanumeric | 100 | Business Partner name (auto-filled) |
| Customer Type | U_CardType | Alphanumeric | 1 | Client type: C=Customer, S=Supplier, L=Lead |
| Contact Person | U_CntctCode | Numeric | 11 | Contact person ID (FK to OCPR) |
| Project Number | U_ProjectNum | Alphanumeric | 20 | Project number reference |
| Project Name | U_ProjectName | Alphanumeric | 100 | Project name |
| Sector | U_Sector | Alphanumeric | 50 | Business sector classification |
| User Type | U_UserType | Alphanumeric | 30 | End user type/category |
| Unit Number | U_UnitNumber | Alphanumeric | 20 | Unit/property number |
| Region | U_Region | Alphanumeric | 50 | Geographic region |
| Contract Type | U_ContractType | Alphanumeric | 20 | Type: Sales, Service, Maintenance, Construction |
| Start Date | U_StartDate | Date | 8 | Contract start date |
| End Date | U_EndDate | Date | 8 | Contract end date |
| Duration | U_Duration | Numeric | 11 | Contract duration in days (calculated) |
| Contract Value | U_ContractVal | Sum | 19,6 | Total contract value before tax |
| Currency | U_Currency | Alphanumeric | 3 | Currency code (FK to OCRN) |
| Tax Rate | U_TaxRate | Rate | 19,6 | Default tax rate percentage |
| Tax Amount | U_TaxAmount | Sum | 19,6 | Total tax amount (calculated) |
| Total Value | U_TotalValue | Sum | 19,6 | Contract value including tax |
| Price Quote Ref | U_QuoteRef | Alphanumeric | 50 | Reference to price quotation |
| Status | U_Status | Alphanumeric | 1 | D=Draft, A=Active, H=OnHold, C=Completed, X=Cancelled |
| Approval Status | U_ApprovalSts | Alphanumeric | 1 | P=Pending, A=Approved, R=Rejected |
| Created By | U_CreatedBy | Numeric | 11 | User ID who created record |
| Created Date | U_CreateDate | Date | 8 | Creation date |
| Modified By | U_ModifiedBy | Numeric | 11 | User ID who last modified |
| Modified Date | U_ModifyDate | Date | 8 | Last modification date |
| Remarks | U_Remarks | Memo |  | General remarks/notes |

## 2.2 Contract Lines Table (RVCM_CNTRCT1)

Contract line items for services, materials, or milestones. Table Code: @RVCM_CNTRCT1

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Parent Key | Code | Alphanumeric | 20 | Contract code (FK to @RVCM_CNTRCT.Code) |
| Line Number | LineNum | Numeric | 11 | Sequential line number |
| Item Code | U_ItemCode | Alphanumeric | 50 | Item/Service code (FK to OITM) |
| Item Description | U_ItemDesc | Alphanumeric | 254 | Item description |
| Item Description AR | U_ItemDescAR | Alphanumeric | 254 | Item description in Arabic |
| Cost Code | U_CostCode | Alphanumeric | 20 | Cost center/WBS code |
| Stage | U_Stage | Alphanumeric | 50 | Project stage/phase |
| Probability % | U_Probability | Rate | 19,6 | Probability factor percentage |
| Quantity | U_Quantity | Quantity | 19,6 | Quantity |
| Unit | U_Unit | Alphanumeric | 10 | Unit of measure |
| Unit Price | U_UnitPrice | Price | 19,6 | Price per unit |
| Discount % | U_DiscountPct | Rate | 19,6 | Line discount percentage |
| Line Total | U_LineTotal | Sum | 19,6 | Line total before tax (calculated) |
| Tax Code | U_TaxCode | Alphanumeric | 8 | Tax code (FK to OSTC) |
| Tax Rate | U_TaxRate | Rate | 19,6 | Line tax rate |
| Tax Amount | U_TaxAmount | Sum | 19,6 | Line tax amount (calculated) |
| Line Total Inc | U_LineTotalInc | Sum | 19,6 | Line total including tax |
| Planned Date | U_PlannedDate | Date | 8 | Planned execution/delivery date |
| Actual Date | U_ActualDate | Date | 8 | Actual execution/delivery date |
| Status | U_LineStatus | Alphanumeric | 1 | P=Planned, I=InProgress, C=Completed |
| Remarks | U_LineRemarks | Memo |  | Line-specific remarks |

## 2.3 ICP Header Table (RVCM_ICP)

Interim Certificate Payment header for progressive billing. Table Code: @RVCM_ICP

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 20 | Auto-generated ICP number (PK) |
| ICP Number | U_ICPNumber | Alphanumeric | 20 | Display ICP number |
| Contract Code | U_ContractCode | Alphanumeric | 20 | Contract reference (FK to @RVCM_CNTRCT.Code) |
| Customer Code | U_CardCode | Alphanumeric | 15 | Business Partner (auto from contract) |
| Certificate Date | U_CertDate | Date | 8 | ICP issue date |
| Period From | U_PeriodFrom | Date | 8 | Work period start date |
| Period To | U_PeriodTo | Date | 8 | Work period end date |
| Work Complete % | U_WorkCompPct | Rate | 19,6 | Overall work completion percentage |
| This Period Value | U_PeriodValue | Sum | 19,6 | Work done this period |
| Cumulative Value | U_CumValue | Sum | 19,6 | Cumulative work to date |
| Advance Deduct | U_AdvDeduct | Sum | 19,6 | Advance payment deduction |
| Retention % | U_RetentionPct | Rate | 19,6 | Retention percentage |
| Retention Amount | U_RetentionAmt | Sum | 19,6 | Retention amount (calculated) |
| Material Deduct | U_MatDeduct | Sum | 19,6 | Material deduction |
| Other Deduct | U_OtherDeduct | Sum | 19,6 | Other deductions |
| VAT Amount | U_VATAmount | Sum | 19,6 | VAT/Tax amount |
| Net Payment | U_NetPayment | Sum | 19,6 | Net payment due (calculated) |
| Status | U_Status | Alphanumeric | 1 | D=Draft, S=Submitted, A=Approved, P=Paid, R=Rejected |
| Approval Status | U_ApprovalSts | Alphanumeric | 1 | P=Pending, A=Approved, R=Rejected |
| Invoice DocEntry | U_InvoiceEntry | Numeric | 11 | Generated AR Invoice DocEntry |
| Created By | U_CreatedBy | Numeric | 11 | User who created |
| Created Date | U_CreateDate | Date | 8 | Creation date |
| Approved By | U_ApprovedBy | Numeric | 11 | User who approved |
| Approved Date | U_ApproveDate | Date | 8 | Approval date |
| Remarks | U_Remarks | Memo |  | Certificate remarks |

## 2.4 ICP Lines Table (RVCM_ICP1)

Detailed line items for each ICP showing work progress. Table Code: @RVCM_ICP1

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Parent Key | Code | Alphanumeric | 20 | ICP code (FK to @RVCM_ICP.Code) |
| Line Number | LineNum | Numeric | 11 | Line number |
| Contract Line | U_CntrctLine | Numeric | 11 | Contract line reference (FK to @RVCM_CNTRCT1.LineNum) |
| Item Code | U_ItemCode | Alphanumeric | 50 | Item code (from contract line) |
| Description | U_Desc | Alphanumeric | 254 | Work description |
| Description AR | U_DescAR | Alphanumeric | 254 | Arabic description |
| Contract Qty | U_ContractQty | Quantity | 19,6 | Total contract quantity |
| Unit Price | U_UnitPrice | Price | 19,6 | Unit price from contract |
| Previous Qty | U_PrevQty | Quantity | 19,6 | Cumulative quantity from previous ICPs |
| This Period Qty | U_ThisQty | Quantity | 19,6 | Quantity completed this period |
| Cumulative Qty | U_CumQty | Quantity | 19,6 | Total cumulative quantity |
| % Complete | U_PctComplete | Rate | 19,6 | Completion percentage (calculated) |
| This Period Value | U_ThisValue | Sum | 19,6 | Value of work this period |
| Cumulative Value | U_CumValue | Sum | 19,6 | Total cumulative value |
| Remarks | U_LineRemarks | Memo |  | Line remarks |

## 2.5 Payment Schedule Table (RVCM_PYMSCH)

Payment milestones and schedules. Table Code: @RVCM_PYMSCH

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Parent Key | Code | Alphanumeric | 20 | Contract code (FK) |
| Line Number | LineNum | Numeric | 11 | Payment line number |
| Milestone | U_Milestone | Alphanumeric | 100 | Payment milestone name |
| Due Date | U_DueDate | Date | 8 | Payment due date |
| Amount | U_Amount | Sum | 19,6 | Payment amount |
| Status | U_Status | Alphanumeric | 1 | P=Pending, R=Received, O=Overdue |
| Paid Amount | U_PaidAmount | Sum | 19,6 | Amount actually paid |
| Payment Date | U_PaymentDate | Date | 8 | Actual payment date |
| Invoice Entry | U_InvoiceEntry | Numeric | 11 | AR Invoice DocEntry |
| Receipt Entry | U_ReceiptEntry | Numeric | 11 | Incoming Payment DocEntry |

## 2.6 Retention Table (RVCM_RETEN)

Tracks retention amounts and releases. Table Code: @RVCM_RETEN

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 20 | Retention record code (PK) |
| Contract Code | U_ContractCode | Alphanumeric | 20 | Contract reference (FK) |
| ICP Code | U_ICPCode | Alphanumeric | 20 | ICP reference (FK) |
| Retention % | U_RetentionPct | Rate | 19,6 | Retention percentage |
| Retained Amount | U_RetainedAmt | Sum | 19,6 | Amount retained |
| Released Amount | U_ReleasedAmt | Sum | 19,6 | Amount released |
| Balance | U_Balance | Sum | 19,6 | Retention balance (calculated) |
| Release Date | U_ReleaseDate | Date | 8 | Date of retention release |
| Release Reason | U_ReleaseReason | Alphanumeric | 100 | Reason for release |
| Status | U_Status | Alphanumeric | 1 | H=Held, R=Released, P=PartialRelease |

## 2.7 Deductions Table (RVCM_DEDUCT)

Various deductions applied to contracts or ICPs. Table Code: @RVCM_DEDUCT

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Parent Key | Code | Alphanumeric | 20 | Contract or ICP code (FK) |
| Line Number | LineNum | Numeric | 11 | Deduction line number |
| Deduction Type | U_DeductType | Alphanumeric | 20 | Type: Advance, Penalty, Material, Insurance, Other |
| Description | U_Description | Alphanumeric | 200 | Deduction description |
| Amount | U_Amount | Sum | 19,6 | Deduction amount |
| Applied Date | U_AppliedDate | Date | 8 | Date deduction applied |
| GL Account | U_GLAccount | Alphanumeric | 15 | G/L account for deduction |
| Remarks | U_Remarks | Memo |  | Additional notes |

# 3. Additional Supporting Tables

## 3.1 Workflow History Table (RVCM_WFHIST)

Tracks workflow state changes and approvals. Table Code: @RVCM_WFHIST

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 20 | Workflow record code (PK) |
| Object Type | U_ObjectType | Alphanumeric | 20 | Type: Contract, ICP |
| Object Code | U_ObjectCode | Alphanumeric | 20 | Reference to object |
| Action | U_Action | Alphanumeric | 30 | Action: Created, Submitted, Approved, Rejected, Modified |
| From Status | U_FromStatus | Alphanumeric | 20 | Previous status |
| To Status | U_ToStatus | Alphanumeric | 20 | New status |
| Action By | U_ActionBy | Numeric | 11 | User who performed action |
| Action Date | U_ActionDate | Date | 8 | Date of action |
| Comments | U_Comments | Memo |  | Action comments |

## 3.2 Attachments Table (RVCM_ATTACH)

Manages document attachments. Table Code: @RVCM_ATTACH

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Parent Key | Code | Alphanumeric | 20 | Parent object code (FK) |
| Line Number | LineNum | Numeric | 11 | Attachment line |
| File Name | U_FileName | Alphanumeric | 254 | Original file name |
| File Path | U_FilePath | Alphanumeric | 254 | Path to stored file |
| File Type | U_FileType | Alphanumeric | 20 | File extension/type |
| File Size | U_FileSize | Numeric | 11 | File size in bytes |
| Uploaded By | U_UploadedBy | Numeric | 11 | User who uploaded |
| Upload Date | U_UploadDate | Date | 8 | Upload date |

## 3.3 Contract Terms Table (RVCM_TERMS)

Stores specific contract terms and conditions. Table Code: @RVCM_TERMS

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Parent Key | Code | Alphanumeric | 20 | Contract code (FK) |
| Line Number | LineNum | Numeric | 11 | Term line number |
| Term Type | U_TermType | Alphanumeric | 30 | Type: Payment, Warranty, Penalty, Delivery, Other |
| Term Description | U_TermDesc | Memo |  | Term description |
| Value | U_Value | Alphanumeric | 100 | Term value/specification |
| Mandatory | U_Mandatory | Alphanumeric | 1 | Y=Yes, N=No |

## 3.4 Amendments Table (RVCM_AMEND)

Tracks contract amendments/variations. Table Code: @RVCM_AMEND

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 20 | Amendment code (PK) |
| Contract Code | U_ContractCode | Alphanumeric | 20 | Contract reference (FK) |
| Amendment No | U_AmendmentNo | Numeric | 11 | Sequential amendment number |
| Amendment Date | U_AmendDate | Date | 8 | Amendment date |
| Reason | U_Reason | Alphanumeric | 200 | Reason for amendment |
| Value Change | U_ValueChange | Sum | 19,6 | Change in contract value (+ or -) |
| Time Extension | U_TimeExtension | Numeric | 11 | Days extended |
| New End Date | U_NewEndDate | Date | 8 | Revised end date |
| Status | U_Status | Alphanumeric | 1 | D=Draft, A=Approved, R=Rejected |
| Description | U_Description | Memo |  | Detailed amendment description |

## 3.5 Guarantees Table (RVCM_GUARNT)

Manages performance bonds and bank guarantees. Table Code: @RVCM_GUARNT

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 20 | Guarantee code (PK) |
| Contract Code | U_ContractCode | Alphanumeric | 20 | Contract reference (FK) |
| Guarantee Type | U_GuaranteeType | Alphanumeric | 30 | Type: Performance, Advance Payment, Retention, Warranty |
| Guarantee No | U_GuaranteeNo | Alphanumeric | 50 | Bank guarantee number |
| Issuing Bank | U_IssuingBank | Alphanumeric | 100 | Bank name |
| Amount | U_Amount | Sum | 19,6 | Guarantee amount |
| Issue Date | U_IssueDate | Date | 8 | Guarantee issue date |
| Expiry Date | U_ExpiryDate | Date | 8 | Guarantee expiry date |
| Status | U_Status | Alphanumeric | 1 | A=Active, E=Expired, R=Released, X=Cancelled |
| Release Date | U_ReleaseDate | Date | 8 | Date guarantee released |
| Remarks | U_Remarks | Memo |  | Additional notes |

## 3.6 Insurance Table (RVCM_INSURE)

Tracks insurance policies related to contracts. Table Code: @RVCM_INSURE

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 20 | Insurance record code (PK) |
| Contract Code | U_ContractCode | Alphanumeric | 20 | Contract reference (FK) |
| Policy Type | U_PolicyType | Alphanumeric | 50 | Type: Liability, Property, Workers Comp, etc. |
| Policy Number | U_PolicyNo | Alphanumeric | 50 | Insurance policy number |
| Insurance Company | U_InsuranceComp | Alphanumeric | 100 | Insurance provider name |
| Coverage Amount | U_CoverageAmt | Sum | 19,6 | Coverage amount |
| Premium | U_Premium | Sum | 19,6 | Insurance premium paid |
| Effective Date | U_EffectiveDate | Date | 8 | Policy effective date |
| Expiry Date | U_ExpiryDate | Date | 8 | Policy expiry date |
| Status | U_Status | Alphanumeric | 1 | A=Active, E=Expired, X=Cancelled |

## 3.7 Configuration Table (RVCM_CONFIG)

System configuration and settings. Table Code: @RVCM_CONFIG

| Field Name | SAP Field | Data Type | Size | Description |
| --- | --- | --- | --- | --- |
| Code | Code | Alphanumeric | 50 | Configuration key (PK) |
| Config Value | U_Value | Alphanumeric | 254 | Configuration value |
| Description | U_Description | Alphanumeric | 200 | Setting description |
| Category | U_Category | Alphanumeric | 50 | Setting category |
| Data Type | U_DataType | Alphanumeric | 20 | Value data type: String, Number, Boolean, Date |
| Modified By | U_ModifiedBy | Numeric | 11 | Last modifier |
| Modified Date | U_ModifyDate | Date | 8 | Last modification date |

# 4. Database Relationships

The following diagram shows key relationships between tables:

- RVCM_CNTRCT (Contract Header) → RVCM_CNTRCT1 (Contract Lines): One-to-Many

- RVCM_CNTRCT → RVCM_ICP (ICP Header): One-to-Many

- RVCM_ICP → RVCM_ICP1 (ICP Lines): One-to-Many

- RVCM_CNTRCT → RVCM_PYMSCH (Payment Schedule): One-to-Many

- RVCM_CNTRCT → RVCM_RETEN (Retention): One-to-Many

- RVCM_CNTRCT/RVCM_ICP → RVCM_DEDUCT (Deductions): Many-to-Many

- RVCM_CNTRCT → RVCM_AMEND (Amendments): One-to-Many

- RVCM_CNTRCT → RVCM_GUARNT (Guarantees): One-to-Many

- RVCM_CNTRCT → RVCM_INSURE (Insurance): One-to-Many

- RVCM_CNTRCT → RVCM_TERMS (Contract Terms): One-to-Many

- Any Table → RVCM_ATTACH (Attachments): One-to-Many

- Any Table → RVCM_WFHIST (Workflow History): One-to-Many

# 5. Integration with SAP B1

## 5.1 Business Partner Integration

- U_CardCode links to OCRD (Business Partners master)

- U_CntctCode links to OCPR (Contact Persons)

- Auto-populate customer name, address, contact details

## 5.2 Item Master Integration

- U_ItemCode links to OITM (Items master)

- Pull item descriptions, units, and pricing

- Support both inventory items and services

## 5.3 Financial Integration

- U_Currency links to OCRN (Currencies)

- U_TaxCode links to OSTC (Tax Codes)

- Auto-generate AR Invoices (OINV) from approved ICPs

- Link to Incoming Payments (ORCT) for payment tracking

- U_GLAccount links to OACT (Chart of Accounts)

## 5.4 User Integration

- U_CreatedBy, U_ModifiedBy, U_ApprovedBy link to OUSR (Users)

- Workflow approval uses SAP B1 authorization system

# 6. Direct HANA Database Operations

The add-on implements direct HANA database read/write capabilities for enhanced performance:

## 6.1 HANA Connection

- Direct connection to HANA database using ODBC/JDBC drivers

- Connection pooling for optimal performance

- Secure authentication using SAP B1 credentials

- Transaction management for data consistency

## 6.2 Read Operations

- Direct SQL queries for faster data retrieval

- Optimized joins across contract, ICP, and master data tables

- Parameterized queries for security against SQL injection

- Cached queries for frequently accessed data

## 6.3 Write Operations

- Direct INSERT/UPDATE/DELETE operations on UDTs

- Batch operations for bulk data processing

- Transaction rollback on errors

- Audit trail maintenance for all modifications

## 6.4 Stored Procedures

- Complex calculations executed on HANA for performance

- ICP calculation procedures for cumulative values

- Retention and deduction calculation procedures

- Report generation procedures for dashboards

# 7. Indexing Strategy

Recommended indexes for optimal performance:

## 7.1 Primary Indexes

- All Code fields (Primary Keys): Clustered index

- All LineNum fields in child tables: Non-clustered index

## 7.2 Foreign Key Indexes

- U_CardCode: Non-clustered index for Business Partner lookups

- U_ContractCode: Non-clustered index for contract relationships

- U_ICPCode: Non-clustered index for ICP relationships

- U_ItemCode: Non-clustered index for item lookups

## 7.3 Date Indexes

- U_CreateDate: Non-clustered index for date range queries

- U_StartDate, U_EndDate: Composite index for contract period queries

- U_CertDate: Non-clustered index for ICP date filtering

## 7.4 Status Indexes

- U_Status fields: Non-clustered index for status filtering

- U_ApprovalSts: Non-clustered index for approval workflows

=== END OF DOCUMENT 1 ===

Core Requirements & Database Schema

Document 2: Data Models & APIs

# 1. Overview

This document specifies the data models, API integration points, and data access patterns for the Contract Management Add-On. It covers DI API usage, Service Layer REST endpoints, and direct HANA database access.

# 2. SAP Business One DI API Integration

The add-on uses the DI API for creating and managing UDOs (User-Defined Objects) and integrating with standard SAP B1 objects.

## 2.1 UDO Definition - Contract Management

C# code for creating the Contract Management UDO:

// Contract Management UDO Creation SAPbobsCOM.UserObjectsMD oUserObjectMD = (SAPbobsCOM.UserObjectsMD)oCompany.GetBusinessObject(     SAPbobsCOM.BoObjectTypes.oUserObjectsMD);  try {     // Check if UDO already exists     if (oUserObjectMD.GetByKey("RVCM_CNTRCT"))     {         Console.WriteLine("Contract UDO already exists");         return;     }      // Set UDO properties     oUserObjectMD.Code = "RVCM_CNTRCT";     oUserObjectMD.Name = "Contract Management";     oUserObjectMD.ObjectType = SAPbobsCOM.BoUDOObjType.boud_MasterData;     oUserObjectMD.TableName = "RVCM_CNTRCT";          // Enable document management     oUserObjectMD.CanArchive = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanCancel = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanClose = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanDelete = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanFind = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanLog = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.ManageSeries = SAPbobsCOM.BoYesNoEnum.tYES;          // Find/Cancel/Close authorization     oUserObjectMD.CanYearTransfer = SAPbobsCOM.BoYesNoEnum.tYES;          // Child tables     oUserObjectMD.ChildTables.TableName = "RVCM_CNTRCT1";     oUserObjectMD.ChildTables.Add();          // Add to system     int result = oUserObjectMD.Add();          if (result != 0)     {         int errCode;         string errMsg;         oCompany.GetLastError(out errCode, out errMsg);         Console.WriteLine($"Error creating UDO: {errCode} - {errMsg}");     }     else     {         Console.WriteLine("Contract UDO created successfully");     } } finally {     System.Runtime.InteropServices.Marshal.ReleaseComObject(oUserObjectMD); }

## 2.2 UDO Definition - ICP Module

C# code for creating the ICP UDO:

// ICP UDO Creation SAPbobsCOM.UserObjectsMD oUserObjectMD = (SAPbobsCOM.UserObjectsMD)oCompany.GetBusinessObject(     SAPbobsCOM.BoObjectTypes.oUserObjectsMD);  try {     if (oUserObjectMD.GetByKey("RVCM_ICP"))     {         Console.WriteLine("ICP UDO already exists");         return;     }      oUserObjectMD.Code = "RVCM_ICP";     oUserObjectMD.Name = "Interim Certificate Payment";     oUserObjectMD.ObjectType = SAPbobsCOM.BoUDOObjType.boud_Document;     oUserObjectMD.TableName = "RVCM_ICP";          oUserObjectMD.CanArchive = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanCancel = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanClose = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanDelete = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanFind = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanLog = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.ManageSeries = SAPbobsCOM.BoYesNoEnum.tYES;     oUserObjectMD.CanYearTransfer = SAPbobsCOM.BoYesNoEnum.tYES;          // Child table for ICP lines     oUserObjectMD.ChildTables.TableName = "RVCM_ICP1";     oUserObjectMD.ChildTables.Add();          int result = oUserObjectMD.Add();          if (result != 0)     {         int errCode;         string errMsg;         oCompany.GetLastError(out errCode, out errMsg);         Console.WriteLine($"Error creating ICP UDO: {errCode} - {errMsg}");     }     else     {         Console.WriteLine("ICP UDO created successfully");     } } finally {     System.Runtime.InteropServices.Marshal.ReleaseComObject(oUserObjectMD); }

## 2.3 Contract Creation via DI API

C# code for creating a contract:

// Create Contract using DI API public int CreateContract(ContractData contractData) {     SAPbobsCOM.GeneralService oGeneralService;     SAPbobsCOM.GeneralData oGeneralData;     SAPbobsCOM.GeneralDataParams oGeneralParams;     SAPbobsCOM.CompanyService oCompanyService;          try     {         oCompanyService = oCompany.GetCompanyService();         oGeneralService = oCompanyService.GetGeneralService("RVCM_CNTRCT");                  oGeneralData = (SAPbobsCOM.GeneralData)oGeneralService.GetDataInterface(             SAPbobsCOM.GeneralServiceDataInterfaces.gsGeneralData);                  // Set header fields         oGeneralData.SetProperty("U_ContractName", contractData.ContractName);         oGeneralData.SetProperty("U_ContractNameAR", contractData.ContractNameAR);         oGeneralData.SetProperty("U_CardCode", contractData.CardCode);         oGeneralData.SetProperty("U_CardName", contractData.CardName);         oGeneralData.SetProperty("U_CardType", contractData.CardType);         oGeneralData.SetProperty("U_CntctCode", contractData.ContactCode);         oGeneralData.SetProperty("U_ProjectNum", contractData.ProjectNumber);         oGeneralData.SetProperty("U_ProjectName", contractData.ProjectName);         oGeneralData.SetProperty("U_Sector", contractData.Sector);         oGeneralData.SetProperty("U_UserType", contractData.UserType);         oGeneralData.SetProperty("U_UnitNumber", contractData.UnitNumber);         oGeneralData.SetProperty("U_Region", contractData.Region);         oGeneralData.SetProperty("U_ContractType", contractData.ContractType);         oGeneralData.SetProperty("U_StartDate", contractData.StartDate);         oGeneralData.SetProperty("U_EndDate", contractData.EndDate);         oGeneralData.SetProperty("U_ContractVal", contractData.ContractValue);         oGeneralData.SetProperty("U_Currency", contractData.Currency);         oGeneralData.SetProperty("U_TaxRate", contractData.TaxRate);         oGeneralData.SetProperty("U_QuoteRef", contractData.QuoteReference);         oGeneralData.SetProperty("U_Status", "D"); // Draft         oGeneralData.SetProperty("U_ApprovalSts", "P"); // Pending         oGeneralData.SetProperty("U_CreatedBy", oCompany.UserSignature);         oGeneralData.SetProperty("U_CreateDate", DateTime.Now);                  // Add lines         SAPbobsCOM.GeneralDataCollection oChildren = oGeneralData.Child("RVCM_CNTRCT1");         foreach (var line in contractData.Lines)         {             SAPbobsCOM.GeneralData oChild = oChildren.Add();             oChild.SetProperty("U_ItemCode", line.ItemCode);             oChild.SetProperty("U_ItemDesc", line.ItemDescription);             oChild.SetProperty("U_ItemDescAR", line.ItemDescriptionAR);             oChild.SetProperty("U_CostCode", line.CostCode);             oChild.SetProperty("U_Stage", line.Stage);             oChild.SetProperty("U_Probability", line.Probability);             oChild.SetProperty("U_Quantity", line.Quantity);             oChild.SetProperty("U_Unit", line.Unit);             oChild.SetProperty("U_UnitPrice", line.UnitPrice);             oChild.SetProperty("U_DiscountPct", line.DiscountPercent);             oChild.SetProperty("U_TaxCode", line.TaxCode);             oChild.SetProperty("U_TaxRate", line.TaxRate);             oChild.SetProperty("U_PlannedDate", line.PlannedDate);             oChild.SetProperty("U_LineStatus", "P"); // Planned         }                  oGeneralParams = oGeneralService.Add(oGeneralData);         string newCode = oGeneralParams.GetProperty("Code");                  Console.WriteLine($"Contract created successfully: {newCode}");         return 0;     }     catch (Exception ex)     {         Console.WriteLine($"Error creating contract: {ex.Message}");         return -1;     } }

# 3. Service Layer REST API

The add-on exposes REST API endpoints through SAP B1 Service Layer for web and mobile integration.

## 3.1 Authentication

All Service Layer requests require authentication:

POST https://server:50000/b1s/v1/Login Content-Type: application/json  {   "CompanyDB": "SBO_DEMO",   "Password": "password",   "UserName": "manager" }  Response: {   "SessionId": "8d1cc2ad-c8b4-4b12-a787-87c6beef3920",   "Version": "10.0",   "SessionTimeout": 30 }

## 3.2 Contract Endpoints

### GET - Retrieve Contracts

// Get all contracts GET https://server:50000/b1s/v1/RVCM_CNTRCT  // Get specific contract GET https://server:50000/b1s/v1/RVCM_CNTRCT('CNTR-2024-001')  // Get with filters GET https://server:50000/b1s/v1/RVCM_CNTRCT?$filter=U_Status eq 'A' and U_CardCode eq 'C00001'  // Get with related lines GET https://server:50000/b1s/v1/RVCM_CNTRCT('CNTR-2024-001')?$expand=RVCM_CNTRCT1

### POST - Create Contract

POST https://server:50000/b1s/v1/RVCM_CNTRCT Content-Type: application/json  {   "U_ContractName": "Office Renovation Project",   "U_ContractNameAR": "مشروع تجديد المكتب",   "U_CardCode": "C00001",   "U_CardType": "C",   "U_ProjectNum": "PRJ-2024-015",   "U_ProjectName": "HQ Renovation",   "U_Sector": "Construction",   "U_Region": "Central",   "U_ContractType": "Construction",   "U_StartDate": "2024-01-15",   "U_EndDate": "2024-12-31",   "U_ContractVal": 500000.00,   "U_Currency": "SAR",   "U_TaxRate": 15.0,   "U_Status": "D",   "RVCM_CNTRCT1": [     {       "U_ItemCode": "SERV-001",       "U_ItemDesc": "Electrical Works",       "U_ItemDescAR": "الأعمال الكهربائية",       "U_Quantity": 1.0,       "U_UnitPrice": 150000.00,       "U_TaxCode": "VAT15",       "U_LineStatus": "P"     },     {       "U_ItemCode": "SERV-002",       "U_ItemDesc": "Plumbing Works",       "U_ItemDescAR": "أعمال السباكة",       "U_Quantity": 1.0,       "U_UnitPrice": 100000.00,       "U_TaxCode": "VAT15",       "U_LineStatus": "P"     }   ] }

### PATCH - Update Contract

PATCH https://server:50000/b1s/v1/RVCM_CNTRCT('CNTR-2024-001') Content-Type: application/json  {   "U_Status": "A",   "U_ApprovalSts": "A",   "U_ModifiedBy": 5,   "U_ModifyDate": "2024-11-12" }

### DELETE - Delete Contract

DELETE https://server:50000/b1s/v1/RVCM_CNTRCT('CNTR-2024-001')

## 3.3 ICP Endpoints

### POST - Create ICP

POST https://server:50000/b1s/v1/RVCM_ICP Content-Type: application/json  {   "U_ICPNumber": "ICP-2024-001",   "U_ContractCode": "CNTR-2024-001",   "U_CardCode": "C00001",   "U_CertDate": "2024-11-12",   "U_PeriodFrom": "2024-10-01",   "U_PeriodTo": "2024-10-31",   "U_WorkCompPct": 25.0,   "U_RetentionPct": 10.0,   "U_Status": "D",   "RVCM_ICP1": [     {       "U_CntrctLine": 1,       "U_ItemCode": "SERV-001",       "U_Desc": "Electrical Works",       "U_DescAR": "الأعمال الكهربائية",       "U_ContractQty": 1.0,       "U_UnitPrice": 150000.00,       "U_PrevQty": 0.0,       "U_ThisQty": 0.25     }   ] }

### GET - Query ICPs

// Get all ICPs for a contract GET https://server:50000/b1s/v1/RVCM_ICP?$filter=U_ContractCode eq 'CNTR-2024-001'  // Get pending approval ICPs GET https://server:50000/b1s/v1/RVCM_ICP?$filter=U_Status eq 'S' and U_ApprovalSts eq 'P'  // Get ICP with lines GET https://server:50000/b1s/v1/RVCM_ICP('ICP-001')?$expand=RVCM_ICP1

# 4. Direct HANA SQL Queries

The add-on uses direct HANA SQL for complex queries and reporting. Below are key SQL queries used throughout the system.

## 4.1 Contract Dashboard Query

-- Get contract summary with financial totals SELECT      c."Code" AS "ContractCode",     c."U_ContractName" AS "ContractName",     c."U_CardCode" AS "CustomerCode",     c."U_CardName" AS "CustomerName",     c."U_ContractType" AS "Type",     c."U_Status" AS "Status",     c."U_StartDate" AS "StartDate",     c."U_EndDate" AS "EndDate",     c."U_ContractVal" AS "ContractValue",     c."U_TotalValue" AS "TotalWithTax",     COUNT(DISTINCT i."Code") AS "ICPCount",     SUM(i."U_NetPayment") AS "TotalPaid",     (c."U_TotalValue" - COALESCE(SUM(i."U_NetPayment"), 0)) AS "Balance" FROM "@RVCM_CNTRCT" c LEFT JOIN "@RVCM_ICP" i ON c."Code" = i."U_ContractCode" AND i."U_Status" = 'P' WHERE c."U_Status" IN ('A', 'H') GROUP BY      c."Code", c."U_ContractName", c."U_CardCode", c."U_CardName",     c."U_ContractType", c."U_Status", c."U_StartDate", c."U_EndDate",     c."U_ContractVal", c."U_TotalValue" ORDER BY c."U_StartDate" DESC;

## 4.2 ICP Calculation Query

-- Calculate ICP values with cumulative totals SELECT     l."Code" AS "ICPCode",     l."LineNum",     l."U_ItemCode" AS "ItemCode",     l."U_Desc" AS "Description",     l."U_ContractQty" AS "ContractQty",     l."U_UnitPrice" AS "UnitPrice",     l."U_PrevQty" AS "PreviousQty",     l."U_ThisQty" AS "ThisPeriodQty",     (l."U_PrevQty" + l."U_ThisQty") AS "CumulativeQty",     ((l."U_PrevQty" + l."U_ThisQty") / l."U_ContractQty" * 100) AS "PctComplete",     (l."U_ThisQty" * l."U_UnitPrice") AS "ThisPeriodValue",     ((l."U_PrevQty" + l."U_ThisQty") * l."U_UnitPrice") AS "CumulativeValue" FROM "@RVCM_ICP1" l INNER JOIN "@RVCM_ICP" h ON l."Code" = h."Code" WHERE h."Code" = ? ORDER BY l."LineNum";

## 4.3 Financial Deductions Query

-- Calculate net payment with all deductions WITH ICPTotals AS (     SELECT         h."Code",         h."U_ContractCode",         SUM(l."U_ThisQty" * l."U_UnitPrice") AS "GrossValue"     FROM "@RVCM_ICP" h     INNER JOIN "@RVCM_ICP1" l ON h."Code" = l."Code"     WHERE h."Code" = ?     GROUP BY h."Code", h."U_ContractCode" ), Deductions AS (     SELECT         d."Code" AS "ICPCode",         SUM(CASE WHEN d."U_DeductType" = 'Advance' THEN d."U_Amount" ELSE 0 END) AS "AdvanceDeduct",         SUM(CASE WHEN d."U_DeductType" = 'Material' THEN d."U_Amount" ELSE 0 END) AS "MaterialDeduct",         SUM(CASE WHEN d."U_DeductType" = 'Other' THEN d."U_Amount" ELSE 0 END) AS "OtherDeduct"     FROM "@RVCM_DEDUCT" d     WHERE d."Code" = ?     GROUP BY d."Code" ) SELECT     t."Code" AS "ICPCode",     t."GrossValue",     COALESCE(d."AdvanceDeduct", 0) AS "AdvanceDeduction",     (t."GrossValue" * h."U_RetentionPct" / 100) AS "RetentionAmount",     COALESCE(d."MaterialDeduct", 0) AS "MaterialDeduction",     COALESCE(d."OtherDeduct", 0) AS "OtherDeduction",     (         t."GrossValue"          - COALESCE(d."AdvanceDeduct", 0)         - (t."GrossValue" * h."U_RetentionPct" / 100)         - COALESCE(d."MaterialDeduct", 0)         - COALESCE(d."OtherDeduct", 0)     ) AS "SubtotalAfterDeductions",     (         (             t."GrossValue"              - COALESCE(d."AdvanceDeduct", 0)             - (t."GrossValue" * h."U_RetentionPct" / 100)             - COALESCE(d."MaterialDeduct", 0)             - COALESCE(d."OtherDeduct", 0)         ) * tc."Rate" / 100     ) AS "VATAmount",     (         (             t."GrossValue"              - COALESCE(d."AdvanceDeduct", 0)             - (t."GrossValue" * h."U_RetentionPct" / 100)             - COALESCE(d."MaterialDeduct", 0)             - COALESCE(d."OtherDeduct", 0)         ) * (1 + tc."Rate" / 100)     ) AS "NetPayment" FROM ICPTotals t INNER JOIN "@RVCM_ICP" h ON t."Code" = h."Code" LEFT JOIN Deductions d ON t."Code" = d."ICPCode" INNER JOIN "@RVCM_CNTRCT" c ON t."U_ContractCode" = c."Code" INNER JOIN "OSTC" tc ON c."U_TaxCode" = tc."Code";

## 4.4 Retention Balance Query

-- Get retention balance for a contract SELECT     r."Code" AS "RetentionCode",     r."U_ContractCode" AS "ContractCode",     c."U_ContractName" AS "ContractName",     r."U_ICPCode" AS "ICPCode",     r."U_RetentionPct" AS "RetentionPct",     r."U_RetainedAmt" AS "RetainedAmount",     r."U_ReleasedAmt" AS "ReleasedAmount",     (r."U_RetainedAmt" - r."U_ReleasedAmt") AS "Balance",     r."U_Status" AS "Status",     r."U_ReleaseDate" AS "ReleaseDate" FROM "@RVCM_RETEN" r INNER JOIN "@RVCM_CNTRCT" c ON r."U_ContractCode" = c."Code" WHERE r."U_ContractCode" = ?     AND r."U_Status" IN ('H', 'P') ORDER BY r."U_ICPCode";

## 4.5 Business Partner Dropdown Query

-- Get active business partners for contract selection SELECT     bp."CardCode",     bp."CardName",     bp."CardType",     bp."Currency",     bp."Phone1",     bp."E_Mail",     CASE bp."CardType"         WHEN 'C' THEN 'Customer'         WHEN 'S' THEN 'Supplier'         WHEN 'L' THEN 'Lead'         ELSE 'Unknown'     END AS "TypeDesc" FROM "OCRD" bp WHERE bp."validFor" = 'Y'     AND bp."frozenFor" = 'N'     AND bp."CardType" IN ('C', 'S', 'L') ORDER BY bp."CardName";

## 4.6 Contact Person Dropdown Query

-- Get contact persons for a business partner SELECT     cp."CntctCode",     cp."Name",     cp."Position",     cp."Tel1",     cp."Cellolar",     cp."E_MailL",     cp."Active" FROM "OCPR" cp WHERE cp."CardCode" = ?     AND cp."Active" = 'Y' ORDER BY cp."Name";

## 4.7 Item Master Dropdown Query

-- Get items and services for contract lines SELECT     itm."ItemCode",     itm."ItemName",     itm."FrgnName" AS "ForeignName",     itm."ItmsGrpCod",     grp."ItmsGrpNam" AS "ItemGroup",     itm."InvntryUom" AS "Unit",     itm."U_UnitPrice" AS "DefaultPrice",     CASE itm."InvntItem"         WHEN 'Y' THEN 'Inventory Item'         ELSE 'Service'     END AS "ItemType" FROM "OITM" itm INNER JOIN "OITB" grp ON itm."ItmsGrpCod" = grp."ItmsGrpCod" WHERE itm."validFor" = 'Y'     AND itm."frozenFor" = 'N' ORDER BY itm."ItemName";

## 4.8 Tax Code Dropdown Query

-- Get available tax codes SELECT     tc."Code" AS "TaxCode",     tc."Name" AS "TaxName",     tc."Rate" AS "TaxRate",     tc."ValidFrom",     tc."ValidTo" FROM "OSTC" tc WHERE tc."Inactive" = 'N'     AND (tc."ValidTo" IS NULL OR tc."ValidTo" >= CURRENT_DATE) ORDER BY tc."Code";

## 4.9 Currency Dropdown Query

-- Get active currencies SELECT     cr."CurrCode" AS "CurrencyCode",     cr."CurrName" AS "CurrencyName",     cr."CurrSymbol" AS "Symbol",     cr."Decimals" FROM "OCRN" cr WHERE cr."Active" = 'Y' ORDER BY cr."CurrCode";

## 4.10 Contract Status Report Query

-- Comprehensive contract status report WITH ContractFinancials AS (     SELECT         c."Code",         SUM(l."U_LineTotal") AS "LineTotal",         SUM(l."U_TaxAmount") AS "TaxTotal"     FROM "@RVCM_CNTRCT" c     LEFT JOIN "@RVCM_CNTRCT1" l ON c."Code" = l."Code"     GROUP BY c."Code" ), ICPSummary AS (     SELECT         i."U_ContractCode",         COUNT(*) AS "ICPCount",         SUM(CASE WHEN i."U_Status" = 'P' THEN i."U_NetPayment" ELSE 0 END) AS "TotalPaid",         SUM(i."U_RetentionAmt") AS "TotalRetention"     FROM "@RVCM_ICP" i     GROUP BY i."U_ContractCode" ) SELECT     c."Code" AS "ContractCode",     c."U_ContractName" AS "ContractName",     c."U_CardCode" AS "CustomerCode",     bp."CardName" AS "CustomerName",     c."U_ContractType" AS "Type",     CASE c."U_Status"         WHEN 'D' THEN 'Draft'         WHEN 'A' THEN 'Active'         WHEN 'H' THEN 'On Hold'         WHEN 'C' THEN 'Completed'         WHEN 'X' THEN 'Cancelled'     END AS "Status",     c."U_StartDate" AS "StartDate",     c."U_EndDate" AS "EndDate",     DAYS_BETWEEN(c."U_StartDate", c."U_EndDate") AS "Duration",     cf."LineTotal" AS "ContractValue",     cf."TaxTotal" AS "TaxAmount",     (cf."LineTotal" + cf."TaxTotal") AS "TotalValue",     COALESCE(ics."ICPCount", 0) AS "NumberOfICPs",     COALESCE(ics."TotalPaid", 0) AS "AmountPaid",     COALESCE(ics."TotalRetention", 0) AS "RetentionHeld",     ((cf."LineTotal" + cf."TaxTotal") - COALESCE(ics."TotalPaid", 0)) AS "Balance",     (COALESCE(ics."TotalPaid", 0) / NULLIF((cf."LineTotal" + cf."TaxTotal"), 0) * 100) AS "PercentagePaid" FROM "@RVCM_CNTRCT" c LEFT JOIN ContractFinancials cf ON c."Code" = cf."Code" LEFT JOIN ICPSummary ics ON c."Code" = ics."U_ContractCode" INNER JOIN "OCRD" bp ON c."U_CardCode" = bp."CardCode" WHERE c."U_Status" IN ('A', 'H', 'C') ORDER BY c."U_StartDate" DESC;

# 5. Data Validation Rules

The following validation rules must be enforced at the data layer:

## 5.1 Contract Validations

- Contract end date must be after start date

- Contract value must be greater than zero

- Business partner must exist and be active

- Contract must have at least one line item

- Tax rate must be between 0 and 100

- Status transitions must follow workflow rules

## 5.2 ICP Validations

- ICP must reference an active contract

- Period end date must be after period start date

- Cumulative quantity cannot exceed contract quantity

- This period quantity must be greater than zero

- Retention percentage must be between 0 and 100

- Net payment cannot be negative

- Cannot create ICP for completed contract

## 5.3 Line Item Validations

- Item code must exist in item master

- Quantity must be greater than zero

- Unit price cannot be negative

- Discount percentage must be between 0 and 100

- Tax code must be valid and active

## 5.4 Financial Validations

- Currency must be active in system

- All monetary amounts must have correct decimal precision

- Total deductions cannot exceed gross value

- VAT calculation must match tax code definition

=== END OF DOCUMENT 2 ===

Data Models & APIs

Document 3: Business Logic & Workflows

# 1. Contract Lifecycle Workflow

## 1.1 Contract States

Contracts progress through the following states:

| Status Code | Status Name | Description |
| --- | --- | --- |
| D | Draft | Initial creation, can be edited freely |
| A | Active | Approved and active, can create ICPs |
| H | On Hold | Temporarily suspended, no new ICPs allowed |
| C | Completed | Work finished, all payments processed |
| X | Cancelled | Contract terminated before completion |

## 1.2 State Transition Rules

- Draft → Active: Requires approval by authorized user

- Active → On Hold: Can be done by manager at any time

- On Hold → Active: Requires reason and approval

- Active → Completed: Only when all work is done and final payment made

- Any State → Cancelled: Requires high-level approval and cancellation reason

- Completed/Cancelled: Cannot be changed back to other states

# 2. ICP Processing Workflow

## 2.1 ICP States

| Status Code | Status Name | Description |
| --- | --- | --- |
| D | Draft | Being prepared, calculations in progress |
| S | Submitted | Submitted for approval, awaiting review |
| A | Approved | Approved, ready to generate invoice |
| P | Paid | Invoice generated and payment received |
| R | Rejected | Rejected by approver, needs revision |

## 2.2 ICP Calculation Logic

The ICP calculation follows this sequence:

- Calculate Gross Value: Sum of (This Period Qty × Unit Price) for all lines

- Deduct Advance Payment: Subtract any advance payment deduction

- Calculate Retention: Multiply remaining amount by retention percentage

- Deduct Retention: Subtract retention amount

- Deduct Materials: Subtract material deduction if applicable

- Deduct Other: Subtract any other deductions

- Calculate VAT: Apply tax rate to subtotal after all deductions

- Net Payment: Subtotal after deductions + VAT amount

## 2.3 Cumulative Value Tracking

- System tracks cumulative quantities for each contract line item

- Previous Qty = Sum of all previous ICP quantities for this line

- Cumulative Qty = Previous Qty + This Period Qty

- Completion % = (Cumulative Qty / Contract Qty) × 100

- System prevents exceeding 100% completion

# 3. Approval Workflows

## 3.1 Contract Approval

- User creates contract in Draft status

- User submits for approval, status remains Draft, ApprovalStatus = Pending

- Approver reviews contract details and financial impact

- If approved: Status = Active, ApprovalStatus = Approved

- If rejected: Status = Draft, ApprovalStatus = Rejected (user can revise and resubmit)

- System logs all approval actions in workflow history

## 3.2 ICP Approval

- Project engineer creates ICP in Draft status

- System calculates all values automatically

- Engineer submits ICP, status = Submitted

- Project manager reviews work completion and values

- If approved: Status = Approved, system auto-generates AR Invoice

- If rejected: Status = Rejected, engineer revises and resubmits

- Once invoice is paid: Status = Paid

# 4. Financial Integration Logic

## 4.1 AR Invoice Generation

When ICP is approved, system automatically creates AR Invoice:

- Customer: From ICP U_CardCode

- Document Date: ICP U_CertDate

- Payment Terms: From Business Partner master data

- Currency: From contract

- Invoice Lines: One line per ICP line item with this period value

- Deductions: Added as negative lines or separate deduction lines

- Tax: Applied according to contract tax code

- Reference: ICP number stored in user field

## 4.2 Retention Management

- Retention amount is calculated but not invoiced

- System tracks cumulative retention in RVCM_RETEN table

- When contract is completed, retention can be released

- Release creates a separate AR Invoice for retained amounts

- Partial releases supported with approval

## 4.3 Payment Tracking

- System links ICPs to AR Invoices (U_InvoiceEntry)

- When payment is received, status updates to Paid

- Payment Schedule (RVCM_PYMSCH) tracks milestone payments

- Dashboard shows payment status and outstanding balances

# 5. Amendment Processing

## 5.1 Contract Amendment Workflow

- User creates amendment record (RVCM_AMEND)

- Specifies reason, value change, and/or time extension

- Amendment requires approval before taking effect

- Upon approval, system updates contract values/dates

- Original values preserved in amendment history

- Amendment impacts all future ICPs automatically

# 6. Business Rules

## 6.1 Critical Business Rules

- Cannot delete contract with approved ICPs

- Cannot create ICP for non-Active contract

- Cannot exceed 100% completion on any line item

- Cumulative payment cannot exceed contract total value

- Must have at least one approved ICP before marking contract Completed

- Retention release requires completion of contract or specific milestone

- All amounts must be in contract currency

=== END OF DOCUMENT 3 ===

Business Logic & Workflows

Document 4: UI/UX Specifications

# Executive Summary

This document provides comprehensive UI/UX specifications for the SAP Business One Contract Management Add-On, including screen layouts, user flows, design principles, and bilingual interface requirements (Arabic/English).

# 1. Design Principles

## 1.1 Core Design Philosophy

- Native SAP B1 Integration: Follow SAP B1 UI patterns and conventions

- Bilingual Support: Full RTL support for Arabic with seamless language switching

- Consistency: Maintain consistent layouts, terminology, and interactions

- Efficiency: Minimize clicks and data entry with smart defaults

- Clarity: Clear field labels, validation messages, and user feedback

## 1.2 Visual Hierarchy

| Level | Element | Style |
| --- | --- | --- |
| Primary | Form Headers | Bold, 14pt, Dark Blue |
| Secondary | Tab Headers | Bold, 11pt, Blue |
| Tertiary | Field Labels | Regular, 10pt, Dark Gray |
| Body | Data Fields | Regular, 10pt, Black |

# 2. Contract Master Form Layout

## 2.1 Form Structure

The Contract Master form follows SAP B1 standard with toolbar, header section, and tabbed details.

### Toolbar Buttons

| Button | Arabic | Function |
| --- | --- | --- |
| Add | إضافة | Create new contract |
| Update | تحديث | Save changes to existing contract |
| Cancel | إلغاء | Cancel contract (sets status to Cancelled) |
| Find | بحث | Open contract search dialog |
| Approve | اعتماد | Submit for approval or approve contract |
| Generate IPC | إنشاء مستخلص | Create new Interim Payment Certificate |

## 2.2 General Tab Fields

| Field | Arabic Label | Control Type & Behavior |
| --- | --- | --- |
| Contract No. | رقم العقد | Text (Auto-generated), Read-only, Format: CNT-YYMMDD-#### |
| Customer | العميل | Linked Button to OCRD, Required, Auto-fills contact person |
| Customer Name | اسم العميل | Text, Read-only, Auto-filled from Customer |
| Contact Person | الشخص المسؤول | Combo Box from OCPR filtered by Customer |
| Status | الحالة | Combo: Draft, Pending Approval, Active, Completed, Cancelled |
| Contract Type | نوع العقد | Combo: Fixed Price, Time & Materials, Unit Price |
| Start Date | تاريخ البداية | Date Picker, Required, Default: Today |
| End Date | تاريخ الانتهاء | Date Picker, Required, Must be > Start Date |
| Contract Value | قيمة العقد | Numeric, Read-only, Sum of all line items |
| Currency | العملة | Combo from OCRN, Default: System Currency |
| Payment Terms | شروط الدفع | Combo from OCTG |
| Project | المشروع | Linked Button to OPRJ |
| Sales Employee | موظف المبيعات | Combo from OSLP |
| Remarks | ملاحظات | Multi-line Text, Optional |

# 3. Interim Payment Certificate (IPC) Form

## 3.1 IPC Header Fields

| Field | Arabic Label | Control Type & Behavior |
| --- | --- | --- |
| IPC No. | رقم المستخلص | Text, Auto-generated, Format: IPC-ContractNo-### |
| Contract | العقد | Linked Button to Contract, Required, Auto-fills Customer |
| IPC Date | تاريخ المستخلص | Date Picker, Required, Default: Today |
| Period From | من تاريخ | Date Picker, Work period start date |
| Period To | إلى تاريخ | Date Picker, Work period end date |
| Status | الحالة | Combo: Draft, Submitted, Approved, Rejected, Paid |
| Retention % | نسبة الخصم | Numeric (0-100), Default from Contract, Auto-calculates retention |
| Advance Deduction % | نسبة خصم الدفعة المقدمة | Numeric (0-100), Auto-calculates advance deduction |
| Total Amount | المبلغ الإجمالي | Numeric, Read-only, Calculated from line items |
| Net Payable | صافي المستحق | Numeric, Read-only, Total - Retention - Advance Deduction |

# 4. Color Scheme & Visual Design

## 4.1 Status Colors

| Status | Color | Hex Code |
| --- | --- | --- |
| Draft | Gray | #E7E6E6 |
| Pending Approval | Yellow | #FFF2CC |
| Active / Approved | Green | #C6E0B4 |
| Rejected / Cancelled | Red | #F4B084 |
| Completed / Paid | Blue | #D5E8F0 |

# 5. Validation Messages & User Feedback

## 5.1 Error Messages

| English Message | Arabic Message |
| --- | --- |
| Customer is required | العميل مطلوب |
| End date must be after start date | تاريخ الانتهاء يجب أن يكون بعد تاريخ البداية |
| Contract has no line items | العقد لا يحتوي على أي بنود |
| Cannot delete active contract | لا يمكن حذف عقد نشط |
| IPC amount exceeds remaining contract value | مبلغ المستخلص يتجاوز القيمة المتبقية للعقد |

## 5.2 Success Messages

| English Message | Arabic Message |
| --- | --- |
| Contract created successfully | تم إنشاء العقد بنجاح |
| Contract approved successfully | تم اعتماد العقد بنجاح |
| IPC generated successfully | تم إنشاء المستخلص بنجاح |
| Invoice created from IPC | تم إنشاء فاتورة من المستخلص |

# 6. Accessibility & Usability

## 6.1 Keyboard Navigation

- Tab Order: Logical top-to-bottom, left-to-right (or right-to-left for Arabic)

- Enter Key: Saves current field and moves to next

- Ctrl+S: Quick save

- Ctrl+F: Find/Search

- Escape: Cancel current operation

## 6.2 Field Auto-Complete Behavior

- Customer Selection: Auto-fills Customer Name, Contact Person dropdown, Currency

- Contract Selection (in IPC): Auto-fills Customer, Project, Currency, Retention %

- Item Selection: Auto-fills Description, Unit Price, Tax Code

## 6.3 Real-Time Calculations

- Line Total: Quantity × Unit Price (updates immediately on field change)

- Contract Total: Sum of all line totals

- IPC Net Payable: Current Work - Previous Work - Retention - Advance Deduction

End of UI/UX Specifications Document

Ready for Development Team Review

Document 5: Implementation Guide

# Executive Summary

This document provides a comprehensive implementation guide for the SAP Business One Contract Management Add-On, including development roadmap, deployment procedures, testing strategies, and go-live checklist.

# 1. Implementation Roadmap

## 1.1 Project Timeline Overview

| Phase | Duration | Effort | Deliverable |
| --- | --- | --- | --- |
| Phase 1: Database Setup | Weeks x | hours | All UDTs/UDFs created |
| Phase 2: UI Development | Weeks x | hours | Contract & IPC forms |
| Phase 3: Business Logic | Weeks x | hours | Workflows & calculations |
| Phase 4: Integration | Weeks x | hours | DI API & Service Layer |
| Phase 5: Testing & UAT | Weeks x | hours | Production-ready system |

## 1.2 Phase 1: Database Setup

### Week 1: Core Tables

- Create @CNTR_HEADER UDT with all 16 fields

- Create @CNTR_LINES UDT with all 13 fields

- Create @CNTR_PAYMENT UDT with all 10 fields

- Add primary keys and indexes for performance

- Test insert/update/delete operations

### Week 2: IPC Tables & Supporting Tables

- Create @CNTR_IPC_HDR UDT with all 15 fields

- Create @CNTR_IPC_LINES UDT with all 12 fields

- Create @CNTR_APPROVALS, @CNTR_DOCUMENTS, @CNTR_TERMS tables

- Create stored procedures for number series generation

- Load test data for validation

### Critical Success Criteria

- All UDTs created without errors in SAP B1

- Foreign key relationships validated

- Index performance tested with 10,000+ records

- Backup and restore procedures documented

## 1.3 Phase 2: UI Development

### Week 3: Contract Master Form

- Create Contract form with 3 tabs (General, Lines, Documents)

- Implement toolbar buttons (Add, Update, Cancel, Find, Approve)

- Add all General tab fields with proper data bindings

- Implement auto-fill logic for Customer selection

- Test bilingual support (English/Arabic) with RTL layout

### Week 4: Contract Lines Matrix

- Create matrix grid for contract line items

- Add columns: Item, Description, Quantity, Unit Price, Discount, Tax, Total

- Implement real-time calculation logic

- Add row-level validation

- Test add/delete/edit row operations

### Week 5: IPC Form Development

- Create IPC form with header and lines sections

- Implement Contract lookup with auto-fill

- Add IPC calculation fields (Retention, Advance Deduction, Net Payable)

- Create IPC lines matrix with work completion %

- Test all calculation formulas with sample data

### Critical Success Criteria

- Forms fully functional in both English and Arabic

- All field validations working correctly

- Real-time calculations accurate to 4 decimal places

- Keyboard navigation fully operational

# 2. Deployment Procedures

## 2.1 Pre-Deployment Checklist

| Item | Description | Status |
| --- | --- | --- |
| 1 | Full database backup completed | ☐ |
| 2 | All UDTs tested in development environment | ☐ |
| 3 | User permissions configured | ☐ |
| 4 | Add-on compiled and signed | ☐ |
| 5 | User training materials prepared | ☐ |
| 6 | Rollback plan documented | ☐ |
| 7 | Support team briefed | ☐ |

# 3. Testing Strategy

## 3.1 Unit Testing

- Test each stored procedure independently

- Verify all calculation formulas with known test cases

- Test field validation rules

- Verify date range validations

## 3.2 Integration Testing

- Test Contract to IPC workflow end-to-end

- Test IPC to A/R Invoice generation

- Verify approval workflow transitions

- Test data synchronization between tables

## 3.3 User Acceptance Testing (UAT)

- Create 10-15 real-world test scenarios

- Have end users perform daily operations

- Document all user feedback and issues

- Retest after bug fixes

## 3.4 Performance Testing

- Load test with 10,000+ contracts

- Test IPC generation performance

- Verify report generation speed

- Test concurrent user access

# 4. Go-Live Checklist

| Day | Activity | Owner |
| --- | --- | --- |
| D-7 | Final UAT sign-off received | PM |
| D-5 | Production database backup completed | DBA |
| D-3 | User training sessions completed | Trainer |
| D-1 | Deploy add-on to production | Dev Team |
| D-1 | Verify all UDTs and forms accessible | QA Team |
| D-Day | Go-Live! | All |
| D+1 | Post-deployment review meeting | PM |

# 5. Post-Go-Live Support

## 5.1 Hyper-Care Period

- Daily check-ins with key users

- 24/7 support hotline available

- Monitor system performance metrics

- Rapid bug fix deployment process

## 5.2 Ongoing Maintenance

- Monthly system health checks

- Quarterly feature enhancement reviews

- Annual SAP B1 version compatibility testing

- Regular database optimization

## 5.3 Knowledge Transfer

- Technical documentation handover to IT team

- User guide distribution to all end users

- Administrator training for system configuration

- Troubleshooting guide for common issues

# 6. Success Metrics & KPIs

| KPI | Target | Measurement |
| --- | --- | --- |
| User Adoption Rate | > 90% | Active users / Total users |
| System Uptime | > 99.5% | Monthly uptime % |
| Contract Processing Time | < 30 min | Avg time from draft to active |
| IPC Generation Time | < 5 min | Avg time to create IPC |
| Calculation Accuracy | 100% | Zero calculation errors |
| User Satisfaction | > 4.0/5.0 | Monthly user surveys |

End of Implementation Guide

Ready for Project Execution

Document 6: IPC Module Specifications

# 1. IPC Module Overview

## 1.1 Purpose

The Interim Payment Certificate (IPC) module manages progressive payment requests based on work completion. It is essential for construction, engineering, and project-based contracts where payments are made in stages rather than lump sum.

## 1.2 Key Features

- Progressive payment tracking based on work completion percentage

- Automatic retention calculation and tracking

- Advance payment deduction management

- Multi-stage approval workflow

- Automatic A/R Invoice generation upon approval

- Historical IPC tracking per contract

# 2. Database Schema

## 2.1 @CNTR_IPC_HDR (IPC Header Table)

| Field | Type | Size | Required | Description |
| --- | --- | --- | --- | --- |
| Code | nvarchar | 20 | Yes | Primary Key, IPC Number |
| U_ContractNo | nvarchar | 20 | Yes | FK to @CNTR_HEADER |
| U_CustomerCode | nvarchar | 15 | Yes | FK to OCRD |
| U_IPCDate | date | - | Yes | IPC issuance date |
| U_PeriodFrom | date | - | No | Work period start |
| U_PeriodTo | date | - | No | Work period end |
| U_Status | nvarchar | 20 | Yes | Draft/Submitted/Approved/Rejected/Paid |
| U_RetentionPct | decimal | 19,6 | Yes | Retention percentage (0-100) |
| U_AdvDeductPct | decimal | 19,6 | No | Advance deduction % (0-100) |
| U_TotalAmount | decimal | 19,6 | Yes | Sum of all IPC lines |
| U_RetentionAmt | decimal | 19,6 | Yes | Calculated retention amount |
| U_AdvDeductAmt | decimal | 19,6 | No | Calculated advance deduction |
| U_NetPayable | decimal | 19,6 | Yes | Total - Retention - Adv Deduction |
| U_ARInvoiceNo | int | - | No | FK to OINV (generated invoice) |
| U_Remarks | nvarchar | 254 | No | Comments/notes |

# 3. IPC Calculation Logic

## 3.1 Formula Breakdown

| Calculation | Formula |
| --- | --- |
| Current Work Value | SUM(Contract Line Unit Price × Current Work Quantity) |
| Previous Work Value | SUM(All Previous IPCs Current Work Value for same Contract) |
| This IPC Work Value | Current Work Value - Previous Work Value |
| Retention Amount | This IPC Work Value × (Retention % ÷ 100) |
| Advance Deduction | This IPC Work Value × (Advance Deduction % ÷ 100) |
| Net Payable | This IPC Work Value - Retention Amount - Advance Deduction |

## 3.2 Calculation Example

| Item | Amount |
| --- | --- |
| Contract Total Value | $1,000,000.00 |
| Previous IPCs Total | $600,000.00 |
| Current Work Completed | $800,000.00 |
| This IPC Work Value | $200,000.00 |
| Less: Retention (10%) | ($20,000.00) |
| Less: Advance Deduction (5%) | ($10,000.00) |
| Net Payable to Contractor | $170,000.00 |

# 4. IPC Workflow States

| Status | Allowed Actions | Business Rules |
| --- | --- | --- |
| Draft | Edit, Submit, Delete | Can modify all fields. No invoice generated yet. |
| Submitted | Approve, Reject | Awaiting approval. Read-only for submitter. |
| Approved | Generate Invoice | Approved by authorized user. Ready for invoicing. |
| Rejected | Edit, Resubmit | Rejected by approver. Can be corrected and resubmitted. |
| Paid | View Only | Invoice generated and linked. Fully read-only. |

# 5. Integration with Contract Module

## 5.1 Data Synchronization

- When IPC is created, it inherits: Customer, Project, Currency, Retention %, Contract Line Items

- IPC status updates do not affect Contract status

- Contract tracks total IPCs generated and total amount invoiced

## 5.2 Validation Rules

- Cannot create IPC if Contract Status is Draft or Cancelled

- Current Work Completion % cannot exceed 100%

- Total of all IPCs cannot exceed Contract Value

- Cannot delete Contract if approved IPCs exist

# 6. A/R Invoice Generation

## 6.1 Automatic Invoice Creation

When IPC status changes to Approved, the system automatically generates an A/R Invoice in SAP B1 with the following mapping:

| IPC Field | A/R Invoice Field (OINV) |
| --- | --- |
| U_CustomerCode | CardCode (Customer) |
| U_IPCDate | DocDate (Document Date) |
| U_NetPayable | DocTotal (Invoice Total) |
| Code (IPC Number) | Comments / UDF Reference |
| Generated Invoice DocEntry | Stored back in U_ARInvoiceNo |

## 6.2 Invoice Line Items

Each IPC line becomes an invoice line with:

- Item Code (from Contract Line)

- Description: This IPC Work Value for Item

- Quantity: Current Work Qty - Previous Work Qty

- Unit Price: From Contract Line

- Line Total: Calculated from quantity × unit price

# 7. Standard IPC Reports

## 7.1 IPC Summary Report

Lists all IPCs with filters by Contract, Customer, Date Range, Status

- IPC Number, Contract Number, Customer Name

- IPC Date, Period From/To

- This IPC Value, Retention, Advance Deduction, Net Payable

- Status, Linked Invoice Number

## 7.2 Contract Payment History

Shows all IPCs for a specific contract

- IPC Number, Date, Period

- Current Work Value, Previous Work Value

- This IPC Work Value

- Retention & Advance Deduction Amounts

- Net Payable, Cumulative Payment

- Completion %: (Cumulative / Contract Total) × 100

End of IPC Module Specifications

Ready for Development

Document 7: Mathematical Calculations & Financial Logic

# 1. Critical Calculation Review

This document addresses six critical mathematical errors identified in the ICP calculation process and provides corrected formulas and implementation guidance.

# 2. ICP Calculation Errors & Corrections

## 2.1 ERROR: Incorrect Deduction Order

Issue: The original calculation applied retention after other deductions, which is mathematically incorrect. Retention should be calculated on the gross value before other deductions.

Incorrect Formula:

GrossValue - AdvanceDeduct - MaterialDeduct - (Subtotal * RetentionPct)

Correct Formula:

Step 1: RetentionAmount = GrossValue * (RetentionPct / 100) Step 2: Subtotal = GrossValue - AdvanceDeduct - RetentionAmount - MaterialDeduct - OtherDeduct Step 3: VATAmount = Subtotal * (TaxRate / 100) Step 4: NetPayment = Subtotal + VATAmount

## 2.2 ERROR: Missing Division-by-Zero Protection

Issue: Percentage completion calculation can cause division by zero if Contract Quantity is zero or null.

Incorrect Formula:

PctComplete = (CumulativeQty / ContractQty) * 100

Correct Formula:

IF ContractQty > 0 THEN     PctComplete = (CumulativeQty / ContractQty) * 100 ELSE     PctComplete = 0 END IF

SQL Implementation:

CASE      WHEN COALESCE("U_ContractQty", 0) > 0      THEN ("U_CumQty" / "U_ContractQty") * 100     ELSE 0 END AS "PctComplete"

## 2.3 ERROR: Undefined Rounding Rules

Issue: No clear rounding rules defined for financial calculations, leading to penny differences in totals.

Correct Implementation:

- All monetary amounts must be rounded to 2 decimal places

- Rounding method: ROUND_HALF_UP (banker's rounding)

- Round after EACH calculation step, not just final result

- Percentages stored with 6 decimal precision but displayed as 2

SQL Implementation:

ROUND(GrossValue * RetentionPct / 100, 2) AS RetentionAmount ROUND(Subtotal * TaxRate / 100, 2) AS VATAmount ROUND(Subtotal + VATAmount, 2) AS NetPayment

## 2.4 ERROR: Incomplete Retention Release Logic

Issue: Retention release calculation doesn't account for partial releases or multiple release events.

Incorrect Formula:

RetentionBalance = RetainedAmount

Correct Formula:

TotalRetained = SUM(All ICP Retention Amounts for Contract) TotalReleased = SUM(All Retention Releases for Contract) RetentionBalance = TotalRetained - TotalReleased AvailableForRelease = MIN(RetentionBalance, ReleasableAmount)

Business Rules:

- Cannot release more than total retained

- Each release must reference specific ICPs

- System tracks cumulative releases per contract

- Partial releases require approval and justification

## 2.5 ERROR: Lack of Cumulative Validation

Issue: System doesn't validate that cumulative payments don't exceed contract value.

Required Validation:

TotalBilled = SUM(All Approved ICP Net Payments) ContractTotal = Contract Total Value (including tax) RemainingValue = ContractTotal - TotalBilled  IF (NewICPNetPayment > RemainingValue) THEN     RAISE ERROR "ICP amount exceeds remaining contract value"     SHOW WARNING "Remaining: " + RemainingValue END IF

SQL Validation Query:

SELECT     c."U_TotalValue" AS "ContractTotal",     COALESCE(SUM(i."U_NetPayment"), 0) AS "TotalBilled",     (c."U_TotalValue" - COALESCE(SUM(i."U_NetPayment"), 0)) AS "Remaining" FROM "@RVCM_CNTRCT" c LEFT JOIN "@RVCM_ICP" i ON c."Code" = i."U_ContractCode"     AND i."U_Status" IN ('A', 'P') WHERE c."Code" = ? GROUP BY c."Code", c."U_TotalValue";

## 2.6 ERROR: Absent Multi-Currency Handling

Issue: No exchange rate handling when contract currency differs from local currency.

Required Implementation:

- Store all amounts in contract currency

- Fetch exchange rate from ORTT table at transaction date

- Calculate local currency equivalent for reporting

- Display both currencies in UI with exchange rate

SQL Implementation:

SELECT     i."U_NetPayment" AS "AmountFC",     i."U_Currency" AS "Currency",     r."Rate" AS "ExchangeRate",     ROUND(i."U_NetPayment" * r."Rate", 2) AS "AmountLC",     sys."MainCurncy" AS "LocalCurrency" FROM "@RVCM_ICP" i INNER JOIN "ORTT" r ON i."U_Currency" = r."Currency"     AND r."RateDate" <= i."U_CertDate" CROSS JOIN "OADM" sys WHERE i."Code" = ? ORDER BY r."RateDate" DESC LIMIT 1;

# 3. Complete Corrected ICP Calculation

Below is the complete, corrected calculation procedure:

-- Step 1: Calculate Gross Value from Lines DECLARE @GrossValue DECIMAL(19,6); SELECT @GrossValue = SUM(ROUND("U_ThisQty" * "U_UnitPrice", 2)) FROM "@RVCM_ICP1" WHERE "Code" = @ICPCode;  -- Step 2: Get Deduction Amounts DECLARE @AdvanceDeduct DECIMAL(19,6) = COALESCE(     (SELECT SUM("U_Amount") FROM "@RVCM_DEDUCT"       WHERE "Code" = @ICPCode AND "U_DeductType" = 'Advance'), 0);  DECLARE @MaterialDeduct DECIMAL(19,6) = COALESCE(     (SELECT SUM("U_Amount") FROM "@RVCM_DEDUCT"      WHERE "Code" = @ICPCode AND "U_DeductType" = 'Material'), 0);  DECLARE @OtherDeduct DECIMAL(19,6) = COALESCE(     (SELECT SUM("U_Amount") FROM "@RVCM_DEDUCT"      WHERE "Code" = @ICPCode AND "U_DeductType" = 'Other'), 0);  -- Step 3: Calculate Retention (BEFORE other deductions) DECLARE @RetentionPct DECIMAL(19,6); SELECT @RetentionPct = "U_RetentionPct" FROM "@RVCM_ICP" WHERE "Code" = @ICPCode;  DECLARE @RetentionAmt DECIMAL(19,6); SET @RetentionAmt = ROUND(@GrossValue * (@RetentionPct / 100), 2);  -- Step 4: Calculate Subtotal After Deductions DECLARE @Subtotal DECIMAL(19,6); SET @Subtotal = ROUND(@GrossValue - @AdvanceDeduct - @RetentionAmt - @MaterialDeduct - @OtherDeduct, 2);  -- Step 5: Validate Subtotal is Not Negative IF @Subtotal < 0 BEGIN     RAISERROR('Net amount cannot be negative. Total deductions exceed gross value.', 16, 1);     RETURN; END;  -- Step 6: Calculate VAT DECLARE @TaxRate DECIMAL(19,6); SELECT @TaxRate = tc."Rate" FROM "@RVCM_ICP" i INNER JOIN "@RVCM_CNTRCT" c ON i."U_ContractCode" = c."Code" INNER JOIN "OSTC" tc ON c."U_TaxCode" = tc."Code" WHERE i."Code" = @ICPCode;  DECLARE @VATAmount DECIMAL(19,6); SET @VATAmount = ROUND(@Subtotal * (@TaxRate / 100), 2);  -- Step 7: Calculate Net Payment DECLARE @NetPayment DECIMAL(19,6); SET @NetPayment = ROUND(@Subtotal + @VATAmount, 2);  -- Step 8: Validate Against Contract Remaining Value DECLARE @ContractTotal DECIMAL(19,6); DECLARE @TotalBilled DECIMAL(19,6);  SELECT      @ContractTotal = c."U_TotalValue",     @TotalBilled = COALESCE(SUM(CASE WHEN i2."Code" != @ICPCode THEN i2."U_NetPayment" ELSE 0 END), 0) FROM "@RVCM_CNTRCT" c LEFT JOIN "@RVCM_ICP" i2 ON c."Code" = i2."U_ContractCode" AND i2."U_Status" IN ('A', 'P') WHERE c."Code" = (SELECT "U_ContractCode" FROM "@RVCM_ICP" WHERE "Code" = @ICPCode) GROUP BY c."U_TotalValue";  DECLARE @Remaining DECIMAL(19,6); SET @Remaining = @ContractTotal - @TotalBilled;  IF @NetPayment > @Remaining BEGIN     RAISERROR('ICP amount (%s) exceeds remaining contract value (%s)', 16, 1,                CAST(@NetPayment AS VARCHAR), CAST(@Remaining AS VARCHAR));     RETURN; END;  -- Step 9: Update ICP Header with Calculated Values UPDATE "@RVCM_ICP" SET      "U_PeriodValue" = @GrossValue,     "U_AdvDeduct" = @AdvanceDeduct,     "U_RetentionAmt" = @RetentionAmt,     "U_MaterialDeduct" = @MaterialDeduct,     "U_OtherDeduct" = @OtherDeduct,     "U_VATAmount" = @VATAmount,     "U_NetPayment" = @NetPayment WHERE "Code" = @ICPCode;

# 4. Testing Requirements

## 4.1 Unit Test Cases

- Test Case 1: Normal ICP with retention and VAT

- Test Case 2: ICP with advance payment deduction

- Test Case 3: ICP with multiple deduction types

- Test Case 4: Zero quantity contract line

- Test Case 5: Exceeding contract value validation

- Test Case 6: Multi-currency with exchange rates

- Test Case 7: Negative subtotal validation

- Test Case 8: Rounding precision verification

## 4.2 Sample Test Data

Test Case 1: Basic ICP Calculation ----------------------------------- Gross Value: 100,000.00 SAR Advance Deduct: 20,000.00 SAR Retention %: 10% Retention Amount: 10,000.00 SAR (calculated on gross) Material Deduct: 5,000.00 SAR Other Deduct: 0.00 SAR Subtotal: 100,000 - 20,000 - 10,000 - 5,000 = 65,000.00 SAR VAT Rate: 15% VAT Amount: 65,000 * 0.15 = 9,750.00 SAR Net Payment: 65,000 + 9,750 = 74,750.00 SAR  Expected Results: - U_PeriodValue: 100,000.00 - U_RetentionAmt: 10,000.00 - U_VATAmount: 9,750.00 - U_NetPayment: 74,750.00

# 5. Implementation Checklist

## 5.1 Code Changes Required

| # | Component | Required Change |
| --- | --- | --- |
| 1 | ICP Calculation Stored Procedure | Update deduction order, add rounding, add validations |
| 2 | Completion % Calculation | Add NULLIF and COALESCE for division-by-zero protection |
| 3 | Retention Release Logic | Implement cumulative tracking and partial release support |
| 4 | Contract Value Validation | Add validation query before ICP approval |
| 5 | Multi-Currency Support | Add exchange rate lookup and local currency conversion |
| 6 | Rounding Configuration | Apply ROUND function to all monetary calculations |

=== END OF DOCUMENT 7 ===

Mathematical Calculations & Financial Logic

Document 8: SAP B1 Technical Architecture

# 1. SYSTEM ARCHITECTURE OVERVIEW

Purpose: This document provides complete technical architecture for both Contract Management and IPC (Interim Payment Certificate) modules, including SAP B1 SDK integration patterns, Form XML definitions, and event handlers.

## 1.1 3-Tier Architecture

| Layer | Components |
| --- | --- |
| Presentation | SAP B1 UI API (SAPbouiCOM) - Forms, Grids, Matrix, Event Handlers |
| Business Logic | C# Classes - ContractManager, IPCManager, Validation, Calculations |
| Data Access | SAP B1 DI API (SAPbobsCOM) + HANA Stored Procedures |

# 2. CONTRACT FORM - XML DEFINITION

Complete Form XML for Contract Master Screen

<?xml version="1.0" encoding="utf-16"?> <Application>   <forms>     <action type="add">       <form          uid="FRM_CONTRACT"          type="0"          BorderStyle="bbs_Sizable"          title="Contract Management"          left="100"          top="100"          width="800"          height="600"          client_width="800"          client_height="600"          AutoManaged="0"          SupportedModes="15"          default_button="btnAdd"          ObjectType="">                  <datasources>           <DataTables>             <DataTable Uid="DT_CONTRACT"/>           </DataTables>           <DBDataSources>             <DBDataSource TableName="@CM_CONTRACT" Uid="DB_CONTRACT"/>           </DBDataSources>         </datasources>                  <items>           <!-- HEADER SECTION -->           <item uid="lblTitle" type="8" left="10" top="10" width="780" height="30">             <specific caption="Contract Information" backColor="14671839" font_Bold="1"/>           </item>                      <!-- Contract Code (Auto-generated) -->           <item uid="lblCode" type="8" left="10" top="50" width="120" height="14">             <specific caption="Contract Code:"/>           </item>           <item uid="txtCode" type="16" left="140" top="50" width="200" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="Code"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Customer Selection -->           <item uid="lblCustomer" type="8" left="10" top="70" width="120" height="14">             <specific caption="Customer:"/>           </item>           <item uid="txtCardCode" type="16" left="140" top="70" width="100" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_CardCode"/>             </specific>             <LinkedObjectType>2</LinkedObjectType>           </item>           <item uid="txtCardName" type="16" left="250" top="70" width="300" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_CardName"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Contract Type -->           <item uid="lblType" type="8" left="10" top="90" width="120" height="14">             <specific caption="Contract Type:"/>           </item>           <item uid="cmbType" type="121" left="140" top="90" width="200" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_ContractType"/>               <ValidValues>                 <ValidValue value="CONSTRUCTION" description="Construction"/>                 <ValidValue value="MAINTENANCE" description="Maintenance"/>                 <ValidValue value="SUPPLY" description="Supply"/>                 <ValidValue value="SERVICE" description="Service"/>                 <ValidValue value="CONSULTING" description="Consulting"/>               </ValidValues>             </specific>           </item>                      <!-- Dates -->           <item uid="lblStart" type="8" left="10" top="110" width="120" height="14">             <specific caption="Start Date:"/>           </item>           <item uid="dtStart" type="16" left="140" top="110" width="100" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_StartDate"/>             </specific>           </item>                      <item uid="lblEnd" type="8" left="260" top="110" width="80" height="14">             <specific caption="End Date:"/>           </item>           <item uid="dtEnd" type="16" left="350" top="110" width="100" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_EndDate"/>             </specific>           </item>                      <!-- Total Value -->           <item uid="lblValue" type="8" left="10" top="130" width="120" height="14">             <specific caption="Total Value:"/>           </item>           <item uid="txtValue" type="16" left="140" top="130" width="150" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_TotalValue"/>             </specific>           </item>                      <item uid="cmbCurrency" type="121" left="300" top="130" width="80" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_Currency"/>             </specific>           </item>                      <!-- Status -->           <item uid="lblStatus" type="8" left="10" top="150" width="120" height="14">             <specific caption="Status:"/>           </item>           <item uid="txtStatus" type="16" left="140" top="150" width="150" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_Status"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Project Code -->           <item uid="lblProject" type="8" left="10" top="170" width="120" height="14">             <specific caption="Project Code:"/>           </item>           <item uid="txtProject" type="16" left="140" top="170" width="200" height="14">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_ProjectCode"/>             </specific>           </item>                      <!-- Notes -->           <item uid="lblNotes" type="8" left="10" top="190" width="120" height="14">             <specific caption="Notes:"/>           </item>           <item uid="txtNotes" type="16" left="140" top="190" width="640" height="60">             <specific>               <databind databound="1" table="@CM_CONTRACT" alias="U_Notes"/>             </specific>           </item>                      <!-- BUTTONS -->           <item uid="btnAdd" type="4" left="10" top="560" width="100" height="19">             <specific caption="Add"/>           </item>           <item uid="btnUpdate" type="4" left="120" top="560" width="100" height="19">             <specific caption="Update"/>           </item>           <item uid="btnCancel" type="4" left="230" top="560" width="100" height="19">             <specific caption="Cancel"/>           </item>           <item uid="btnIPC" type="4" left="350" top="560" width="120" height="19">             <specific caption="Create IPC"/>           </item>           <item uid="btnWorkflow" type="4" left="480" top="560" width="100" height="19">             <specific caption="Change Status"/>           </item>                      <!-- TAB for IPCs List -->           <item uid="fold01" type="117" left="10" top="260" width="780" height="280">             <specific caption="IPC History" ValOn="1" ValOff="2"/>           </item>                      <!-- Matrix for IPC List -->           <item uid="mtxIPC" type="127" left="15" top="280" width="770" height="250">             <specific SelectionMode="2" layout="0">               <columns>                 <column uid="colIPCNo" type="16" title="IPC #" width="50" editable="0"                          DataBind="DT_CONTRACT,IPCNumber"/>                 <column uid="colIPCDate" type="16" title="Date" width="80" editable="0"                          DataBind="DT_CONTRACT,IPCDate"/>                 <column uid="colPeriod" type="16" title="Period" width="150" editable="0"                          DataBind="DT_CONTRACT,Period"/>                 <column uid="colGross" type="16" title="Gross Value" width="100" editable="0"                          DataBind="DT_CONTRACT,GrossValue"/>                 <column uid="colCurrent" type="16" title="Current Cert." width="100" editable="0"                          DataBind="DT_CONTRACT,CurrentCertified"/>                 <column uid="colNet" type="16" title="Net Payable" width="100" editable="0"                          DataBind="DT_CONTRACT,NetPayable"/>                 <column uid="colTotal" type="16" title="Total Due" width="100" editable="0"                          DataBind="DT_CONTRACT,TotalDue"/>                 <column uid="colStatus" type="16" title="Status" width="80" editable="0"                          DataBind="DT_CONTRACT,IPCStatus"/>               </columns>             </specific>           </item>                    </items>       </form>     </action>   </forms> </Application>

# 3. IPC FORM - XML DEFINITION

Complete Form XML for IPC (Interim Payment Certificate) Screen

<?xml version="1.0" encoding="utf-16"?> <Application>   <forms>     <action type="add">       <form          uid="FRM_IPC"          type="0"          BorderStyle="bbs_Sizable"          title="IPC - Interim Payment Certificate"          left="100"          top="100"          width="900"          height="700"          client_width="900"          client_height="700"          AutoManaged="0"          SupportedModes="15">                  <datasources>           <DataTables>             <DataTable Uid="DT_LINES"/>           </DataTables>           <DBDataSources>             <DBDataSource TableName="@CM_IPC_HDR" Uid="DB_IPC"/>             <DBDataSource TableName="@CM_IPC_LINES" Uid="DB_LINES"/>           </DBDataSources>         </datasources>                  <items>           <!-- HEADER SECTION -->           <item uid="lblTitle" type="8" left="10" top="10" width="880" height="30">             <specific caption="Interim Payment Certificate (IPC)" backColor="16764057" font_Bold="1"/>           </item>                      <!-- IPC Code -->           <item uid="lblCode" type="8" left="10" top="50" width="120" height="14">             <specific caption="IPC Code:"/>           </item>           <item uid="txtCode" type="16" left="140" top="50" width="250" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="Code"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- IPC Number -->           <item uid="lblIPCNo" type="8" left="420" top="50" width="80" height="14">             <specific caption="IPC #:"/>           </item>           <item uid="txtIPCNo" type="16" left="510" top="50" width="80" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_IPCNumber"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Contract Reference -->           <item uid="lblContract" type="8" left="10" top="70" width="120" height="14">             <specific caption="Contract Code:"/>           </item>           <item uid="txtContract" type="16" left="140" top="70" width="250" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_ContractCode"/>             </specific>             <LinkedObjectType>UserTable:CM_CONTRACT</LinkedObjectType>           </item>                      <!-- IPC Date -->           <item uid="lblDate" type="8" left="420" top="70" width="80" height="14">             <specific caption="IPC Date:"/>           </item>           <item uid="dtIPCDate" type="16" left="510" top="70" width="100" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_IPCDate"/>             </specific>           </item>                      <!-- Period -->           <item uid="lblPeriod" type="8" left="10" top="90" width="120" height="14">             <specific caption="Period:"/>           </item>           <item uid="dtPeriodFrom" type="16" left="140" top="90" width="100" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_PeriodFrom"/>             </specific>           </item>           <item uid="lblTo" type="8" left="250" top="90" width="30" height="14">             <specific caption="to"/>           </item>           <item uid="dtPeriodTo" type="16" left="290" top="90" width="100" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_PeriodTo"/>             </specific>           </item>                      <!-- Status -->           <item uid="lblStatus" type="8" left="420" top="90" width="80" height="14">             <specific caption="Status:"/>           </item>           <item uid="txtStatus" type="16" left="510" top="90" width="150" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_Status"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- ============================== -->           <!-- CALCULATION SECTION - CASCADE -->           <!-- ============================== -->                      <item uid="lblCalc" type="8" left="10" top="120" width="880" height="25">             <specific caption="IPC Calculation Summary" backColor="14671839" font_Bold="1"/>           </item>                      <!-- Gross Value -->           <item uid="lblGross" type="8" left="10" top="155" width="200" height="14">             <specific caption="Gross Value:"/>           </item>           <item uid="txtGross" type="16" left="220" top="155" width="150" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_GrossValue"/>             </specific>           </item>                      <!-- Material on Site -->           <item uid="lblMaterial" type="8" left="400" top="155" width="200" height="14">             <specific caption="Material on Site:"/>           </item>           <item uid="txtMaterial" type="16" left="610" top="155" width="150" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_MaterialOnSite"/>             </specific>           </item>                      <!-- SubTotal -->           <item uid="lblSubTotal" type="8" left="10" top="175" width="200" height="14">             <specific caption="SubTotal:" font_Bold="1"/>           </item>           <item uid="txtSubTotal" type="16" left="220" top="175" width="150" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_SubTotal"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>               <backColor>14671839</backColor>             </AutoManagedAttribute>           </item>                      <!-- Previous Certified -->           <item uid="lblPrevious" type="8" left="10" top="195" width="200" height="14">             <specific caption="Previous Certified:"/>           </item>           <item uid="txtPrevious" type="16" left="220" top="195" width="150" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_PreviousCertified"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>               <backColor>14671839</backColor>             </AutoManagedAttribute>           </item>                      <!-- Current Certified -->           <item uid="lblCurrent" type="8" left="10" top="215" width="200" height="14">             <specific caption="Current Certified:" font_Bold="1" ForeColor="255"/>           </item>           <item uid="txtCurrent" type="16" left="220" top="215" width="150" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_CurrentCertified"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>               <backColor>16776960</backColor>             </AutoManagedAttribute>           </item>                      <!-- CASCADE DEDUCTIONS -->           <item uid="lblDeduct" type="8" left="10" top="245" width="880" height="20">             <specific caption="Deductions (Cascade Order)" backColor="16764006" font_Bold="1"/>           </item>                      <!-- Retention -->           <item uid="lblRetPct" type="8" left="10" top="275" width="180" height="14">             <specific caption="Retention %:"/>           </item>           <item uid="txtRetPct" type="16" left="200" top="275" width="60" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_RetentionPct"/>             </specific>           </item>           <item uid="lblRetAmt" type="8" left="280" top="275" width="120" height="14">             <specific caption="Retention Amount:"/>           </item>           <item uid="txtRetAmt" type="16" left="410" top="275" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_RetentionAmount"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>           <item uid="lblAfterRet" type="8" left="550" top="275" width="100" height="14">             <specific caption="After Retention:"/>           </item>           <item uid="txtAfterRet" type="16" left="660" top="275" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_AfterRetention"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Advance Payment Recovery -->           <item uid="lblAdvPct" type="8" left="10" top="295" width="180" height="14">             <specific caption="Advance Recovery %:"/>           </item>           <item uid="txtAdvPct" type="16" left="200" top="295" width="60" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_AdvancePaymentPct"/>             </specific>           </item>           <item uid="lblAdvAmt" type="8" left="280" top="295" width="120" height="14">             <specific caption="Advance Recovered:"/>           </item>           <item uid="txtAdvAmt" type="16" left="410" top="295" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_AdvanceRecovered"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>           <item uid="lblAfterAdv" type="8" left="550" top="295" width="100" height="14">             <specific caption="After Advance:"/>           </item>           <item uid="txtAfterAdv" type="16" left="660" top="295" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_AfterAdvanceRecovery"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Material Recovery -->           <item uid="lblMatPct" type="8" left="10" top="315" width="180" height="14">             <specific caption="Material Recovery %:"/>           </item>           <item uid="txtMatPct" type="16" left="200" top="315" width="60" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_MaterialRecoveryPct"/>             </specific>           </item>           <item uid="lblMatAmt" type="8" left="280" top="315" width="120" height="14">             <specific caption="Material Recovered:"/>           </item>           <item uid="txtMatAmt" type="16" left="410" top="315" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_MaterialRecovered"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>           <item uid="lblAfterMat" type="8" left="550" top="315" width="100" height="14">             <specific caption="After Material:"/>           </item>           <item uid="txtAfterMat" type="16" left="660" top="315" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_AfterMaterialRecovery"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Other Deductions -->           <item uid="lblOther" type="8" left="10" top="335" width="180" height="14">             <specific caption="Other Deductions:"/>           </item>           <item uid="txtOther" type="16" left="200" top="335" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_OtherDeductions"/>             </specific>           </item>                      <!-- Net Payable -->           <item uid="lblNet" type="8" left="10" top="365" width="180" height="14">             <specific caption="Net Payable:" font_Bold="1" ForeColor="16711680"/>           </item>           <item uid="txtNet" type="16" left="200" top="365" width="150" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_NetPayable"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>               <backColor>12648447</backColor>             </AutoManagedAttribute>           </item>                      <!-- VAT -->           <item uid="lblVATPct" type="8" left="10" top="385" width="180" height="14">             <specific caption="VAT %:"/>           </item>           <item uid="txtVATPct" type="16" left="200" top="385" width="60" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_VATRate"/>             </specific>           </item>           <item uid="lblVATAmt" type="8" left="280" top="385" width="120" height="14">             <specific caption="VAT Amount:"/>           </item>           <item uid="txtVATAmt" type="16" left="410" top="385" width="120" height="14">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_VATAmount"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>             </AutoManagedAttribute>           </item>                      <!-- Total Due -->           <item uid="lblTotal" type="8" left="10" top="415" width="180" height="16">             <specific caption="TOTAL DUE:" font_Bold="1" font_Size="14" ForeColor="255"/>           </item>           <item uid="txtTotal" type="16" left="200" top="415" width="180" height="16">             <specific>               <databind databound="1" table="@CM_IPC_HDR" alias="U_TotalDue"/>             </specific>             <AutoManagedAttribute>               <Enabled>0</Enabled>               <backColor>65535</backColor>             </AutoManagedAttribute>           </item>                      <!-- BUTTONS -->           <item uid="btnCalc" type="4" left="10" top="650" width="120" height="22">             <specific caption="Calculate IPC" font_Bold="1" backColor="16776960"/>           </item>           <item uid="btnSave" type="4" left="140" top="650" width="100" height="22">             <specific caption="Save"/>           </item>           <item uid="btnStatus" type="4" left="250" top="650" width="120" height="22">             <specific caption="Change Status"/>           </item>           <item uid="btnCancel" type="4" left="380" top="650" width="100" height="22">             <specific caption="Cancel"/>           </item>           <item uid="btnPrint" type="4" left="490" top="650" width="100" height="22">             <specific caption="Print IPC"/>           </item>                      <!-- MATRIX for Line Items -->           <item uid="mtxLines" type="127" left="10" top="450" width="880" height="180">             <specific SelectionMode="2" layout="0">               <columns>                 <column uid="colItem" type="16" title="Item Code" width="100" editable="1"                          DataBind="DB_LINES,U_ItemCode"/>                 <column uid="colDesc" type="16" title="Description" width="200" editable="1"                          DataBind="DB_LINES,U_Description"/>                 <column uid="colUOM" type="16" title="UOM" width="50" editable="1"                          DataBind="DB_LINES,U_UOM"/>                 <column uid="colConQty" type="16" title="Contract Qty" width="80" editable="0"                          DataBind="DB_LINES,U_ContractQty"/>                 <column uid="colRate" type="16" title="Rate" width="80" editable="0"                          DataBind="DB_LINES,U_ContractRate"/>                 <column uid="colPrevQty" type="16" title="Prev Qty" width="80" editable="0"                          DataBind="DB_LINES,U_PreviousQty"/>                 <column uid="colCurQty" type="16" title="Current Qty" width="80" editable="1"                          DataBind="DB_LINES,U_CurrentQty"/>                 <column uid="colCumQty" type="16" title="Cumul. Qty" width="80" editable="0"                          DataBind="DB_LINES,U_CumulativeQty"/>                 <column uid="colValue" type="16" title="Current Value" width="100" editable="0"                          DataBind="DB_LINES,U_CurrentValue"/>               </columns>             </specific>           </item>                    </items>       </form>     </action>   </forms> </Application>

# 4. CONTRACT FORM - EVENT HANDLERS

using System; using SAPbouiCOM; using SAPbobsCOM;  namespace ContractManagementAddon.Forms {     public class ContractForm     {         private Application SAPApplication;         private Company SAPCompany;         private Form oForm;                  public ContractForm(Application app, Company company)         {             SAPApplication = app;             SAPCompany = company;         }                  public void LoadForm()         {             // Load form from XML             string formXML = System.IO.File.ReadAllText("Forms/ContractForm.xml");             SAPApplication.LoadBatchActions(ref formXML);                          // Get form reference             oForm = SAPApplication.Forms.Item("FRM_CONTRACT");                          // Initialize form             InitializeForm();                          // Attach event handlers             oForm.DataSources.DBDataSources.Item("DB_CONTRACT").Offset = 0;         }                  private void InitializeForm()         {             // Set form mode to Add             oForm.Mode = BoFormMode.fm_ADD_MODE;                          // Populate currency combo box             ComboBox cmbCurrency = (ComboBox)oForm.Items.Item("cmbCurrency").Specific;             Recordset rsC = (Recordset)SAPCompany.GetBusinessObject(BoObjectTypes.BoRecordset);             rsC.DoQuery("SELECT CurrCode, CurrName FROM OCRN WHERE CurrCode != ''");                          while (!rsC.EoF)             {                 cmbCurrency.ValidValues.Add(rsC.Fields.Item("CurrCode").Value.ToString(),                                              rsC.Fields.Item("CurrName").Value.ToString());                 rsC.MoveNext();             }                          // Set default currency to EGP             cmbCurrency.Select("EGP", BoSearchKey.psk_ByValue);                          // Load IPC history matrix             LoadIPCHistory("");         }                  // Event: Customer Code Changed         public void OnCustomerChanged()         {             EditText txtCardCode = (EditText)oForm.Items.Item("txtCardCode").Specific;             EditText txtCardName = (EditText)oForm.Items.Item("txtCardName").Specific;                          string cardCode = txtCardCode.Value.Trim();                          if (!string.IsNullOrEmpty(cardCode))             {                 Recordset rs = (Recordset)SAPCompany.GetBusinessObject(BoObjectTypes.BoRecordset);                 rs.DoQuery($"SELECT CardName FROM OCRD WHERE CardCode = '{cardCode}'");                                  if (!rs.EoF)                 {                     txtCardName.Value = rs.Fields.Item("CardName").Value.ToString();                 }                 else                 {                     SAPApplication.StatusBar.SetText("Customer not found",                          BoMessageTime.bmt_Short, BoStatusBarMessageType.smt_Error);                     txtCardCode.Value = "";                 }             }         }                  // Event: Add Button Clicked         public void OnAddButtonClick()         {             try             {                 // Validate fields                 if (!ValidateForm())                     return;                                  // Get form values                 EditText txtCardCode = (EditText)oForm.Items.Item("txtCardCode").Specific;                 ComboBox cmbType = (ComboBox)oForm.Items.Item("cmbType").Specific;                 EditText dtStart = (EditText)oForm.Items.Item("dtStart").Specific;                 EditText dtEnd = (EditText)oForm.Items.Item("dtEnd").Specific;                 EditText txtValue = (EditText)oForm.Items.Item("txtValue").Specific;                 ComboBox cmbCurrency = (ComboBox)oForm.Items.Item("cmbCurrency").Specific;                 EditText txtProject = (EditText)oForm.Items.Item("txtProject").Specific;                 EditText txtNotes = (EditText)oForm.Items.Item("txtNotes").Specific;                                  // Call stored procedure                 Recordset rs = (Recordset)SAPCompany.GetBusinessObject(BoObjectTypes.BoRecordset);                                  string query = $@"CALL SP_CM_CREATE_CONTRACT(                     '{txtCardCode.Value}',                     '{cmbType.Selected.Value}',                     '{dtStart.Value}',                     '{dtEnd.Value}',                     {txtValue.Value},                     '{cmbCurrency.Selected.Value}',                     '{txtProject.Value}',                     '',                     '{txtNotes.Value}',                     {SAPCompany.UserSignature},                     ?, ?, ?                 )";                                  rs.DoQuery(query);                                  string contractCode = rs.Fields.Item("O_ContractCode").Value.ToString();                 int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);                 string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                                  if (success == 1)                 {                     SAPApplication.StatusBar.SetText(message,                          BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Success);                                          // Set form to find mode and display the contract                     oForm.Mode = BoFormMode.fm_FIND_MODE;                     EditText txtCode = (EditText)oForm.Items.Item("txtCode").Specific;                     txtCode.Value = contractCode;                     oForm.Items.Item("btnAdd").Click();                 }                 else                 {                     SAPApplication.StatusBar.SetText(message,                          BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);                 }             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error creating contract: {ex.Message}",                      BoMessageTime.bmt_Long, BoStatusBarMessageType.smt_Error);             }         }                  // Event: Create IPC Button Clicked         public void OnCreateIPCClick()         {             try             {                 EditText txtCode = (EditText)oForm.Items.Item("txtCode").Specific;                 EditText txtStatus = (EditText)oForm.Items.Item("txtStatus").Specific;                                  string contractCode = txtCode.Value.Trim();                 string status = txtStatus.Value.Trim();                                  // Validate contract is ACTIVE                 if (status != "ACTIVE")                 {                     SAPApplication.StatusBar.SetText(                         "Contract must be ACTIVE to create IPC",                          BoMessageTime.bmt_Short, BoStatusBarMessageType.smt_Error);                     return;                 }                                  // Open IPC form                 IPCForm ipcForm = new IPCForm(SAPApplication, SAPCompany);                 ipcForm.LoadForm(contractCode);             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  // Event: Change Status Button Clicked         public void OnChangeStatusClick()         {             try             {                 EditText txtCode = (EditText)oForm.Items.Item("txtCode").Specific;                 EditText txtStatus = (EditText)oForm.Items.Item("txtStatus").Specific;                                  string contractCode = txtCode.Value.Trim();                 string currentStatus = txtStatus.Value.Trim();                                  // Open status change dialog                 StatusChangeDialog dialog = new StatusChangeDialog(                     SAPApplication, SAPCompany, "CONTRACT", contractCode, currentStatus);                 dialog.ShowDialog();                                  // Refresh form                 oForm.Refresh();             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  // Load IPC History Matrix         private void LoadIPCHistory(string contractCode)         {             try             {                 if (string.IsNullOrEmpty(contractCode))                     return;                                  Matrix mtxIPC = (Matrix)oForm.Items.Item("mtxIPC").Specific;                 DataTable dtContract = oForm.DataSources.DataTables.Item("DT_CONTRACT");                                  string query = $@"                     SELECT                          U_IPCNumber as IPCNumber,                         TO_NVARCHAR(U_IPCDate, 'DD/MM/YYYY') as IPCDate,                         TO_NVARCHAR(U_PeriodFrom, 'DD/MM/YYYY') || ' - ' ||                              TO_NVARCHAR(U_PeriodTo, 'DD/MM/YYYY') as Period,                         U_GrossValue as GrossValue,                         U_CurrentCertified as CurrentCertified,                         U_NetPayable as NetPayable,                         U_TotalDue as TotalDue,                         U_Status as IPCStatus                     FROM [@CM_IPC_HDR]                     WHERE U_ContractCode = '{contractCode}'                     ORDER BY U_IPCNumber";                                  dtContract.ExecuteQuery(query);                 mtxIPC.LoadFromDataSource();                 mtxIPC.AutoResizeColumns();             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error loading IPC history: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  // Validation         private bool ValidateForm()         {             EditText txtCardCode = (EditText)oForm.Items.Item("txtCardCode").Specific;             ComboBox cmbType = (ComboBox)oForm.Items.Item("cmbType").Specific;             EditText dtStart = (EditText)oForm.Items.Item("dtStart").Specific;             EditText dtEnd = (EditText)oForm.Items.Item("dtEnd").Specific;             EditText txtValue = (EditText)oForm.Items.Item("txtValue").Specific;                          if (string.IsNullOrEmpty(txtCardCode.Value))             {                 SAPApplication.MessageBox("Please select a customer");                 txtCardCode.Item.Click();                 return false;             }                          if (string.IsNullOrEmpty(cmbType.Selected?.Value))             {                 SAPApplication.MessageBox("Please select contract type");                 cmbType.Item.Click();                 return false;             }                          if (string.IsNullOrEmpty(dtStart.Value) || string.IsNullOrEmpty(dtEnd.Value))             {                 SAPApplication.MessageBox("Please enter start and end dates");                 return false;             }                          if (string.IsNullOrEmpty(txtValue.Value) || Convert.ToDecimal(txtValue.Value) <= 0)             {                 SAPApplication.MessageBox("Please enter a valid contract value");                 txtValue.Item.Click();                 return false;             }                          return true;         }     } }

# 5. IPC FORM - EVENT HANDLERS

Complete IPC form event handling with cascade calculation

using System; using SAPbouiCOM; using SAPbobsCOM;  namespace ContractManagementAddon.Forms {     public class IPCForm     {         private Application SAPApplication;         private Company SAPCompany;         private Form oForm;                  public IPCForm(Application app, Company company)         {             SAPApplication = app;             SAPCompany = company;         }                  public void LoadForm(string contractCode = "")         {             // Load form from XML             string formXML = System.IO.File.ReadAllText("Forms/IPCForm.xml");             SAPApplication.LoadBatchActions(ref formXML);                          // Get form reference             oForm = SAPApplication.Forms.Item("FRM_IPC");                          // Initialize form             if (!string.IsNullOrEmpty(contractCode))             {                 InitializeFormForNewIPC(contractCode);             }             else             {                 InitializeForm();             }         }                  private void InitializeFormForNewIPC(string contractCode)         {             try             {                 // Set form mode to Add                 oForm.Mode = BoFormMode.fm_ADD_MODE;                                  EditText txtContract = (EditText)oForm.Items.Item("txtContract").Specific;                 txtContract.Value = contractCode;                                  // Set default dates                 EditText dtIPCDate = (EditText)oForm.Items.Item("dtIPCDate").Specific;                 dtIPCDate.Value = DateTime.Now.ToString("yyyyMMdd");                                  // Set default retention and VAT                 EditText txtRetPct = (EditText)oForm.Items.Item("txtRetPct").Specific;                 txtRetPct.Value = "10.00";                                  EditText txtVATPct = (EditText)oForm.Items.Item("txtVATPct").Specific;                 txtVATPct.Value = "14.00";                                  // Load contract line items                 LoadContractLineItems(contractCode);             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error initializing IPC: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  // Event: Calculate Button Clicked         public void OnCalculateClick()         {             try             {                 // Validate required fields                 EditText txtCode = (EditText)oForm.Items.Item("txtCode").Specific;                 EditText txtGross = (EditText)oForm.Items.Item("txtGross").Specific;                                  string ipcCode = txtCode.Value.Trim();                                  if (string.IsNullOrEmpty(ipcCode))                 {                     SAPApplication.MessageBox("Please save the IPC before calculating");                     return;                 }                                  // Calculate line items first                 CalculateLineItems();                                  // Update gross value from line items                 Matrix mtxLines = (Matrix)oForm.Items.Item("mtxLines").Specific;                 decimal totalGross = 0;                                  for (int i = 1; i <= mtxLines.RowCount; i++)                 {                     EditText cellValue = (EditText)mtxLines.Columns.Item("colValue").Cells.Item(i).Specific;                     if (!string.IsNullOrEmpty(cellValue.Value))                     {                         totalGross += Convert.ToDecimal(cellValue.Value);                     }                 }                                  txtGross.Value = totalGross.ToString("0.00");                                  // Call stored procedure for cascade calculation                 Recordset rs = (Recordset)SAPCompany.GetBusinessObject(BoObjectTypes.BoRecordset);                                  string query = $"CALL SP_CM_CALCULATE_IPC('{ipcCode}', ?, ?)";                 rs.DoQuery(query);                                  int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);                 string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                                  if (success == 1)                 {                     SAPApplication.StatusBar.SetText(message,                          BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Success);                                          // Refresh form to show calculated values                     oForm.Mode = BoFormMode.fm_FIND_MODE;                     txtCode.Value = ipcCode;                     oForm.Items.Item("btnCalc").Click();                                          // Highlight the Total Due field                     EditText txtTotal = (EditText)oForm.Items.Item("txtTotal").Specific;                     SAPApplication.MessageBox(                         $"IPC Calculation Complete!\n\n" +                         $"Total Due: {txtTotal.Value}\n\n" +                         $"Please review the cascade deductions and click Save to confirm.",                         1, "OK", "", "");                 }                 else                 {                     SAPApplication.StatusBar.SetText(message,                          BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);                 }             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error calculating IPC: {ex.Message}",                      BoMessageTime.bmt_Long, BoStatusBarMessageType.smt_Error);             }         }                  // Event: Save Button Clicked         public void OnSaveClick()         {             try             {                 EditText txtCode = (EditText)oForm.Items.Item("txtCode").Specific;                 string ipcCode = txtCode.Value.Trim();                                  if (string.IsNullOrEmpty(ipcCode))                 {                     // New IPC - Create it                     CreateNewIPC();                 }                 else                 {                     // Update existing IPC                     UpdateIPC();                 }             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error saving IPC: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  private void CreateNewIPC()         {             try             {                 EditText txtContract = (EditText)oForm.Items.Item("txtContract").Specific;                 EditText dtIPCDate = (EditText)oForm.Items.Item("dtIPCDate").Specific;                 EditText dtPeriodFrom = (EditText)oForm.Items.Item("dtPeriodFrom").Specific;                 EditText dtPeriodTo = (EditText)oForm.Items.Item("dtPeriodTo").Specific;                                  string contractCode = txtContract.Value.Trim();                                  // Validate                 if (string.IsNullOrEmpty(contractCode))                 {                     SAPApplication.MessageBox("Please select a contract");                     return;                 }                                  if (string.IsNullOrEmpty(dtPeriodFrom.Value) || string.IsNullOrEmpty(dtPeriodTo.Value))                 {                     SAPApplication.MessageBox("Please enter period dates");                     return;                 }                                  // Call stored procedure                 Recordset rs = (Recordset)SAPCompany.GetBusinessObject(BoObjectTypes.BoRecordset);                                  string query = $@"CALL SP_CM_CREATE_IPC(                     '{contractCode}',                     '{dtIPCDate.Value}',                     '{dtPeriodFrom.Value}',                     '{dtPeriodTo.Value}',                     {SAPCompany.UserSignature},                     ?, ?, ?, ?                 )";                                  rs.DoQuery(query);                                  string ipcCode = rs.Fields.Item("O_IPCCode").Value.ToString();                 int ipcNumber = Convert.ToInt32(rs.Fields.Item("O_IPCNumber").Value);                 int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);                 string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                                  if (success == 1)                 {                     SAPApplication.StatusBar.SetText(message,                          BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Success);                                          // Set form to find mode and display the IPC                     oForm.Mode = BoFormMode.fm_FIND_MODE;                     EditText txtCode = (EditText)oForm.Items.Item("txtCode").Specific;                     txtCode.Value = ipcCode;                     oForm.Items.Item("btnSave").Click();                                          // Prompt to calculate                     SAPApplication.MessageBox(                         $"IPC #{ipcNumber} created successfully!\n\n" +                         $"Please enter line items and click 'Calculate IPC' to compute amounts.",                         1, "OK", "", "");                 }                 else                 {                     SAPApplication.StatusBar.SetText(message,                          BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);                 }             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error creating IPC: {ex.Message}",                      BoMessageTime.bmt_Long, BoStatusBarMessageType.smt_Error);             }         }                  // Event: Change Status Button Clicked         public void OnChangeStatusClick()         {             try             {                 EditText txtCode = (EditText)oForm.Items.Item("txtCode").Specific;                 EditText txtStatus = (EditText)oForm.Items.Item("txtStatus").Specific;                 EditText txtTotal = (EditText)oForm.Items.Item("txtTotal").Specific;                                  string ipcCode = txtCode.Value.Trim();                 string currentStatus = txtStatus.Value.Trim();                 string totalDue = txtTotal.Value.Trim();                                  // Validate                 if (currentStatus == "DRAFT" && (string.IsNullOrEmpty(totalDue) || totalDue == "0"))                 {                     SAPApplication.MessageBox(                         "Please calculate the IPC before submitting.\n\n" +                         "Click 'Calculate IPC' button to compute amounts.",                         1, "OK", "", "");                     return;                 }                                  // Open status change dialog                 StatusChangeDialog dialog = new StatusChangeDialog(                     SAPApplication, SAPCompany, "IPC", ipcCode, currentStatus);                 dialog.ShowDialog();                                  // Refresh form                 oForm.Refresh();             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  // Calculate line items (quantity * rate)         private void CalculateLineItems()         {             try             {                 Matrix mtxLines = (Matrix)oForm.Items.Item("mtxLines").Specific;                                  for (int i = 1; i <= mtxLines.RowCount; i++)                 {                     EditText cellCurQty = (EditText)mtxLines.Columns.Item("colCurQty").Cells.Item(i).Specific;                     EditText cellRate = (EditText)mtxLines.Columns.Item("colRate").Cells.Item(i).Specific;                     EditText cellPrevQty = (EditText)mtxLines.Columns.Item("colPrevQty").Cells.Item(i).Specific;                     EditText cellCumQty = (EditText)mtxLines.Columns.Item("colCumQty").Cells.Item(i).Specific;                     EditText cellValue = (EditText)mtxLines.Columns.Item("colValue").Cells.Item(i).Specific;                                          if (!string.IsNullOrEmpty(cellCurQty.Value) && !string.IsNullOrEmpty(cellRate.Value))                     {                         decimal currentQty = Convert.ToDecimal(cellCurQty.Value);                         decimal rate = Convert.ToDecimal(cellRate.Value);                         decimal previousQty = string.IsNullOrEmpty(cellPrevQty.Value) ? 0 : Convert.ToDecimal(cellPrevQty.Value);                                                  // Calculate cumulative and value                         decimal cumulativeQty = previousQty + currentQty;                         decimal currentValue = currentQty * rate;                                                  cellCumQty.Value = cumulativeQty.ToString("0.000");                         cellValue.Value = currentValue.ToString("0.00");                     }                 }                                  mtxLines.FlushToDataSource();             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error calculating line items: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  // Load contract line items into matrix         private void LoadContractLineItems(string contractCode)         {             try             {                 Matrix mtxLines = (Matrix)oForm.Items.Item("mtxLines").Specific;                 DBDataSource dbLines = oForm.DataSources.DBDataSources.Item("DB_LINES");                                  // Query to get contract line items or BOQ                 string query = $@"                     SELECT                          ItemCode,                         ItemName as Description,                         'EA' as UOM,                         ContractQty,                         ContractRate,                         0 as PreviousQty,                         0 as CurrentQty                     FROM [@CONTRACT_LINES]                     WHERE ContractCode = '{contractCode}'                     ORDER BY LineNum";                                  Recordset rs = (Recordset)SAPCompany.GetBusinessObject(BoObjectTypes.BoRecordset);                 rs.DoQuery(query);                                  int row = 0;                 while (!rs.EoF)                 {                     dbLines.Offset = row;                     dbLines.SetValue("U_ItemCode", row, rs.Fields.Item("ItemCode").Value.ToString());                     dbLines.SetValue("U_Description", row, rs.Fields.Item("Description").Value.ToString());                     dbLines.SetValue("U_UOM", row, rs.Fields.Item("UOM").Value.ToString());                     dbLines.SetValue("U_ContractQty", row, rs.Fields.Item("ContractQty").Value.ToString());                     dbLines.SetValue("U_ContractRate", row, rs.Fields.Item("ContractRate").Value.ToString());                     dbLines.SetValue("U_PreviousQty", row, "0");                     dbLines.SetValue("U_CurrentQty", row, "0");                                          row++;                     rs.MoveNext();                 }                                  mtxLines.LoadFromDataSource();                 mtxLines.AutoResizeColumns();             }             catch (Exception ex)             {                 SAPApplication.StatusBar.SetText($"Error loading contract items: {ex.Message}",                      BoMessageTime.bmt_Medium, BoStatusBarMessageType.smt_Error);             }         }                  private void InitializeForm()         {             // Standard form initialization for browsing existing IPCs             oForm.Mode = BoFormMode.fm_OK_MODE;         }                  private void UpdateIPC()         {             // Update IPC logic             SAPApplication.StatusBar.SetText("IPC updated successfully",                  BoMessageTime.bmt_Short, BoStatusBarMessageType.smt_Success);         }     } }

# 6. DEPLOYMENT CHECKLIST

Complete deployment steps for Contract & IPC modules

| Step | Task | Status |
| --- | --- | --- |
| 1 | Deploy database tables and stored procedures (Document 10) | ☐ |
| 2 | Compile Contract Form XML (Section 2 of this document) | ☐ |
| 3 | Compile IPC Form XML (Section 3 of this document) | ☐ |
| 4 | Implement Contract Form event handlers (Section 4) | ☐ |
| 5 | Implement IPC Form event handlers (Section 5) | ☐ |
| 6 | Implement business logic classes (ContractManager, IPCManager from Document 9) | ☐ |
| 7 | Test Contract creation workflow | ☐ |
| 8 | Test IPC creation and calculation (verify 12-step cascade) | ☐ |
| 9 | Test workflow status changes for both Contract and IPC | ☐ |
| 10 | User acceptance testing (UAT) | ☐ |
| 11 | Production deployment | ☐ |

--- END OF DOCUMENT 8 ---

Complete Technical Architecture for Contract & IPC Modules

Document 9: Database Scripts & Code Implementation

# 1. OVERVIEW

Purpose: This document provides complete database scripts and code implementations for both SAP HANA and SQL Server databases, covering Contract Management and IPC (Interim Payment Certificate) modules.

## 1.1 Database Compatibility

The system supports both SAP HANA and SQL Server with database-agnostic code patterns. All stored procedures are provided in both HANA SQLScript and T-SQL formats.

| Feature | SAP HANA | SQL Server |
| --- | --- | --- |
| Stored Procedures | SQLScript | T-SQL |
| String Concatenation | ¦¦ operator | + operator |
| NULL Handling | IFNULL() | ISNULL() |
| Current Date | CURRENT_DATE | GETDATE() |
| Limit Results | LIMIT N | TOP N |

# 2. COMPLETE TABLE CREATION SCRIPTS

The following scripts create all custom tables required for the Contract Management system.

## 2.1 Contract Header Table - SAP HANA

-- Contract Master Table (HANA) CREATE COLUMN TABLE "@CM_CONTRACT" (     "Code" NVARCHAR(50) PRIMARY KEY,     "Name" NVARCHAR(200),     "U_CardCode" NVARCHAR(15),     "U_CardName" NVARCHAR(100),     "U_ContractType" NVARCHAR(20),     "U_StartDate" DATE,     "U_EndDate" DATE,     "U_TotalValue" DECIMAL(19,6),     "U_Currency" NVARCHAR(3) DEFAULT 'EGP',     "U_Status" NVARCHAR(30) DEFAULT 'DRAFT',     "U_CompletionPct" DECIMAL(5,2) DEFAULT 0,     "U_CreatedBy" INTEGER,     "U_CreatedDate" TIMESTAMP DEFAULT CURRENT_TIMESTAMP,     "U_ModifiedBy" INTEGER,     "U_ModifiedDate" TIMESTAMP,     "U_ApprovedBy" INTEGER,     "U_ApprovedDate" TIMESTAMP,     "U_ProjectCode" NVARCHAR(30),     "U_DepartmentCode" NVARCHAR(20),     "U_Notes" NVARCHAR(500) );  -- Indexes for performance CREATE INDEX "IX_CONTRACT_Status" ON "@CM_CONTRACT"("U_Status"); CREATE INDEX "IX_CONTRACT_Customer" ON "@CM_CONTRACT"("U_CardCode"); CREATE INDEX "IX_CONTRACT_Dates" ON "@CM_CONTRACT"("U_StartDate", "U_EndDate"); CREATE INDEX "IX_CONTRACT_Type" ON "@CM_CONTRACT"("U_ContractType");

## 2.2 IPC Header Table - SAP HANA

-- IPC (Interim Payment Certificate) Header Table (HANA) CREATE COLUMN TABLE "@CM_IPC_HDR" (     "Code" NVARCHAR(50) PRIMARY KEY,     "Name" NVARCHAR(200),     "U_ContractCode" NVARCHAR(50),     "U_IPCNumber" INTEGER,     "U_IPCDate" DATE,     "U_PeriodFrom" DATE,     "U_PeriodTo" DATE,     "U_GrossValue" DECIMAL(19,6) DEFAULT 0,     "U_MaterialOnSite" DECIMAL(19,6) DEFAULT 0,     "U_SubTotal" DECIMAL(19,6) DEFAULT 0,     "U_PreviousCertified" DECIMAL(19,6) DEFAULT 0,     "U_CurrentCertified" DECIMAL(19,6) DEFAULT 0,     "U_RetentionPct" DECIMAL(5,2) DEFAULT 10,     "U_RetentionAmount" DECIMAL(19,6) DEFAULT 0,     "U_AfterRetention" DECIMAL(19,6) DEFAULT 0,     "U_AdvancePaymentPct" DECIMAL(5,2) DEFAULT 0,     "U_AdvanceRecovered" DECIMAL(19,6) DEFAULT 0,     "U_AfterAdvanceRecovery" DECIMAL(19,6) DEFAULT 0,     "U_MaterialRecoveryPct" DECIMAL(5,2) DEFAULT 0,     "U_MaterialRecovered" DECIMAL(19,6) DEFAULT 0,     "U_AfterMaterialRecovery" DECIMAL(19,6) DEFAULT 0,     "U_OtherDeductions" DECIMAL(19,6) DEFAULT 0,     "U_NetPayable" DECIMAL(19,6) DEFAULT 0,     "U_VATRate" DECIMAL(5,2) DEFAULT 14,     "U_VATAmount" DECIMAL(19,6) DEFAULT 0,     "U_TotalDue" DECIMAL(19,6) DEFAULT 0,     "U_Status" NVARCHAR(30) DEFAULT 'DRAFT',     "U_CreatedBy" INTEGER,     "U_CreatedDate" TIMESTAMP DEFAULT CURRENT_TIMESTAMP,     "U_ApprovedBy" INTEGER,     "U_ApprovedDate" TIMESTAMP,     "U_Notes" NVARCHAR(500),     FOREIGN KEY ("U_ContractCode") REFERENCES "@CM_CONTRACT"("Code") );  -- Indexes CREATE INDEX "IX_IPC_Contract" ON "@CM_IPC_HDR"("U_ContractCode"); CREATE INDEX "IX_IPC_Status" ON "@CM_IPC_HDR"("U_Status"); CREATE INDEX "IX_IPC_Date" ON "@CM_IPC_HDR"("U_IPCDate"); CREATE INDEX "IX_IPC_Number" ON "@CM_IPC_HDR"("U_ContractCode", "U_IPCNumber");

## 2.3 IPC Line Items Table - SAP HANA

-- IPC Line Items Table (HANA) CREATE COLUMN TABLE "@CM_IPC_LINES" (     "Code" NVARCHAR(50),     "LineId" INTEGER,     "U_ItemCode" NVARCHAR(20),     "U_ItemName" NVARCHAR(100),     "U_Description" NVARCHAR(200),     "U_UOM" NVARCHAR(20),     "U_ContractQty" DECIMAL(19,6),     "U_ContractRate" DECIMAL(19,6),     "U_ContractValue" DECIMAL(19,6),     "U_PreviousQty" DECIMAL(19,6) DEFAULT 0,     "U_CurrentQty" DECIMAL(19,6) DEFAULT 0,     "U_CumulativeQty" DECIMAL(19,6) DEFAULT 0,     "U_CurrentValue" DECIMAL(19,6) DEFAULT 0,     "U_CompletionPct" DECIMAL(5,2) DEFAULT 0,     "U_Notes" NVARCHAR(200),     PRIMARY KEY ("Code", "LineId"),     FOREIGN KEY ("Code") REFERENCES "@CM_IPC_HDR"("Code") );  -- Index CREATE INDEX "IX_IPC_LINES_Item" ON "@CM_IPC_LINES"("U_ItemCode");

## 2.4 Workflow History Table - SAP HANA

-- Workflow History Table (HANA) CREATE COLUMN TABLE "@CM_WORKFLOW_HISTORY" (     "Code" NVARCHAR(50) PRIMARY KEY,     "U_DocumentType" NVARCHAR(20),     "U_DocumentCode" NVARCHAR(50),     "U_FromStatus" NVARCHAR(30),     "U_ToStatus" NVARCHAR(30),     "U_ChangedBy" INTEGER,     "U_ChangeDate" TIMESTAMP DEFAULT CURRENT_TIMESTAMP,     "U_Comments" NVARCHAR(500),     "U_ActionType" NVARCHAR(20) );  -- Indexes CREATE INDEX "IX_WORKFLOW_Doc" ON "@CM_WORKFLOW_HISTORY"("U_DocumentType", "U_DocumentCode"); CREATE INDEX "IX_WORKFLOW_Date" ON "@CM_WORKFLOW_HISTORY"("U_ChangeDate");

# 3. HANA STORED PROCEDURES - CONTRACT MODULE

CRITICAL: These stored procedures implement all business logic for contract management with proper error handling and validation.

## 3.1 SP_CM_CREATE_CONTRACT - Create New Contract

CREATE PROCEDURE "SP_CM_CREATE_CONTRACT"(     IN "P_CardCode" NVARCHAR(15),     IN "P_ContractType" NVARCHAR(20),     IN "P_StartDate" DATE,     IN "P_EndDate" DATE,     IN "P_TotalValue" DECIMAL(19,6),     IN "P_Currency" NVARCHAR(3),     IN "P_ProjectCode" NVARCHAR(30),     IN "P_CreatedBy" INTEGER,     OUT "O_ContractCode" NVARCHAR(50),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_Counter INTEGER;     DECLARE V_Year NVARCHAR(4);     DECLARE V_CardName NVARCHAR(100);     DECLARE V_Exists INTEGER;          -- Initialize outputs     O_ErrorMsg := '';     O_ContractCode := '';     O_Success := 0;          -- Validate Business Partner     SELECT COUNT(*) INTO V_Exists     FROM "OCRD"     WHERE "CardCode" = :P_CardCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Invalid Business Partner Code: ' || :P_CardCode;         RETURN;     END IF;          -- Get Business Partner Name     SELECT "CardName" INTO V_CardName     FROM "OCRD"     WHERE "CardCode" = :P_CardCode;          -- Validate Dates     IF :P_StartDate >= :P_EndDate THEN         O_ErrorMsg := 'Start Date must be before End Date';         RETURN;     END IF;          -- Validate Total Value     IF :P_TotalValue <= 0 THEN         O_ErrorMsg := 'Total Value must be greater than zero';         RETURN;     END IF;          -- Generate Contract Code (Format: CT-YYYY-XXXXX)     V_Year := TO_NVARCHAR(:P_StartDate, 'YYYY');          SELECT IFNULL(MAX(CAST(SUBSTRING("Code", 9, 5) AS INTEGER)), 0) + 1      INTO V_Counter     FROM "@CM_CONTRACT"     WHERE LEFT("Code", 7) = 'CT-' || :V_Year;          O_ContractCode := 'CT-' || :V_Year || '-' || LPAD(CAST(:V_Counter AS NVARCHAR), 5, '0');          -- Insert Contract     INSERT INTO "@CM_CONTRACT"(         "Code", "Name",         "U_CardCode", "U_CardName",         "U_ContractType", "U_StartDate", "U_EndDate",         "U_TotalValue", "U_Currency",         "U_Status", "U_CompletionPct",         "U_ProjectCode",         "U_CreatedBy", "U_CreatedDate"     )     VALUES(         :O_ContractCode,         :V_CardName || ' - ' || :P_ContractType,         :P_CardCode,         :V_CardName,         :P_ContractType,         :P_StartDate,         :P_EndDate,         :P_TotalValue,         :P_Currency,         'DRAFT',         0,         :P_ProjectCode,         :P_CreatedBy,         CURRENT_TIMESTAMP     );          -- Create initial workflow history entry     INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         'WF-' || :O_ContractCode || '-001',         'CONTRACT',         :O_ContractCode,         NULL,         'DRAFT',         :P_CreatedBy,         CURRENT_TIMESTAMP,         'Contract created',         'CREATE'     );          O_Success := 1;     O_ErrorMsg := 'Contract created successfully: ' || :O_ContractCode;      END;

## 3.2 SP_CM_CHANGE_CONTRACT_STATUS - Change Contract Status

CREATE PROCEDURE "SP_CM_CHANGE_CONTRACT_STATUS"(     IN "P_ContractCode" NVARCHAR(50),     IN "P_NewStatus" NVARCHAR(30),     IN "P_ChangedBy" INTEGER,     IN "P_Comments" NVARCHAR(500),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_CurrentStatus NVARCHAR(30);     DECLARE V_Allowed INTEGER;     DECLARE V_HistoryCode NVARCHAR(50);     DECLARE V_HistoryCount INTEGER;     DECLARE V_Exists INTEGER;          -- Initialize outputs     O_Success := 0;     O_ErrorMsg := '';          -- Check if contract exists     SELECT COUNT(*) INTO V_Exists     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Contract not found: ' || :P_ContractCode;         RETURN;     END IF;          -- Get current status     SELECT "U_Status" INTO V_CurrentStatus     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          -- Check if status change is allowed (workflow validation)     -- DRAFT -> SUBMITTED     -- SUBMITTED -> APPROVED or REJECTED     -- APPROVED -> ACTIVE     -- ACTIVE -> COMPLETED or SUSPENDED     -- SUSPENDED -> ACTIVE     -- COMPLETED -> No further changes          V_Allowed := 0;          IF :V_CurrentStatus = 'DRAFT' AND :P_NewStatus = 'SUBMITTED' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'SUBMITTED' AND (:P_NewStatus = 'APPROVED' OR :P_NewStatus = 'REJECTED') THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'APPROVED' AND :P_NewStatus = 'ACTIVE' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'ACTIVE' AND (:P_NewStatus = 'COMPLETED' OR :P_NewStatus = 'SUSPENDED') THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'SUSPENDED' AND :P_NewStatus = 'ACTIVE' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = :P_NewStatus THEN         O_ErrorMsg := 'Contract is already in status: ' || :P_NewStatus;         RETURN;     END IF;          IF :V_Allowed = 0 THEN         O_ErrorMsg := 'Invalid status transition from ' || :V_CurrentStatus || ' to ' || :P_NewStatus;         RETURN;     END IF;          -- Update contract status     UPDATE "@CM_CONTRACT"     SET "U_Status" = :P_NewStatus,         "U_ModifiedBy" = :P_ChangedBy,         "U_ModifiedDate" = CURRENT_TIMESTAMP,         "U_ApprovedBy" = CASE WHEN :P_NewStatus = 'APPROVED' THEN :P_ChangedBy ELSE "U_ApprovedBy" END,         "U_ApprovedDate" = CASE WHEN :P_NewStatus = 'APPROVED' THEN CURRENT_TIMESTAMP ELSE "U_ApprovedDate" END     WHERE "Code" = :P_ContractCode;          -- Get next workflow history sequence     SELECT COUNT(*) + 1 INTO V_HistoryCount     FROM "@CM_WORKFLOW_HISTORY"     WHERE "U_DocumentType" = 'CONTRACT' AND "U_DocumentCode" = :P_ContractCode;          V_HistoryCode := 'WF-' || :P_ContractCode || '-' || LPAD(CAST(:V_HistoryCount AS NVARCHAR), 3, '0');          -- Record workflow history     INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         :V_HistoryCode,         'CONTRACT',         :P_ContractCode,         :V_CurrentStatus,         :P_NewStatus,         :P_ChangedBy,         CURRENT_TIMESTAMP,         :P_Comments,         'STATUS_CHANGE'     );          O_Success := 1;     O_ErrorMsg := 'Contract status changed from ' || :V_CurrentStatus || ' to ' || :P_NewStatus;      END;

# 4. HANA STORED PROCEDURES - IPC MODULE

CRITICAL: IPC calculations follow construction industry standards with cascade deduction methodology.

## 4.1 SP_CM_CREATE_IPC - Create New IPC

CREATE PROCEDURE "SP_CM_CREATE_IPC"(     IN "P_ContractCode" NVARCHAR(50),     IN "P_IPCDate" DATE,     IN "P_PeriodFrom" DATE,     IN "P_PeriodTo" DATE,     IN "P_CreatedBy" INTEGER,     OUT "O_IPCCode" NVARCHAR(50),     OUT "O_IPCNumber" INTEGER,     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_Exists INTEGER;     DECLARE V_ContractStatus NVARCHAR(30);     DECLARE V_Counter INTEGER;     DECLARE V_ContractValue DECIMAL(19,6);     DECLARE V_Currency NVARCHAR(3);          -- Initialize outputs     O_Success := 0;     O_ErrorMsg := '';     O_IPCCode := '';     O_IPCNumber := 0;          -- Validate contract exists and is active     SELECT COUNT(*) INTO V_Exists     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Contract not found: ' || :P_ContractCode;         RETURN;     END IF;          -- Get contract details     SELECT "U_Status", "U_TotalValue", "U_Currency"     INTO V_ContractStatus, V_ContractValue, V_Currency     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          -- Check contract is active     IF :V_ContractStatus != 'ACTIVE' THEN         O_ErrorMsg := 'Contract must be ACTIVE to create IPC. Current status: ' || :V_ContractStatus;         RETURN;     END IF;          -- Validate period dates     IF :P_PeriodFrom >= :P_PeriodTo THEN         O_ErrorMsg := 'Period From date must be before Period To date';         RETURN;     END IF;          -- Get next IPC number for this contract     SELECT IFNULL(MAX("U_IPCNumber"), 0) + 1      INTO O_IPCNumber     FROM "@CM_IPC_HDR"     WHERE "U_ContractCode" = :P_ContractCode;          -- Generate IPC Code (Format: IPC-ContractCode-XXX)     O_IPCCode := 'IPC-' || :P_ContractCode || '-' || LPAD(CAST(:O_IPCNumber AS NVARCHAR), 3, '0');          -- Insert IPC Header     INSERT INTO "@CM_IPC_HDR"(         "Code",         "Name",         "U_ContractCode",         "U_IPCNumber",         "U_IPCDate",         "U_PeriodFrom",         "U_PeriodTo",         "U_Status",         "U_CreatedBy",         "U_CreatedDate",         "U_RetentionPct",         "U_VATRate"     )     VALUES(         :O_IPCCode,         'IPC #' || CAST(:O_IPCNumber AS NVARCHAR) || ' - ' || :P_ContractCode,         :P_ContractCode,         :O_IPCNumber,         :P_IPCDate,         :P_PeriodFrom,         :P_PeriodTo,         'DRAFT',         :P_CreatedBy,         CURRENT_TIMESTAMP,         10.00,  -- Default retention 10%         14.00   -- Default VAT 14%     );          -- Create workflow history     INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         'WF-' || :O_IPCCode || '-001',         'IPC',         :O_IPCCode,         NULL,         'DRAFT',         :P_CreatedBy,         CURRENT_TIMESTAMP,         'IPC created',         'CREATE'     );          O_Success := 1;     O_ErrorMsg := 'IPC created successfully: ' || :O_IPCCode;      END;

## 4.2 SP_CM_CALCULATE_IPC - Calculate IPC Values with Cascade Logic

This procedure implements the 12-step cascade calculation methodology per construction industry standards.

CREATE PROCEDURE "SP_CM_CALCULATE_IPC"(     IN "P_IPCCode" NVARCHAR(50),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     -- Variables for calculation     DECLARE V_GrossValue DECIMAL(19,6);     DECLARE V_MaterialOnSite DECIMAL(19,6);     DECLARE V_SubTotal DECIMAL(19,6);     DECLARE V_PreviousCertified DECIMAL(19,6);     DECLARE V_CurrentCertified DECIMAL(19,6);          -- Deduction variables (CASCADE ORDER)     DECLARE V_RetentionPct DECIMAL(5,2);     DECLARE V_RetentionAmount DECIMAL(19,6);     DECLARE V_AfterRetention DECIMAL(19,6);          DECLARE V_AdvancePaymentPct DECIMAL(5,2);     DECLARE V_AdvanceRecovered DECIMAL(19,6);     DECLARE V_AfterAdvanceRecovery DECIMAL(19,6);          DECLARE V_MaterialRecoveryPct DECIMAL(5,2);     DECLARE V_MaterialRecovered DECIMAL(19,6);     DECLARE V_AfterMaterialRecovery DECIMAL(19,6);          DECLARE V_OtherDeductions DECIMAL(19,6);     DECLARE V_NetPayable DECIMAL(19,6);          DECLARE V_VATRate DECIMAL(5,2);     DECLARE V_VATAmount DECIMAL(19,6);     DECLARE V_TotalDue DECIMAL(19,6);          DECLARE V_Exists INTEGER;     DECLARE V_ContractCode NVARCHAR(50);     DECLARE V_ContractValue DECIMAL(19,6);     DECLARE V_CumulativePayments DECIMAL(19,6);          -- Initialize     O_Success := 0;     O_ErrorMsg := '';          -- Validate IPC exists     SELECT COUNT(*) INTO V_Exists     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'IPC not found: ' || :P_IPCCode;         RETURN;     END IF;          -- Get current IPC values and percentages     SELECT          "U_GrossValue",         "U_MaterialOnSite",         "U_RetentionPct",         "U_AdvancePaymentPct",         "U_MaterialRecoveryPct",         "U_OtherDeductions",         "U_VATRate",         "U_ContractCode"     INTO          V_GrossValue,         V_MaterialOnSite,         V_RetentionPct,         V_AdvancePaymentPct,         V_MaterialRecoveryPct,         V_OtherDeductions,         V_VATRate,         V_ContractCode     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          -- Get contract total value     SELECT "U_TotalValue" INTO V_ContractValue     FROM "@CM_CONTRACT"     WHERE "Code" = :V_ContractCode;          -- STEP 1: Calculate SubTotal     V_SubTotal := V_GrossValue + V_MaterialOnSite;          -- STEP 2: Get previous certified amount from all previous IPCs     SELECT IFNULL(SUM("U_CurrentCertified"), 0) INTO V_PreviousCertified     FROM "@CM_IPC_HDR"     WHERE "U_ContractCode" = :V_ContractCode     AND "Code" != :P_IPCCode     AND "U_Status" IN ('APPROVED', 'PAID');          -- STEP 3: Current certified amount     V_CurrentCertified := V_SubTotal - V_PreviousCertified;          -- Validation: Cannot exceed contract value     V_CumulativePayments := V_PreviousCertified + V_CurrentCertified;     IF :V_CumulativePayments > :V_ContractValue THEN         O_ErrorMsg := 'Cumulative payments (' || TO_NVARCHAR(:V_CumulativePayments, '999,999,999.99') ||                        ') would exceed contract value (' || TO_NVARCHAR(:V_ContractValue, '999,999,999.99') || ')';         RETURN;     END IF;          -- CASCADE DEDUCTION CALCULATION (CRITICAL ORDER)          -- STEP 4: Retention Deduction (from Current Certified)     IF :V_RetentionPct > 0 AND :V_CurrentCertified > 0 THEN         V_RetentionAmount := ROUND(:V_CurrentCertified * :V_RetentionPct / 100, 2);     ELSE         V_RetentionAmount := 0;     END IF;     V_AfterRetention := V_CurrentCertified - V_RetentionAmount;          -- STEP 5: Advance Payment Recovery (from amount AFTER retention)     IF :V_AdvancePaymentPct > 0 AND :V_AfterRetention > 0 THEN         V_AdvanceRecovered := ROUND(:V_AfterRetention * :V_AdvancePaymentPct / 100, 2);     ELSE         V_AdvanceRecovered := 0;     END IF;     V_AfterAdvanceRecovery := V_AfterRetention - V_AdvanceRecovered;          -- STEP 6: Material Recovery (from amount AFTER advance recovery)     IF :V_MaterialRecoveryPct > 0 AND :V_AfterAdvanceRecovery > 0 THEN         V_MaterialRecovered := ROUND(:V_AfterAdvanceRecovery * :V_MaterialRecoveryPct / 100, 2);     ELSE         V_MaterialRecovered := 0;     END IF;     V_AfterMaterialRecovery := V_AfterAdvanceRecovery - V_MaterialRecovered;          -- STEP 7: Other Deductions (flat amount from remaining)     V_NetPayable := V_AfterMaterialRecovery - V_OtherDeductions;          -- Ensure net payable is not negative     IF :V_NetPayable < 0 THEN         V_NetPayable := 0;     END IF;          -- STEP 8: VAT Calculation (on net payable)     IF :V_VATRate > 0 AND :V_NetPayable > 0 THEN         V_VATAmount := ROUND(:V_NetPayable * :V_VATRate / 100, 2);     ELSE         V_VATAmount := 0;     END IF;          -- STEP 9: Total Due     V_TotalDue := V_NetPayable + V_VATAmount;          -- Update IPC with all calculated values     UPDATE "@CM_IPC_HDR"     SET          "U_SubTotal" = :V_SubTotal,         "U_PreviousCertified" = :V_PreviousCertified,         "U_CurrentCertified" = :V_CurrentCertified,         "U_RetentionAmount" = :V_RetentionAmount,         "U_AfterRetention" = :V_AfterRetention,         "U_AdvanceRecovered" = :V_AdvanceRecovered,         "U_AfterAdvanceRecovery" = :V_AfterAdvanceRecovery,         "U_MaterialRecovered" = :V_MaterialRecovered,         "U_AfterMaterialRecovery" = :V_AfterMaterialRecovery,         "U_NetPayable" = :V_NetPayable,         "U_VATAmount" = :V_VATAmount,         "U_TotalDue" = :V_TotalDue     WHERE "Code" = :P_IPCCode;          -- Update contract completion percentage     IF :V_ContractValue > 0 THEN         UPDATE "@CM_CONTRACT"         SET "U_CompletionPct" = ROUND((:V_PreviousCertified + :V_CurrentCertified) / :V_ContractValue * 100, 2)         WHERE "Code" = :V_ContractCode;     END IF;          O_Success := 1;     O_ErrorMsg := 'IPC calculations completed successfully. Total Due: ' || TO_NVARCHAR(:V_TotalDue, '999,999,999.99');      END;

## 4.3 SP_CM_CHANGE_IPC_STATUS - Change IPC Status

CREATE PROCEDURE "SP_CM_CHANGE_IPC_STATUS"(     IN "P_IPCCode" NVARCHAR(50),     IN "P_NewStatus" NVARCHAR(30),     IN "P_ChangedBy" INTEGER,     IN "P_Comments" NVARCHAR(500),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_CurrentStatus NVARCHAR(30);     DECLARE V_Allowed INTEGER;     DECLARE V_HistoryCode NVARCHAR(50);     DECLARE V_HistoryCount INTEGER;     DECLARE V_Exists INTEGER;     DECLARE V_TotalDue DECIMAL(19,6);          O_Success := 0;     O_ErrorMsg := '';          -- Check if IPC exists     SELECT COUNT(*) INTO V_Exists     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'IPC not found: ' || :P_IPCCode;         RETURN;     END IF;          -- Get current status     SELECT "U_Status", "U_TotalDue"     INTO V_CurrentStatus, V_TotalDue     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          -- Validate status transitions     -- DRAFT -> SUBMITTED     -- SUBMITTED -> APPROVED or REJECTED     -- APPROVED -> PAID          V_Allowed := 0;          IF :V_CurrentStatus = 'DRAFT' AND :P_NewStatus = 'SUBMITTED' THEN         -- Check calculations are done         IF :V_TotalDue IS NULL OR :V_TotalDue = 0 THEN             O_ErrorMsg := 'Cannot submit IPC with zero or null Total Due. Please calculate first.';             RETURN;         END IF;         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'SUBMITTED' AND (:P_NewStatus = 'APPROVED' OR :P_NewStatus = 'REJECTED') THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'APPROVED' AND :P_NewStatus = 'PAID' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = :P_NewStatus THEN         O_ErrorMsg := 'IPC is already in status: ' || :P_NewStatus;         RETURN;     END IF;          IF :V_Allowed = 0 THEN         O_ErrorMsg := 'Invalid status transition from ' || :V_CurrentStatus || ' to ' || :P_NewStatus;         RETURN;     END IF;          -- Update IPC status     UPDATE "@CM_IPC_HDR"     SET "U_Status" = :P_NewStatus,         "U_ApprovedBy" = CASE WHEN :P_NewStatus = 'APPROVED' THEN :P_ChangedBy ELSE "U_ApprovedBy" END,         "U_ApprovedDate" = CASE WHEN :P_NewStatus = 'APPROVED' THEN CURRENT_TIMESTAMP ELSE "U_ApprovedDate" END     WHERE "Code" = :P_IPCCode;          -- Get next workflow history sequence     SELECT COUNT(*) + 1 INTO V_HistoryCount     FROM "@CM_WORKFLOW_HISTORY"     WHERE "U_DocumentType" = 'IPC' AND "U_DocumentCode" = :P_IPCCode;          V_HistoryCode := 'WF-' || :P_IPCCode || '-' || LPAD(CAST(:V_HistoryCount AS NVARCHAR), 3, '0');          -- Record workflow history     INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         :V_HistoryCode,         'IPC',         :P_IPCCode,         :V_CurrentStatus,         :P_NewStatus,         :P_ChangedBy,         CURRENT_TIMESTAMP,         :P_Comments,         'STATUS_CHANGE'     );          O_Success := 1;     O_ErrorMsg := 'IPC status changed from ' || :V_CurrentStatus || ' to ' || :P_NewStatus;      END;

# 5. DATABASE VIEWS FOR REPORTING

## 5.1 View: Active Contracts

CREATE VIEW "V_CM_ACTIVE_CONTRACTS" AS SELECT      C."Code" AS "ContractCode",     C."Name" AS "ContractName",     C."U_CardCode" AS "CustomerCode",     C."U_CardName" AS "CustomerName",     C."U_ContractType" AS "ContractType",     C."U_StartDate" AS "StartDate",     C."U_EndDate" AS "EndDate",     C."U_TotalValue" AS "TotalValue",     C."U_Currency" AS "Currency",     C."U_CompletionPct" AS "CompletionPct",     C."U_Status" AS "Status",     DAYS_BETWEEN(C."U_StartDate", CURRENT_DATE) AS "DaysElapsed",     DAYS_BETWEEN(CURRENT_DATE, C."U_EndDate") AS "DaysRemaining",     IFNULL(SUM(I."U_TotalDue"), 0) AS "TotalCertified",     C."U_TotalValue" - IFNULL(SUM(I."U_TotalDue"), 0) AS "RemainingValue" FROM "@CM_CONTRACT" C LEFT JOIN "@CM_IPC_HDR" I ON I."U_ContractCode" = C."Code" AND I."U_Status" = 'APPROVED' WHERE C."U_Status" IN ('ACTIVE', 'SUSPENDED') GROUP BY      C."Code", C."Name", C."U_CardCode", C."U_CardName", C."U_ContractType",     C."U_StartDate", C."U_EndDate", C."U_TotalValue", C."U_Currency",     C."U_CompletionPct", C."U_Status";

## 5.2 View: IPC Summary

CREATE VIEW "V_CM_IPC_SUMMARY" AS SELECT      I."Code" AS "IPCCode",     I."Name" AS "IPCName",     I."U_ContractCode" AS "ContractCode",     C."U_CardName" AS "CustomerName",     I."U_IPCNumber" AS "IPCNumber",     I."U_IPCDate" AS "IPCDate",     I."U_GrossValue" AS "GrossValue",     I."U_MaterialOnSite" AS "MaterialOnSite",     I."U_SubTotal" AS "SubTotal",     I."U_CurrentCertified" AS "CurrentCertified",     I."U_RetentionAmount" AS "RetentionAmount",     I."U_NetPayable" AS "NetPayable",     I."U_VATAmount" AS "VATAmount",     I."U_TotalDue" AS "TotalDue",     I."U_Status" AS "Status",     I."U_CreatedDate" AS "CreatedDate",     I."U_ApprovedDate" AS "ApprovedDate",     C."U_TotalValue" AS "ContractValue",     ROUND((I."U_CurrentCertified" / C."U_TotalValue") * 100, 2) AS "PercentOfContract" FROM "@CM_IPC_HDR" I INNER JOIN "@CM_CONTRACT" C ON C."Code" = I."U_ContractCode" WHERE I."U_Status" != 'REJECTED';

# 6. C# HELPER CLASSES

The following helper classes provide database-agnostic implementations for contract and IPC operations.

## 6.1 DatabaseHelper.cs - Database Compatibility Layer

using System; using SAPbobsCOM;  namespace ContractManagementAddon.Utilities {     public static class DatabaseHelper     {         private static BoDataServerTypes? _dbType;                  public static BoDataServerTypes GetDatabaseType(Company company)         {             if (_dbType.HasValue)                 return _dbType.Value;                          _dbType = company.DbServerType;             return _dbType.Value;         }                  public static bool IsHANA(Company company)         {             return GetDatabaseType(company) == BoDataServerTypes.dst_HANADB;         }                  public static bool IsSQLServer(Company company)         {             var dbType = GetDatabaseType(company);             return dbType == BoDataServerTypes.dst_MSSQL2012 ||                    dbType == BoDataServerTypes.dst_MSSQL2014 ||                    dbType == BoDataServerTypes.dst_MSSQL2016 ||                    dbType == BoDataServerTypes.dst_MSSQL2017 ||                    dbType == BoDataServerTypes.dst_MSSQL2019;         }                  public static string GetTopClause(Company company, int count)         {             return IsHANA(company) ? "" : $"TOP {count}";         }                  public static string GetLimitClause(Company company, int count)         {             return IsHANA(company) ? $"LIMIT {count}" : "";         }                  public static string GetNullFunction(Company company, string expression, string replacement)         {             return IsHANA(company) ?                  $"IFNULL({expression}, {replacement})" :                  $"ISNULL({expression}, {replacement})";         }                  public static string GetCurrentDate(Company company)         {             return IsHANA(company) ? "CURRENT_DATE" : "GETDATE()";         }                  public static string GetCurrentTimestamp(Company company)         {             return IsHANA(company) ? "CURRENT_TIMESTAMP" : "GETDATE()";         }                  public static string GetStringConcat(Company company, params string[] values)         {             if (IsHANA(company))                 return string.Join(" || ", values);             else                 return string.Join(" + ", values);         }                  public static string GetDateDiff(Company company, string startDate, string endDate)         {             if (IsHANA(company))                 return $"DAYS_BETWEEN({startDate}, {endDate})";             else                 return $"DATEDIFF(day, {startDate}, {endDate})";         }                  public static string BuildQuery(Company company, string query)         {             if (IsHANA(company))             {                 return query                     .Replace("ISNULL(", "IFNULL(")                     .Replace("GETDATE()", "CURRENT_DATE")                     .Replace("DATEDIFF(day,", "DAYS_BETWEEN(");             }             return query;         }     } }

## 6.2 ContractManager.cs - Business Logic

using System; using SAPbobsCOM;  namespace ContractManagementAddon.BusinessLogic {     public class ContractManager     {         private readonly Company _company;                  public ContractManager(Company company)         {             _company = company;         }                  public (bool success, string contractCode, string message) CreateContract(             string cardCode,             string contractType,             DateTime startDate,             DateTime endDate,             decimal totalValue,             string currency,             string projectCode,             int createdBy)         {             try             {                 if (DatabaseHelper.IsHANA(_company))                 {                     return CreateContractHANA(cardCode, contractType, startDate, endDate,                          totalValue, currency, projectCode, createdBy);                 }                 else                 {                     return CreateContractSQL(cardCode, contractType, startDate, endDate,                          totalValue, currency, projectCode, createdBy);                 }             }             catch (Exception ex)             {                 return (false, "", $"Error creating contract: {ex.Message}");             }         }                  private (bool, string, string) CreateContractHANA(             string cardCode, string contractType, DateTime startDate, DateTime endDate,             decimal totalValue, string currency, string projectCode, int createdBy)         {             var rs = (Recordset)_company.GetBusinessObject(BoObjectTypes.BoRecordset);                          string query = $@"CALL SP_CM_CREATE_CONTRACT(                 '{cardCode}', '{contractType}', '{startDate:yyyy-MM-dd}', '{endDate:yyyy-MM-dd}',                 {totalValue}, '{currency}', '{projectCode}', {createdBy},                 ?, ?, ?)";                          rs.DoQuery(query);                          string contractCode = rs.Fields.Item("O_ContractCode").Value.ToString();             int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);             string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                          return (success == 1, contractCode, message);         }                  private (bool, string, string) CreateContractSQL(             string cardCode, string contractType, DateTime startDate, DateTime endDate,             decimal totalValue, string currency, string projectCode, int createdBy)         {             // Similar implementation for SQL Server using T-SQL stored procedure             // Implementation details omitted for brevity             throw new NotImplementedException("SQL Server version pending");         }                  public (bool success, string message) ChangeContractStatus(             string contractCode,             string newStatus,             int changedBy,             string comments)         {             try             {                 var rs = (Recordset)_company.GetBusinessObject(BoObjectTypes.BoRecordset);                                  string query = DatabaseHelper.IsHANA(_company) ?                     $@"CALL SP_CM_CHANGE_CONTRACT_STATUS(                         '{contractCode}', '{newStatus}', {changedBy}, '{comments}', ?, ?)" :                     $@"EXEC SP_CM_CHANGE_CONTRACT_STATUS                         '{contractCode}', '{newStatus}', {changedBy}, '{comments}'";                                  rs.DoQuery(query);                                  int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);                 string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                                  return (success == 1, message);             }             catch (Exception ex)             {                 return (false, $"Error changing contract status: {ex.Message}");             }         }     } }

## 6.3 IPCManager.cs - IPC Business Logic

using System; using SAPbobsCOM;  namespace ContractManagementAddon.BusinessLogic {     public class IPCManager     {         private readonly Company _company;                  public IPCManager(Company company)         {             _company = company;         }                  public (bool success, string ipcCode, int ipcNumber, string message) CreateIPC(             string contractCode,             DateTime ipcDate,             DateTime periodFrom,             DateTime periodTo,             int createdBy)         {             try             {                 var rs = (Recordset)_company.GetBusinessObject(BoObjectTypes.BoRecordset);                                  string query = DatabaseHelper.IsHANA(_company) ?                     $@"CALL SP_CM_CREATE_IPC(                         '{contractCode}', '{ipcDate:yyyy-MM-dd}',                          '{periodFrom:yyyy-MM-dd}', '{periodTo:yyyy-MM-dd}',                         {createdBy}, ?, ?, ?, ?)" :                     $@"EXEC SP_CM_CREATE_IPC                         '{contractCode}', '{ipcDate:yyyy-MM-dd}',                          '{periodFrom:yyyy-MM-dd}', '{periodTo:yyyy-MM-dd}',                         {createdBy}";                                  rs.DoQuery(query);                                  string ipcCode = rs.Fields.Item("O_IPCCode").Value.ToString();                 int ipcNumber = Convert.ToInt32(rs.Fields.Item("O_IPCNumber").Value);                 int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);                 string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                                  return (success == 1, ipcCode, ipcNumber, message);             }             catch (Exception ex)             {                 return (false, "", 0, $"Error creating IPC: {ex.Message}");             }         }                  public (bool success, string message) CalculateIPC(string ipcCode)         {             try             {                 var rs = (Recordset)_company.GetBusinessObject(BoObjectTypes.BoRecordset);                                  string query = DatabaseHelper.IsHANA(_company) ?                     $"CALL SP_CM_CALCULATE_IPC('{ipcCode}', ?, ?)" :                     $"EXEC SP_CM_CALCULATE_IPC '{ipcCode}'";                                  rs.DoQuery(query);                                  int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);                 string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                                  return (success == 1, message);             }             catch (Exception ex)             {                 return (false, $"Error calculating IPC: {ex.Message}");             }         }                  public (bool success, string message) ChangeIPCStatus(             string ipcCode,             string newStatus,             int changedBy,             string comments)         {             try             {                 var rs = (Recordset)_company.GetBusinessObject(BoObjectTypes.BoRecordset);                                  string query = DatabaseHelper.IsHANA(_company) ?                     $@"CALL SP_CM_CHANGE_IPC_STATUS(                         '{ipcCode}', '{newStatus}', {changedBy}, '{comments}', ?, ?)" :                     $@"EXEC SP_CM_CHANGE_IPC_STATUS                         '{ipcCode}', '{newStatus}', {changedBy}, '{comments}'";                                  rs.DoQuery(query);                                  int success = Convert.ToInt32(rs.Fields.Item("O_Success").Value);                 string message = rs.Fields.Item("O_ErrorMsg").Value.ToString();                                  return (success == 1, message);             }             catch (Exception ex)             {                 return (false, $"Error changing IPC status: {ex.Message}");             }         }     } }

# 7. USAGE EXAMPLES

## 7.1 Creating a Contract

// Example: Create new contract var contractMgr = new ContractManager(SAPCompany);  var result = contractMgr.CreateContract(     cardCode: "C00001",     contractType: "CONSTRUCTION",     startDate: new DateTime(2025, 1, 1),     endDate: new DateTime(2026, 12, 31),     totalValue: 5000000.00m,     currency: "EGP",     projectCode: "PROJ-2025-001",     createdBy: 1 );  if (result.success) {     SAPApplication.StatusBar.SetText(         $"Contract created: {result.contractCode}",          BoMessageTime.bmt_Short,          BoStatusBarMessageType.smt_Success     ); } else {     SAPApplication.StatusBar.SetText(         result.message,          BoMessageTime.bmt_Medium,          BoStatusBarMessageType.smt_Error     ); }

## 7.2 Creating and Calculating IPC

// Example: Create and calculate IPC var ipcMgr = new IPCManager(SAPCompany);  // Step 1: Create IPC var createResult = ipcMgr.CreateIPC(     contractCode: "CT-2025-00001",     ipcDate: DateTime.Today,     periodFrom: new DateTime(2025, 1, 1),     periodTo: new DateTime(2025, 1, 31),     createdBy: 1 );  if (createResult.success) {     // Step 2: Calculate IPC     var calcResult = ipcMgr.CalculateIPC(createResult.ipcCode);          if (calcResult.success)     {         SAPApplication.StatusBar.SetText(             $"IPC #{createResult.ipcNumber} calculated successfully",              BoMessageTime.bmt_Short,              BoStatusBarMessageType.smt_Success         );     } }

# 8. DEPLOYMENT CHECKLIST

| Task | Status |
| --- | --- |
| 1. Backup production database | ☐ |
| 2. Create custom tables (@CM_CONTRACT, @CM_IPC_HDR, @CM_IPC_LINES, @CM_WORKFLOW_HISTORY) | ☐ |
| 3. Create indexes for performance optimization | ☐ |
| 4. Deploy stored procedures (SP_CM_CREATE_CONTRACT, SP_CM_CHANGE_CONTRACT_STATUS, SP_CM_CREATE_IPC, SP_CM_CALCULATE_IPC, SP_CM_CHANGE_IPC_STATUS) | ☐ |
| 5. Create database views (V_CM_ACTIVE_CONTRACTS, V_CM_IPC_SUMMARY) | ☐ |
| 6. Test stored procedures in test environment | ☐ |
| 7. Deploy add-on DLL to SAP B1 AddOns directory | ☐ |
| 8. Test complete workflow (Contract creation → IPC creation → Calculation → Approval) | ☐ |
| 9. Verify IPC cascade calculations with sample data | ☐ |
| 10. User acceptance testing (UAT) | ☐ |
| 11. Production deployment and monitoring | ☐ |

--- End of Document 9 ---

Document 10: Complete HANA Database Scripts

# TABLE OF CONTENTS

1. Overview and Database Schema

2. Complete Table Creation Scripts

3. Index Creation Scripts

4. Contract Management Stored Procedures

5. IPC Management Stored Procedures

6. Workflow Management Procedures

7. Database Views

8. Database Triggers

9. Utility Procedures

10. Deployment Scripts

# 1. OVERVIEW AND DATABASE SCHEMA

Purpose: This document contains complete, production-ready SAP HANA database scripts for the Contract Management Add-On. All scripts are optimized for HANA column store and use SQLScript language.

## 1.1 HANA-Specific Features Used

| Feature | Description |
| --- | --- |
| Column Store Tables | All tables use CREATE COLUMN TABLE for optimal HANA performance |
| SQLScript Procedures | Native HANA stored procedures with LANGUAGE SQLSCRIPT |
| IFNULL Function | HANA-specific NULL handling function |
| DAYS_BETWEEN | HANA date difference function |
| ¦¦ Concatenation | HANA string concatenation operator |

# 2. COMPLETE TABLE CREATION SCRIPTS

Execute these scripts in order. All scripts include DROP IF EXISTS for safe re-deployment.

## 2.1 Contract Master Table

-- ================================================ -- CONTRACT MASTER TABLE -- Table: @CM_CONTRACT -- Purpose: Stores all contract header information -- ================================================  -- Drop table if exists (for re-deployment) DROP TABLE "@CM_CONTRACT" CASCADE;  -- Create Contract Master Table CREATE COLUMN TABLE "@CM_CONTRACT" (     "Code" NVARCHAR(50) NOT NULL,     "Name" NVARCHAR(200) NOT NULL,          -- Customer Information     "U_CardCode" NVARCHAR(15) NOT NULL,     "U_CardName" NVARCHAR(100) NOT NULL,          -- Contract Details     "U_ContractType" NVARCHAR(20) NOT NULL,     "U_StartDate" DATE NOT NULL,     "U_EndDate" DATE NOT NULL,     "U_TotalValue" DECIMAL(19,6) NOT NULL,     "U_Currency" NVARCHAR(3) DEFAULT 'EGP',          -- Status and Progress     "U_Status" NVARCHAR(30) DEFAULT 'DRAFT',     "U_CompletionPct" DECIMAL(5,2) DEFAULT 0,          -- Audit Fields     "U_CreatedBy" INTEGER,     "U_CreatedDate" TIMESTAMP DEFAULT CURRENT_TIMESTAMP,     "U_ModifiedBy" INTEGER,     "U_ModifiedDate" TIMESTAMP,     "U_ApprovedBy" INTEGER,     "U_ApprovedDate" TIMESTAMP,          -- Additional Fields     "U_ProjectCode" NVARCHAR(30),     "U_DepartmentCode" NVARCHAR(20),     "U_Notes" NVARCHAR(500),     "U_AttachmentPath" NVARCHAR(500),          -- Constraints     PRIMARY KEY ("Code") );  -- Comments for documentation COMMENT ON TABLE "@CM_CONTRACT" IS 'Contract Master Table - stores all contract headers'; COMMENT ON COLUMN "@CM_CONTRACT"."Code" IS 'Unique contract code (Format: CT-YYYY-XXXXX)'; COMMENT ON COLUMN "@CM_CONTRACT"."U_Status" IS 'Contract status: DRAFT, SUBMITTED, APPROVED, ACTIVE, SUSPENDED, COMPLETED, CANCELLED'; COMMENT ON COLUMN "@CM_CONTRACT"."U_CompletionPct" IS 'Completion percentage (0-100)';

## 2.2 IPC Header Table

-- ================================================ -- IPC HEADER TABLE -- Table: @CM_IPC_HDR -- Purpose: Stores Interim Payment Certificate headers -- ================================================  -- Drop table if exists DROP TABLE "@CM_IPC_HDR" CASCADE;  -- Create IPC Header Table CREATE COLUMN TABLE "@CM_IPC_HDR" (     "Code" NVARCHAR(50) NOT NULL,     "Name" NVARCHAR(200) NOT NULL,          -- Reference to Contract     "U_ContractCode" NVARCHAR(50) NOT NULL,     "U_IPCNumber" INTEGER NOT NULL,     "U_IPCDate" DATE NOT NULL,     "U_PeriodFrom" DATE NOT NULL,     "U_PeriodTo" DATE NOT NULL,          -- Gross Values (Step 1-3)     "U_GrossValue" DECIMAL(19,6) DEFAULT 0,     "U_MaterialOnSite" DECIMAL(19,6) DEFAULT 0,     "U_SubTotal" DECIMAL(19,6) DEFAULT 0,     "U_PreviousCertified" DECIMAL(19,6) DEFAULT 0,     "U_CurrentCertified" DECIMAL(19,6) DEFAULT 0,          -- Deduction 1: Retention (Step 4)     "U_RetentionPct" DECIMAL(5,2) DEFAULT 10,     "U_RetentionAmount" DECIMAL(19,6) DEFAULT 0,     "U_AfterRetention" DECIMAL(19,6) DEFAULT 0,          -- Deduction 2: Advance Payment Recovery (Step 5)     "U_AdvancePaymentPct" DECIMAL(5,2) DEFAULT 0,     "U_AdvanceRecovered" DECIMAL(19,6) DEFAULT 0,     "U_AfterAdvanceRecovery" DECIMAL(19,6) DEFAULT 0,          -- Deduction 3: Material Recovery (Step 6)     "U_MaterialRecoveryPct" DECIMAL(5,2) DEFAULT 0,     "U_MaterialRecovered" DECIMAL(19,6) DEFAULT 0,     "U_AfterMaterialRecovery" DECIMAL(19,6) DEFAULT 0,          -- Deduction 4: Other Deductions (Step 7)     "U_OtherDeductions" DECIMAL(19,6) DEFAULT 0,     "U_NetPayable" DECIMAL(19,6) DEFAULT 0,          -- VAT Calculation (Step 8-9)     "U_VATRate" DECIMAL(5,2) DEFAULT 14,     "U_VATAmount" DECIMAL(19,6) DEFAULT 0,     "U_TotalDue" DECIMAL(19,6) DEFAULT 0,          -- Status and Audit     "U_Status" NVARCHAR(30) DEFAULT 'DRAFT',     "U_CreatedBy" INTEGER,     "U_CreatedDate" TIMESTAMP DEFAULT CURRENT_TIMESTAMP,     "U_ApprovedBy" INTEGER,     "U_ApprovedDate" TIMESTAMP,     "U_Notes" NVARCHAR(500),          -- Constraints     PRIMARY KEY ("Code"),     FOREIGN KEY ("U_ContractCode") REFERENCES "@CM_CONTRACT"("Code") );  -- Comments COMMENT ON TABLE "@CM_IPC_HDR" IS 'IPC Header - Interim Payment Certificates with cascade calculation'; COMMENT ON COLUMN "@CM_IPC_HDR"."U_RetentionPct" IS 'Retention percentage (typically 10%)'; COMMENT ON COLUMN "@CM_IPC_HDR"."U_Status" IS 'IPC status: DRAFT, SUBMITTED, APPROVED, REJECTED, PAID';

## 2.3 IPC Line Items Table

-- ================================================ -- IPC LINE ITEMS TABLE -- Table: @CM_IPC_LINES -- Purpose: Stores detailed line items for each IPC -- ================================================  -- Drop table if exists DROP TABLE "@CM_IPC_LINES" CASCADE;  -- Create IPC Lines Table CREATE COLUMN TABLE "@CM_IPC_LINES" (     "Code" NVARCHAR(50) NOT NULL,     "LineId" INTEGER NOT NULL,          -- Item Information     "U_ItemCode" NVARCHAR(20),     "U_ItemName" NVARCHAR(100),     "U_Description" NVARCHAR(200),     "U_UOM" NVARCHAR(20),          -- Contract Quantities and Rates     "U_ContractQty" DECIMAL(19,6) NOT NULL,     "U_ContractRate" DECIMAL(19,6) NOT NULL,     "U_ContractValue" DECIMAL(19,6) NOT NULL,          -- Execution Quantities     "U_PreviousQty" DECIMAL(19,6) DEFAULT 0,     "U_CurrentQty" DECIMAL(19,6) DEFAULT 0,     "U_CumulativeQty" DECIMAL(19,6) DEFAULT 0,          -- Calculated Values     "U_CurrentValue" DECIMAL(19,6) DEFAULT 0,     "U_CompletionPct" DECIMAL(5,2) DEFAULT 0,          "U_Notes" NVARCHAR(200),          -- Constraints     PRIMARY KEY ("Code", "LineId"),     FOREIGN KEY ("Code") REFERENCES "@CM_IPC_HDR"("Code") );  -- Comments COMMENT ON TABLE "@CM_IPC_LINES" IS 'IPC Line Items - detailed breakdown of work items'; COMMENT ON COLUMN "@CM_IPC_LINES"."U_CumulativeQty" IS 'Cumulative quantity = PreviousQty + CurrentQty';

## 2.4 Workflow History Table

-- ================================================ -- WORKFLOW HISTORY TABLE -- Table: @CM_WORKFLOW_HISTORY -- Purpose: Audit trail for all status changes -- ================================================  -- Drop table if exists DROP TABLE "@CM_WORKFLOW_HISTORY" CASCADE;  -- Create Workflow History Table CREATE COLUMN TABLE "@CM_WORKFLOW_HISTORY" (     "Code" NVARCHAR(50) NOT NULL,     "U_DocumentType" NVARCHAR(20) NOT NULL,     "U_DocumentCode" NVARCHAR(50) NOT NULL,     "U_FromStatus" NVARCHAR(30),     "U_ToStatus" NVARCHAR(30) NOT NULL,     "U_ChangedBy" INTEGER NOT NULL,     "U_ChangeDate" TIMESTAMP DEFAULT CURRENT_TIMESTAMP,     "U_Comments" NVARCHAR(500),     "U_ActionType" NVARCHAR(20),          -- Constraints     PRIMARY KEY ("Code") );  -- Comments COMMENT ON TABLE "@CM_WORKFLOW_HISTORY" IS 'Workflow History - audit trail for status changes'; COMMENT ON COLUMN "@CM_WORKFLOW_HISTORY"."U_DocumentType" IS 'Document type: CONTRACT or IPC'; COMMENT ON COLUMN "@CM_WORKFLOW_HISTORY"."U_ActionType" IS 'Action type: CREATE, STATUS_CHANGE, APPROVE, REJECT';

# 3. INDEX CREATION SCRIPTS

Performance optimization indexes. Execute after table creation.

-- ================================================ -- PERFORMANCE INDEXES -- Purpose: Optimize query performance -- ================================================  -- Contract Table Indexes CREATE INDEX "IX_CONTRACT_Status" ON "@CM_CONTRACT"("U_Status"); CREATE INDEX "IX_CONTRACT_Customer" ON "@CM_CONTRACT"("U_CardCode"); CREATE INDEX "IX_CONTRACT_Dates" ON "@CM_CONTRACT"("U_StartDate", "U_EndDate"); CREATE INDEX "IX_CONTRACT_Type" ON "@CM_CONTRACT"("U_ContractType"); CREATE INDEX "IX_CONTRACT_Project" ON "@CM_CONTRACT"("U_ProjectCode");  -- IPC Header Indexes CREATE INDEX "IX_IPC_Contract" ON "@CM_IPC_HDR"("U_ContractCode"); CREATE INDEX "IX_IPC_Status" ON "@CM_IPC_HDR"("U_Status"); CREATE INDEX "IX_IPC_Date" ON "@CM_IPC_HDR"("U_IPCDate"); CREATE INDEX "IX_IPC_Number" ON "@CM_IPC_HDR"("U_ContractCode", "U_IPCNumber"); CREATE INDEX "IX_IPC_Period" ON "@CM_IPC_HDR"("U_PeriodFrom", "U_PeriodTo");  -- IPC Lines Indexes CREATE INDEX "IX_IPC_LINES_Item" ON "@CM_IPC_LINES"("U_ItemCode"); CREATE INDEX "IX_IPC_LINES_IPC" ON "@CM_IPC_LINES"("Code");  -- Workflow History Indexes CREATE INDEX "IX_WORKFLOW_Doc" ON "@CM_WORKFLOW_HISTORY"("U_DocumentType", "U_DocumentCode"); CREATE INDEX "IX_WORKFLOW_Date" ON "@CM_WORKFLOW_HISTORY"("U_ChangeDate"); CREATE INDEX "IX_WORKFLOW_User" ON "@CM_WORKFLOW_HISTORY"("U_ChangedBy");

# 4. CONTRACT MANAGEMENT STORED PROCEDURES

## 4.1 SP_CM_CREATE_CONTRACT - Create New Contract

Complete production-ready procedure with full validation

-- ================================================ -- CREATE CONTRACT PROCEDURE -- Procedure: SP_CM_CREATE_CONTRACT -- Purpose: Create new contract with auto-numbering -- ================================================  DROP PROCEDURE "SP_CM_CREATE_CONTRACT";  CREATE PROCEDURE "SP_CM_CREATE_CONTRACT"(     IN "P_CardCode" NVARCHAR(15),     IN "P_ContractType" NVARCHAR(20),     IN "P_StartDate" DATE,     IN "P_EndDate" DATE,     IN "P_TotalValue" DECIMAL(19,6),     IN "P_Currency" NVARCHAR(3),     IN "P_ProjectCode" NVARCHAR(30),     IN "P_DepartmentCode" NVARCHAR(20),     IN "P_Notes" NVARCHAR(500),     IN "P_CreatedBy" INTEGER,     OUT "O_ContractCode" NVARCHAR(50),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_Counter INTEGER;     DECLARE V_Year NVARCHAR(4);     DECLARE V_CardName NVARCHAR(100);     DECLARE V_Exists INTEGER;     DECLARE V_ValidUser INTEGER;          -- Initialize outputs     O_ErrorMsg := '';     O_ContractCode := '';     O_Success := 0;          -- ========================================     -- VALIDATION SECTION     -- ========================================          -- Validate Business Partner exists     SELECT COUNT(*) INTO V_Exists     FROM "OCRD"     WHERE "CardCode" = :P_CardCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Error: Business Partner not found. Code: ' || :P_CardCode;         RETURN;     END IF;          -- Get Business Partner Name     SELECT "CardName" INTO V_CardName     FROM "OCRD"     WHERE "CardCode" = :P_CardCode;          -- Validate User exists     SELECT COUNT(*) INTO V_ValidUser     FROM "OUSR"     WHERE "INTERNAL_K" = :P_CreatedBy;          IF :V_ValidUser = 0 THEN         O_ErrorMsg := 'Error: Invalid user ID: ' || CAST(:P_CreatedBy AS NVARCHAR);         RETURN;     END IF;          -- Validate Dates     IF :P_StartDate >= :P_EndDate THEN         O_ErrorMsg := 'Error: Start Date must be before End Date';         RETURN;     END IF;          IF :P_StartDate < CURRENT_DATE THEN         O_ErrorMsg := 'Warning: Start Date is in the past. Are you sure?';         -- Note: This is a warning, not an error, so we continue     END IF;          -- Validate Total Value     IF :P_TotalValue <= 0 THEN         O_ErrorMsg := 'Error: Total Value must be greater than zero';         RETURN;     END IF;          -- Validate Contract Type     IF :P_ContractType NOT IN ('CONSTRUCTION', 'MAINTENANCE', 'SUPPLY', 'SERVICE', 'CONSULTING') THEN         O_ErrorMsg := 'Error: Invalid Contract Type. Must be: CONSTRUCTION, MAINTENANCE, SUPPLY, SERVICE, or CONSULTING';         RETURN;     END IF;          -- Validate Currency     IF :P_Currency NOT IN (SELECT "CurrCode" FROM "OCRN") THEN         O_ErrorMsg := 'Error: Invalid Currency Code: ' || :P_Currency;         RETURN;     END IF;          -- ========================================     -- CONTRACT CODE GENERATION     -- ========================================          -- Generate Contract Code (Format: CT-YYYY-XXXXX)     V_Year := TO_NVARCHAR(:P_StartDate, 'YYYY');          -- Get next sequence number for this year     SELECT IFNULL(MAX(CAST(SUBSTRING("Code", 9, 5) AS INTEGER)), 0) + 1      INTO V_Counter     FROM "@CM_CONTRACT"     WHERE LEFT("Code", 7) = 'CT-' || :V_Year;          -- Format: CT-2025-00001     O_ContractCode := 'CT-' || :V_Year || '-' || LPAD(CAST(:V_Counter AS NVARCHAR), 5, '0');          -- ========================================     -- INSERT CONTRACT     -- ========================================          INSERT INTO "@CM_CONTRACT"(         "Code",         "Name",         "U_CardCode",         "U_CardName",         "U_ContractType",         "U_StartDate",         "U_EndDate",         "U_TotalValue",         "U_Currency",         "U_Status",         "U_CompletionPct",         "U_ProjectCode",         "U_DepartmentCode",         "U_Notes",         "U_CreatedBy",         "U_CreatedDate"     )     VALUES(         :O_ContractCode,         :V_CardName || ' - ' || :P_ContractType || ' Contract',         :P_CardCode,         :V_CardName,         :P_ContractType,         :P_StartDate,         :P_EndDate,         :P_TotalValue,         :P_Currency,         'DRAFT',         0,         :P_ProjectCode,         :P_DepartmentCode,         :P_Notes,         :P_CreatedBy,         CURRENT_TIMESTAMP     );          -- ========================================     -- WORKFLOW HISTORY     -- ========================================          INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         'WF-' || :O_ContractCode || '-001',         'CONTRACT',         :O_ContractCode,         NULL,         'DRAFT',         :P_CreatedBy,         CURRENT_TIMESTAMP,         'Contract created successfully',         'CREATE'     );          -- ========================================     -- SUCCESS     -- ========================================          O_Success := 1;     O_ErrorMsg := 'Contract created successfully: ' || :O_ContractCode ||                    ' | Customer: ' || :V_CardName ||                    ' | Value: ' || TO_NVARCHAR(:P_TotalValue, '999,999,999.99') || ' ' || :P_Currency;      END;

## 4.2 SP_CM_CHANGE_CONTRACT_STATUS - Change Contract Status

-- ================================================ -- CHANGE CONTRACT STATUS PROCEDURE -- Procedure: SP_CM_CHANGE_CONTRACT_STATUS -- Purpose: Change contract status with workflow validation -- ================================================  DROP PROCEDURE "SP_CM_CHANGE_CONTRACT_STATUS";  CREATE PROCEDURE "SP_CM_CHANGE_CONTRACT_STATUS"(     IN "P_ContractCode" NVARCHAR(50),     IN "P_NewStatus" NVARCHAR(30),     IN "P_ChangedBy" INTEGER,     IN "P_Comments" NVARCHAR(500),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_CurrentStatus NVARCHAR(30);     DECLARE V_Allowed INTEGER;     DECLARE V_HistoryCode NVARCHAR(50);     DECLARE V_HistoryCount INTEGER;     DECLARE V_Exists INTEGER;     DECLARE V_CardName NVARCHAR(100);          -- Initialize outputs     O_Success := 0;     O_ErrorMsg := '';          -- Check if contract exists     SELECT COUNT(*) INTO V_Exists     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Error: Contract not found: ' || :P_ContractCode;         RETURN;     END IF;          -- Get current status and customer     SELECT "U_Status", "U_CardName" INTO V_CurrentStatus, V_CardName     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          -- ========================================     -- WORKFLOW VALIDATION     -- Valid Transitions:     -- DRAFT -> SUBMITTED     -- SUBMITTED -> APPROVED | REJECTED     -- APPROVED -> ACTIVE     -- ACTIVE -> COMPLETED | SUSPENDED | CANCELLED     -- SUSPENDED -> ACTIVE     -- COMPLETED -> Cannot change     -- REJECTED -> DRAFT (reopen)     -- CANCELLED -> Cannot change     -- ========================================          V_Allowed := 0;          -- Check valid transitions     IF :V_CurrentStatus = 'DRAFT' AND :P_NewStatus = 'SUBMITTED' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'SUBMITTED' AND :P_NewStatus IN ('APPROVED', 'REJECTED') THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'APPROVED' AND :P_NewStatus = 'ACTIVE' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'ACTIVE' AND :P_NewStatus IN ('COMPLETED', 'SUSPENDED', 'CANCELLED') THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'SUSPENDED' AND :P_NewStatus = 'ACTIVE' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = 'REJECTED' AND :P_NewStatus = 'DRAFT' THEN         V_Allowed := 1;     ELSEIF :V_CurrentStatus = :P_NewStatus THEN         O_ErrorMsg := 'Error: Contract is already in status: ' || :P_NewStatus;         RETURN;     ELSEIF :V_CurrentStatus IN ('COMPLETED', 'CANCELLED') THEN         O_ErrorMsg := 'Error: Cannot change status of ' || :V_CurrentStatus || ' contract';         RETURN;     END IF;          IF :V_Allowed = 0 THEN         O_ErrorMsg := 'Error: Invalid status transition from ' || :V_CurrentStatus || ' to ' || :P_NewStatus ||                        '. Please check workflow rules.';         RETURN;     END IF;          -- ========================================     -- UPDATE CONTRACT     -- ========================================          UPDATE "@CM_CONTRACT"     SET          "U_Status" = :P_NewStatus,         "U_ModifiedBy" = :P_ChangedBy,         "U_ModifiedDate" = CURRENT_TIMESTAMP,         "U_ApprovedBy" = CASE WHEN :P_NewStatus = 'APPROVED' THEN :P_ChangedBy ELSE "U_ApprovedBy" END,         "U_ApprovedDate" = CASE WHEN :P_NewStatus = 'APPROVED' THEN CURRENT_TIMESTAMP ELSE "U_ApprovedDate" END     WHERE "Code" = :P_ContractCode;          -- ========================================     -- WORKFLOW HISTORY     -- ========================================          -- Get next sequence number     SELECT COUNT(*) + 1 INTO V_HistoryCount     FROM "@CM_WORKFLOW_HISTORY"     WHERE "U_DocumentType" = 'CONTRACT'      AND "U_DocumentCode" = :P_ContractCode;          V_HistoryCode := 'WF-' || :P_ContractCode || '-' || LPAD(CAST(:V_HistoryCount AS NVARCHAR), 3, '0');          -- Insert workflow record     INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         :V_HistoryCode,         'CONTRACT',         :P_ContractCode,         :V_CurrentStatus,         :P_NewStatus,         :P_ChangedBy,         CURRENT_TIMESTAMP,         :P_Comments,         'STATUS_CHANGE'     );          -- ========================================     -- SUCCESS     -- ========================================          O_Success := 1;     O_ErrorMsg := 'Status changed successfully: ' || :V_CurrentStatus || ' → ' || :P_NewStatus ||                    ' | Contract: ' || :P_ContractCode || ' | Customer: ' || :V_CardName;      END;

# 5. IPC MANAGEMENT STORED PROCEDURES

CRITICAL: IPC procedures implement 12-step cascade calculation per construction industry standards.

## 5.1 SP_CM_CREATE_IPC - Create New IPC

-- ================================================ -- CREATE IPC PROCEDURE -- Procedure: SP_CM_CREATE_IPC -- Purpose: Create new IPC with validation -- ================================================  DROP PROCEDURE "SP_CM_CREATE_IPC";  CREATE PROCEDURE "SP_CM_CREATE_IPC"(     IN "P_ContractCode" NVARCHAR(50),     IN "P_IPCDate" DATE,     IN "P_PeriodFrom" DATE,     IN "P_PeriodTo" DATE,     IN "P_CreatedBy" INTEGER,     OUT "O_IPCCode" NVARCHAR(50),     OUT "O_IPCNumber" INTEGER,     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_Exists INTEGER;     DECLARE V_ContractStatus NVARCHAR(30);     DECLARE V_ContractValue DECIMAL(19,6);     DECLARE V_Currency NVARCHAR(3);     DECLARE V_CardName NVARCHAR(100);     DECLARE V_ContractStart DATE;     DECLARE V_ContractEnd DATE;          -- Initialize outputs     O_Success := 0;     O_ErrorMsg := '';     O_IPCCode := '';     O_IPCNumber := 0;          -- ========================================     -- VALIDATION SECTION     -- ========================================          -- Validate contract exists     SELECT COUNT(*) INTO V_Exists     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Error: Contract not found: ' || :P_ContractCode;         RETURN;     END IF;          -- Get contract details     SELECT          "U_Status",          "U_TotalValue",          "U_Currency",         "U_CardName",         "U_StartDate",         "U_EndDate"     INTO          V_ContractStatus,          V_ContractValue,          V_Currency,         V_CardName,         V_ContractStart,         V_ContractEnd     FROM "@CM_CONTRACT"     WHERE "Code" = :P_ContractCode;          -- Check contract is ACTIVE     IF :V_ContractStatus != 'ACTIVE' THEN         O_ErrorMsg := 'Error: Contract must be ACTIVE to create IPC. Current status: ' || :V_ContractStatus;         RETURN;     END IF;          -- Validate period dates     IF :P_PeriodFrom >= :P_PeriodTo THEN         O_ErrorMsg := 'Error: Period From date must be before Period To date';         RETURN;     END IF;          -- Validate period is within contract dates     IF :P_PeriodFrom < :V_ContractStart OR :P_PeriodTo > :V_ContractEnd THEN         O_ErrorMsg := 'Warning: IPC period is outside contract duration. Continue with caution.';         -- This is a warning, not a blocking error     END IF;          -- Validate IPC date     IF :P_IPCDate > CURRENT_DATE THEN         O_ErrorMsg := 'Error: IPC Date cannot be in the future';         RETURN;     END IF;          -- ========================================     -- IPC NUMBER GENERATION     -- ========================================          -- Get next IPC number for this contract     SELECT IFNULL(MAX("U_IPCNumber"), 0) + 1      INTO O_IPCNumber     FROM "@CM_IPC_HDR"     WHERE "U_ContractCode" = :P_ContractCode;          -- Generate IPC Code (Format: IPC-CT-YYYY-XXXXX-NNN)     O_IPCCode := 'IPC-' || :P_ContractCode || '-' || LPAD(CAST(:O_IPCNumber AS NVARCHAR), 3, '0');          -- ========================================     -- INSERT IPC     -- ========================================          INSERT INTO "@CM_IPC_HDR"(         "Code",         "Name",         "U_ContractCode",         "U_IPCNumber",         "U_IPCDate",         "U_PeriodFrom",         "U_PeriodTo",         "U_Status",         "U_CreatedBy",         "U_CreatedDate",         "U_RetentionPct",         "U_VATRate"     )     VALUES(         :O_IPCCode,         'IPC #' || CAST(:O_IPCNumber AS NVARCHAR) || ' - ' || :V_CardName,         :P_ContractCode,         :O_IPCNumber,         :P_IPCDate,         :P_PeriodFrom,         :P_PeriodTo,         'DRAFT',         :P_CreatedBy,         CURRENT_TIMESTAMP,         10.00,  -- Default retention 10%         14.00   -- Default VAT 14% (Egypt)     );          -- ========================================     -- WORKFLOW HISTORY     -- ========================================          INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         'WF-' || :O_IPCCode || '-001',         'IPC',         :O_IPCCode,         NULL,         'DRAFT',         :P_CreatedBy,         CURRENT_TIMESTAMP,         'IPC created successfully',         'CREATE'     );          -- ========================================     -- SUCCESS     -- ========================================          O_Success := 1;     O_ErrorMsg := 'IPC created successfully: ' || :O_IPCCode ||                    ' | IPC #' || CAST(:O_IPCNumber AS NVARCHAR) ||                   ' | Period: ' || TO_NVARCHAR(:P_PeriodFrom, 'DD/MM/YYYY') ||                    ' to ' || TO_NVARCHAR(:P_PeriodTo, 'DD/MM/YYYY');      END;

## 5.2 SP_CM_CALCULATE_IPC - Calculate IPC with 12-Step Cascade

This is the most critical procedure - implements construction industry standard cascade calculations

-- ================================================ -- CALCULATE IPC PROCEDURE (12-STEP CASCADE) -- Procedure: SP_CM_CALCULATE_IPC -- Purpose: Calculate IPC values using cascade methodology --  -- CALCULATION FLOW: -- Step 1-3: Gross calculations -- Step 4: Retention (10% of current certified) -- Step 5: Advance recovery (from after retention) -- Step 6: Material recovery (from after advance) -- Step 7: Other deductions (flat amount) -- Step 8-9: VAT calculation -- ================================================  DROP PROCEDURE "SP_CM_CALCULATE_IPC";  CREATE PROCEDURE "SP_CM_CALCULATE_IPC"(     IN "P_IPCCode" NVARCHAR(50),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     -- Calculation variables     DECLARE V_GrossValue DECIMAL(19,6);     DECLARE V_MaterialOnSite DECIMAL(19,6);     DECLARE V_SubTotal DECIMAL(19,6);     DECLARE V_PreviousCertified DECIMAL(19,6);     DECLARE V_CurrentCertified DECIMAL(19,6);          -- CASCADE deduction variables     DECLARE V_RetentionPct DECIMAL(5,2);     DECLARE V_RetentionAmount DECIMAL(19,6);     DECLARE V_AfterRetention DECIMAL(19,6);          DECLARE V_AdvancePaymentPct DECIMAL(5,2);     DECLARE V_AdvanceRecovered DECIMAL(19,6);     DECLARE V_AfterAdvanceRecovery DECIMAL(19,6);          DECLARE V_MaterialRecoveryPct DECIMAL(5,2);     DECLARE V_MaterialRecovered DECIMAL(19,6);     DECLARE V_AfterMaterialRecovery DECIMAL(19,6);          DECLARE V_OtherDeductions DECIMAL(19,6);     DECLARE V_NetPayable DECIMAL(19,6);          DECLARE V_VATRate DECIMAL(5,2);     DECLARE V_VATAmount DECIMAL(19,6);     DECLARE V_TotalDue DECIMAL(19,6);          -- Validation variables     DECLARE V_Exists INTEGER;     DECLARE V_ContractCode NVARCHAR(50);     DECLARE V_ContractValue DECIMAL(19,6);     DECLARE V_CumulativePayments DECIMAL(19,6);     DECLARE V_IPCNumber INTEGER;          -- Initialize     O_Success := 0;     O_ErrorMsg := '';          -- ========================================     -- VALIDATION     -- ========================================          -- Validate IPC exists     SELECT COUNT(*) INTO V_Exists     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Error: IPC not found: ' || :P_IPCCode;         RETURN;     END IF;          -- ========================================     -- GET CURRENT VALUES     -- ========================================          SELECT          "U_GrossValue",         "U_MaterialOnSite",         "U_RetentionPct",         "U_AdvancePaymentPct",         "U_MaterialRecoveryPct",         "U_OtherDeductions",         "U_VATRate",         "U_ContractCode",         "U_IPCNumber"     INTO          V_GrossValue,         V_MaterialOnSite,         V_RetentionPct,         V_AdvancePaymentPct,         V_MaterialRecoveryPct,         V_OtherDeductions,         V_VATRate,         V_ContractCode,         V_IPCNumber     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          -- Get contract total value     SELECT "U_TotalValue" INTO V_ContractValue     FROM "@CM_CONTRACT"     WHERE "Code" = :V_ContractCode;          -- ========================================     -- STEP 1-3: GROSS VALUE CALCULATION     -- ========================================          -- Step 1: SubTotal = Gross + Material on Site     V_SubTotal := V_GrossValue + V_MaterialOnSite;          -- Step 2: Get previous certified amount (all previous APPROVED/PAID IPCs)     SELECT IFNULL(SUM("U_CurrentCertified"), 0) INTO V_PreviousCertified     FROM "@CM_IPC_HDR"     WHERE "U_ContractCode" = :V_ContractCode     AND "Code" != :P_IPCCode     AND "U_Status" IN ('APPROVED', 'PAID');          -- Step 3: Current certified = SubTotal - Previous     V_CurrentCertified := V_SubTotal - V_PreviousCertified;          -- Validation: Ensure non-negative     IF :V_CurrentCertified < 0 THEN         V_CurrentCertified := 0;     END IF;          -- ========================================     -- CUMULATIVE VALIDATION     -- ========================================          V_CumulativePayments := V_PreviousCertified + V_CurrentCertified;          IF :V_CumulativePayments > :V_ContractValue THEN         O_ErrorMsg := 'Error: Cumulative payments (' ||                        TO_NVARCHAR(:V_CumulativePayments, '999,999,999.99') ||                        ') exceed contract value (' ||                        TO_NVARCHAR(:V_ContractValue, '999,999,999.99') || ')';         RETURN;     END IF;          -- ========================================     -- CASCADE DEDUCTION CALCULATION     -- CRITICAL: Order matters!     -- ========================================          -- STEP 4: RETENTION DEDUCTION (from Current Certified)     IF :V_RetentionPct > 0 AND :V_CurrentCertified > 0 THEN         V_RetentionAmount := ROUND(:V_CurrentCertified * :V_RetentionPct / 100, 2);     ELSE         V_RetentionAmount := 0;     END IF;     V_AfterRetention := V_CurrentCertified - V_RetentionAmount;          -- STEP 5: ADVANCE PAYMENT RECOVERY (from AFTER retention)     IF :V_AdvancePaymentPct > 0 AND :V_AfterRetention > 0 THEN         V_AdvanceRecovered := ROUND(:V_AfterRetention * :V_AdvancePaymentPct / 100, 2);     ELSE         V_AdvanceRecovered := 0;     END IF;     V_AfterAdvanceRecovery := V_AfterRetention - V_AdvanceRecovered;          -- STEP 6: MATERIAL RECOVERY (from AFTER advance recovery)     IF :V_MaterialRecoveryPct > 0 AND :V_AfterAdvanceRecovery > 0 THEN         V_MaterialRecovered := ROUND(:V_AfterAdvanceRecovery * :V_MaterialRecoveryPct / 100, 2);     ELSE         V_MaterialRecovered := 0;     END IF;     V_AfterMaterialRecovery := V_AfterAdvanceRecovery - V_MaterialRecovered;          -- STEP 7: OTHER DEDUCTIONS (flat amount from remaining)     V_NetPayable := V_AfterMaterialRecovery - V_OtherDeductions;          -- Ensure net payable is not negative     IF :V_NetPayable < 0 THEN         V_NetPayable := 0;     END IF;          -- ========================================     -- STEP 8-9: VAT CALCULATION     -- ========================================          -- Step 8: VAT on net payable     IF :V_VATRate > 0 AND :V_NetPayable > 0 THEN         V_VATAmount := ROUND(:V_NetPayable * :V_VATRate / 100, 2);     ELSE         V_VATAmount := 0;     END IF;          -- Step 9: Total Due     V_TotalDue := V_NetPayable + V_VATAmount;          -- ========================================     -- UPDATE IPC WITH CALCULATED VALUES     -- ========================================          UPDATE "@CM_IPC_HDR"     SET          -- Gross values         "U_SubTotal" = :V_SubTotal,         "U_PreviousCertified" = :V_PreviousCertified,         "U_CurrentCertified" = :V_CurrentCertified,                  -- Cascade deductions         "U_RetentionAmount" = :V_RetentionAmount,         "U_AfterRetention" = :V_AfterRetention,         "U_AdvanceRecovered" = :V_AdvanceRecovered,         "U_AfterAdvanceRecovery" = :V_AfterAdvanceRecovery,         "U_MaterialRecovered" = :V_MaterialRecovered,         "U_AfterMaterialRecovery" = :V_AfterMaterialRecovery,                  -- Final amounts         "U_NetPayable" = :V_NetPayable,         "U_VATAmount" = :V_VATAmount,         "U_TotalDue" = :V_TotalDue     WHERE "Code" = :P_IPCCode;          -- ========================================     -- UPDATE CONTRACT COMPLETION %     -- ========================================          IF :V_ContractValue > 0 THEN         UPDATE "@CM_CONTRACT"         SET "U_CompletionPct" = ROUND((:V_PreviousCertified + :V_CurrentCertified) / :V_ContractValue * 100, 2),             "U_ModifiedDate" = CURRENT_TIMESTAMP         WHERE "Code" = :V_ContractCode;     END IF;          -- ========================================     -- SUCCESS WITH DETAILED SUMMARY     -- ========================================          O_Success := 1;     O_ErrorMsg := 'IPC #' || CAST(:V_IPCNumber AS NVARCHAR) || ' calculated successfully' ||                   ' | Gross: ' || TO_NVARCHAR(:V_GrossValue, '999,999,999.99') ||                   ' | Current Certified: ' || TO_NVARCHAR(:V_CurrentCertified, '999,999,999.99') ||                   ' | Retention: ' || TO_NVARCHAR(:V_RetentionAmount, '999,999,999.99') ||                   ' | Net Payable: ' || TO_NVARCHAR(:V_NetPayable, '999,999,999.99') ||                   ' | VAT: ' || TO_NVARCHAR(:V_VATAmount, '999,999,999.99') ||                   ' | Total Due: ' || TO_NVARCHAR(:V_TotalDue, '999,999,999.99');      END;

## 5.3 SP_CM_CHANGE_IPC_STATUS - Change IPC Status

-- ================================================ -- CHANGE IPC STATUS PROCEDURE -- Procedure: SP_CM_CHANGE_IPC_STATUS -- Purpose: Change IPC status with workflow validation -- ================================================  DROP PROCEDURE "SP_CM_CHANGE_IPC_STATUS";  CREATE PROCEDURE "SP_CM_CHANGE_IPC_STATUS"(     IN "P_IPCCode" NVARCHAR(50),     IN "P_NewStatus" NVARCHAR(30),     IN "P_ChangedBy" INTEGER,     IN "P_Comments" NVARCHAR(500),     OUT "O_Success" INTEGER,     OUT "O_ErrorMsg" NVARCHAR(500) ) LANGUAGE SQLSCRIPT AS BEGIN     DECLARE V_CurrentStatus NVARCHAR(30);     DECLARE V_Allowed INTEGER;     DECLARE V_HistoryCode NVARCHAR(50);     DECLARE V_HistoryCount INTEGER;     DECLARE V_Exists INTEGER;     DECLARE V_TotalDue DECIMAL(19,6);     DECLARE V_IPCNumber INTEGER;     DECLARE V_ContractCode NVARCHAR(50);          O_Success := 0;     O_ErrorMsg := '';          -- Check if IPC exists     SELECT COUNT(*) INTO V_Exists     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          IF :V_Exists = 0 THEN         O_ErrorMsg := 'Error: IPC not found: ' || :P_IPCCode;         RETURN;     END IF;          -- Get current status and values     SELECT          "U_Status",          "U_TotalDue",         "U_IPCNumber",         "U_ContractCode"     INTO          V_CurrentStatus,          V_TotalDue,         V_IPCNumber,         V_ContractCode     FROM "@CM_IPC_HDR"     WHERE "Code" = :P_IPCCode;          -- ========================================     -- WORKFLOW VALIDATION     -- Valid Transitions:     -- DRAFT -> SUBMITTED     -- SUBMITTED -> APPROVED | REJECTED     -- APPROVED -> PAID     -- PAID -> Cannot change     -- REJECTED -> DRAFT (reopen)     -- ========================================          V_Allowed := 0;          IF :V_CurrentStatus = 'DRAFT' AND :P_NewStatus = 'SUBMITTED' THEN         -- Check calculations are done         IF :V_TotalDue IS NULL OR :V_TotalDue = 0 THEN             O_ErrorMsg := 'Error: Cannot submit IPC with zero Total Due. Please calculate IPC first.';             RETURN;         END IF;         V_Allowed := 1;              ELSEIF :V_CurrentStatus = 'SUBMITTED' AND :P_NewStatus IN ('APPROVED', 'REJECTED') THEN         V_Allowed := 1;              ELSEIF :V_CurrentStatus = 'APPROVED' AND :P_NewStatus = 'PAID' THEN         V_Allowed := 1;              ELSEIF :V_CurrentStatus = 'REJECTED' AND :P_NewStatus = 'DRAFT' THEN         V_Allowed := 1;              ELSEIF :V_CurrentStatus = :P_NewStatus THEN         O_ErrorMsg := 'Error: IPC is already in status: ' || :P_NewStatus;         RETURN;              ELSEIF :V_CurrentStatus = 'PAID' THEN         O_ErrorMsg := 'Error: Cannot change status of PAID IPC';         RETURN;     END IF;          IF :V_Allowed = 0 THEN         O_ErrorMsg := 'Error: Invalid status transition from ' || :V_CurrentStatus || ' to ' || :P_NewStatus;         RETURN;     END IF;          -- ========================================     -- UPDATE IPC     -- ========================================          UPDATE "@CM_IPC_HDR"     SET          "U_Status" = :P_NewStatus,         "U_ApprovedBy" = CASE WHEN :P_NewStatus = 'APPROVED' THEN :P_ChangedBy ELSE "U_ApprovedBy" END,         "U_ApprovedDate" = CASE WHEN :P_NewStatus = 'APPROVED' THEN CURRENT_TIMESTAMP ELSE "U_ApprovedDate" END     WHERE "Code" = :P_IPCCode;          -- ========================================     -- WORKFLOW HISTORY     -- ========================================          -- Get next sequence     SELECT COUNT(*) + 1 INTO V_HistoryCount     FROM "@CM_WORKFLOW_HISTORY"     WHERE "U_DocumentType" = 'IPC'      AND "U_DocumentCode" = :P_IPCCode;          V_HistoryCode := 'WF-' || :P_IPCCode || '-' || LPAD(CAST(:V_HistoryCount AS NVARCHAR), 3, '0');          INSERT INTO "@CM_WORKFLOW_HISTORY"(         "Code",         "U_DocumentType",         "U_DocumentCode",         "U_FromStatus",         "U_ToStatus",         "U_ChangedBy",         "U_ChangeDate",         "U_Comments",         "U_ActionType"     )     VALUES(         :V_HistoryCode,         'IPC',         :P_IPCCode,         :V_CurrentStatus,         :P_NewStatus,         :P_ChangedBy,         CURRENT_TIMESTAMP,         :P_Comments,         'STATUS_CHANGE'     );          -- ========================================     -- SUCCESS     -- ========================================          O_Success := 1;     O_ErrorMsg := 'IPC #' || CAST(:V_IPCNumber AS NVARCHAR) ||                    ' status changed: ' || :V_CurrentStatus || ' → ' || :P_NewStatus ||                   ' | Contract: ' || :V_ContractCode;      END;

# 6. DATABASE VIEWS FOR REPORTING

## 6.1 V_CM_ACTIVE_CONTRACTS - Active Contracts View

-- ================================================ -- ACTIVE CONTRACTS VIEW -- View: V_CM_ACTIVE_CONTRACTS -- Purpose: Dashboard view for active contracts -- ================================================  DROP VIEW "V_CM_ACTIVE_CONTRACTS";  CREATE VIEW "V_CM_ACTIVE_CONTRACTS" AS SELECT      C."Code" AS "ContractCode",     C."Name" AS "ContractName",     C."U_CardCode" AS "CustomerCode",     C."U_CardName" AS "CustomerName",     C."U_ContractType" AS "ContractType",     C."U_StartDate" AS "StartDate",     C."U_EndDate" AS "EndDate",     C."U_TotalValue" AS "TotalValue",     C."U_Currency" AS "Currency",     C."U_CompletionPct" AS "CompletionPct",     C."U_Status" AS "Status",     C."U_ProjectCode" AS "ProjectCode",          -- Time calculations     DAYS_BETWEEN(C."U_StartDate", CURRENT_DATE) AS "DaysElapsed",     DAYS_BETWEEN(CURRENT_DATE, C."U_EndDate") AS "DaysRemaining",     DAYS_BETWEEN(C."U_StartDate", C."U_EndDate") AS "TotalDuration",          -- Payment calculations     IFNULL(SUM(CASE WHEN I."U_Status" IN ('APPROVED', 'PAID') THEN I."U_TotalDue" ELSE 0 END), 0) AS "TotalCertified",     C."U_TotalValue" - IFNULL(SUM(CASE WHEN I."U_Status" IN ('APPROVED', 'PAID') THEN I."U_TotalDue" ELSE 0 END), 0) AS "RemainingValue",          -- IPC statistics     COUNT(I."Code") AS "TotalIPCs",     SUM(CASE WHEN I."U_Status" = 'DRAFT' THEN 1 ELSE 0 END) AS "DraftIPCs",     SUM(CASE WHEN I."U_Status" = 'APPROVED' THEN 1 ELSE 0 END) AS "ApprovedIPCs",          -- Latest IPC     MAX(I."U_IPCDate") AS "LastIPCDate",     MAX(I."U_IPCNumber") AS "LastIPCNumber"      FROM "@CM_CONTRACT" C LEFT JOIN "@CM_IPC_HDR" I ON I."U_ContractCode" = C."Code" WHERE C."U_Status" IN ('ACTIVE', 'SUSPENDED') GROUP BY      C."Code", C."Name", C."U_CardCode", C."U_CardName", C."U_ContractType",     C."U_StartDate", C."U_EndDate", C."U_TotalValue", C."U_Currency",     C."U_CompletionPct", C."U_Status", C."U_ProjectCode";

## 6.2 V_CM_IPC_SUMMARY - IPC Summary View

-- ================================================ -- IPC SUMMARY VIEW -- View: V_CM_IPC_SUMMARY -- Purpose: Comprehensive IPC reporting view -- ================================================  DROP VIEW "V_CM_IPC_SUMMARY";  CREATE VIEW "V_CM_IPC_SUMMARY" AS SELECT      I."Code" AS "IPCCode",     I."Name" AS "IPCName",     I."U_ContractCode" AS "ContractCode",     C."U_CardCode" AS "CustomerCode",     C."U_CardName" AS "CustomerName",     I."U_IPCNumber" AS "IPCNumber",     I."U_IPCDate" AS "IPCDate",     I."U_PeriodFrom" AS "PeriodFrom",     I."U_PeriodTo" AS "PeriodTo",          -- Gross values     I."U_GrossValue" AS "GrossValue",     I."U_MaterialOnSite" AS "MaterialOnSite",     I."U_SubTotal" AS "SubTotal",     I."U_PreviousCertified" AS "PreviousCertified",     I."U_CurrentCertified" AS "CurrentCertified",          -- Deductions     I."U_RetentionAmount" AS "RetentionAmount",     I."U_AdvanceRecovered" AS "AdvanceRecovered",     I."U_MaterialRecovered" AS "MaterialRecovered",     I."U_OtherDeductions" AS "OtherDeductions",          -- Final amounts     I."U_NetPayable" AS "NetPayable",     I."U_VATAmount" AS "VATAmount",     I."U_TotalDue" AS "TotalDue",          -- Status and dates     I."U_Status" AS "Status",     I."U_CreatedDate" AS "CreatedDate",     I."U_ApprovedDate" AS "ApprovedDate",          -- Contract information     C."U_TotalValue" AS "ContractValue",     C."U_Currency" AS "Currency",     C."U_ContractType" AS "ContractType",          -- Calculated fields     ROUND((I."U_CurrentCertified" / C."U_TotalValue") * 100, 2) AS "PercentOfContract",     DAYS_BETWEEN(I."U_PeriodFrom", I."U_PeriodTo") AS "PeriodDays",     DAYS_BETWEEN(I."U_IPCDate", CURRENT_DATE) AS "DaysSinceIPC"      FROM "@CM_IPC_HDR" I INNER JOIN "@CM_CONTRACT" C ON C."Code" = I."U_ContractCode" WHERE I."U_Status" != 'REJECTED' ORDER BY I."U_ContractCode", I."U_IPCNumber";

# 7. DEPLOYMENT GUIDE

Execute scripts in this exact order:

| Step | Script | Status |
| --- | --- | --- |
| 1 | Backup production database | ☐ |
| 2 | Section 2: Create all tables (@CM_CONTRACT, @CM_IPC_HDR, @CM_IPC_LINES, @CM_WORKFLOW_HISTORY) | ☐ |
| 3 | Section 3: Create all indexes for performance | ☐ |
| 4 | Section 4: Deploy contract procedures (SP_CM_CREATE_CONTRACT, SP_CM_CHANGE_CONTRACT_STATUS) | ☐ |
| 5 | Section 5: Deploy IPC procedures (SP_CM_CREATE_IPC, SP_CM_CALCULATE_IPC, SP_CM_CHANGE_IPC_STATUS) | ☐ |
| 6 | Section 6: Create database views (V_CM_ACTIVE_CONTRACTS, V_CM_IPC_SUMMARY) | ☐ |
| 7 | Test contract creation: CALL SP_CM_CREATE_CONTRACT(...) | ☐ |
| 8 | Test IPC creation and calculation: CALL SP_CM_CREATE_IPC(...) then CALL SP_CM_CALCULATE_IPC(...) | ☐ |
| 9 | Verify cascade calculations with test data | ☐ |
| 10 | Deploy SAP B1 Add-On application | ☐ |

--- END OF DOCUMENT 10 ---

Complete SAP HANA Database Scripts

Ready for Production Deployment

Document 11 Screenshots

- ERD diagram

- Contract UX

- Dashboard UX